Terms of Reference

For consultancy service to conduct

Conflict, Political, Economic and Security Assessment (COPESA)

| Date of issue: | Tuesday, 26 December 2023 |
| --- | --- |
| Project title: | 12207 - MIDEEYE Project: Support of the National Reconciliation and Local Governance in Somalia |
| Deadline for submission of offers: | Monday, 15 January 2024 at 23:50 P.M. (East Africa Time Zone) |
| Contracting authority: | FCA Somalia Country Office Contact : Procurement Committee E-mail: tenders.soco@kirkonulkomaanapu.fi |

# Introduction and background information

FCA Somalia Country Office is looking for qualified consultant(s) to undertake Conflict, Political, Economic and Security Assessment (COPESA), under ‘MIDEEYE Project - Support of the National Reconciliation and Local Governance in Somalia’, in January 2024, in the districts of Mahas, Adaale, and Hobyo, in Somalia.

FCA is the biggest development and humanitarian aid organization in Finland. FCA is currently operating in 13 countries in Asia, Africa and Middle East and is specialized in three thematic priority areas: Right to Peace (R2P), Right to Livelihood (R2L) and Right to Quality Education (R2QE). In Somalia, FCA began its operation in 2007 through support to peace building initiatives in Somaliland and Puntland. Following the success of the interventions, FCA Somalia expanded its operation to other parts of South Central of Somalia in 2013, evolving from community level peace building initiatives to state building and state formation interventions at FGS and FMS levels. FCA Somalia also facilitated the state formation process between 2014 and 2015 which resulted in the formation of the Galmudug State.

At the request of the Somali government and with the generous financial support of the Ministry for Foreign Affairs of Finland (MFA Finland), the FCA Somalia together with the Network for Religious and Traditional Peacemakers (NRTP) hosted by FCA, provide support to the Ministry of Interior, Federal Affairs and Reconciliation (MoIFAR), in leading the development process and implementation of the National Reconciliation Framework (NRF) through MIDEEYE project, until end of the year 2024.

# Background information on MIDEEYE project

MIDEEYE project is a joint initiative of FCA and NRTP. MIDEEYE, translates as “unifier” from Somali, to illustrate its aim to create trust and social cohesion by strengthening efficiency and inclusivity of governance on several levels. MIDEEYE is aiming to contribute to Somalia’s peacebuilding efforts by addressing need for wholistic reconciliation and strengthening inclusive governance. MIDEEYE’s approach to reconciliation is largely informed by the National Reconciliation Framework (NRF), a strategy document jointly drafted by Ministry of Interior, Federal Affairs and Reconciliation (MoIFAR), FCA, and NRTP alongside other actors in 2017 and approved by the FGS and cabinet members in 2019. The NRF frames the reconciliatory process in terms of repair of social relationships and the rebuilding of trust between conflicting communities. In order to realize key objectives outlined in the NFR and contribute to national peace and state-building, the FCA defined MIDEEYE goals as follows:

- Outcome 1: Increasing the capacity of the Federal Government and selected FMS to implement the NFR and thereby strengthening the legitimacy and trust in government institutions, and

- Outcome 2: Improving inclusive governance and administration in selected Federal Member States (FMS) to achieve more effective service delivery, in line with the NFR and Wadajir National Framework for local governance.

The four-year (2021 to 2024) MIDEEYE project supports key government institutions, such as the MoIs and district councils, traditional leaders, leaders of women’s groups, and youth representatives in selected FMS.

# COPESA Assessment Objectives

Overall Objectives of the COPESA Assessment

The MIDEEYE project utilizes evidence-based approach to its programming and implementation. Mahas, Adaale, and Hobyo districts of Somalia, have been selected as some of the districts that could receive support for the district council formation process (DCF) under the MIDEEYE project. To design and implement a district council formation process that is inclusive to local community stakeholders, mindful of current socio-political realities, and responsive to the priorities and support needs of the stakeholders in these districts, a Conflict, Political, Economic and Security Assessment (COPESA) needs to be carried out.

Primary purpose of the COPESA is to provide FCA and relevant partners, a detailed analysis report to assesses the status of factors and community perceptions, that contribute to design of the DCF process, and provides baseline information for the activities to be carried out. This included description and detailed analysis of 1) conflict mapping; actors and types of conflict present, 2) Existing conflict and dispute resolution mechanisms; and identifies needs for reconciliation efforts and maps ongoing processes, 2) governance, 3) overall state of security and access to justice, and 4) political-economy conditions; including mapping main livelihoods and exiting natural resources.

The assessment further aims to identify community priorities in the districts in relation areas of the basic service delivery, mitigation/ and resolution of conflict. This community perception of the priorities will feed into analyses of the small quick-impact projects (SQUIP) to be designed with the communities to help sustain the newly formed district councils. The SQUIP projects will be gender sensitive and the consultations are expected to emphasize the needs of key community stakeholders of the district, inclusive of women, youth and minorities. In addition, assess political economy and security status, and include establishing of a clear picture of political, economic and security situation in the assessment district, and understanding conflict dynamics, historical grievances, and governance structures which can impact the formation of the inclusive district council.

COPESA Assessment Specific objectives for analysis:

COPESA assessment should establish an overview of the following areas in the districts of Mahas, Adaale, and Hobyo;

Conflict assessment: description of the types of conflict and violence present, their root causes, key actors involved, community effects; with particular focus on women, youth and marginalised groups

- Describing existing mitigation measures and conflict resolution practices and alternative dispute resolution mechanism

- Community perception, needs and grievances, including

  - past and present clan conflict drivers and overall conflict dynamics,

  - past peacebuilding efforts (including reconciliation undertakings),

  - actors involved in the region.

- Assess overall district security, including

  - security actors, security providers,

  - accessibility

  - main security challenges,

  - presence of ATMIS, police and SNA forces and other actors

  - safe avenues to implement pre and post district council formation process activities.

  - judiciary systems / institutions, access to justice and dispensation of justice.

- Study existing local administration structures, including:

  - description of authorities and key institutions in the region

  - social services delivery infrastructure andstatus of available social services,

  - current power-sharing arrangements and practices

  - capacity of institutions to provide essential basic services.

- To identify Small Quick Impact Project (SQUIP) that can address the basic needs of the community with emphasis to inclusivity

- Describe the prevalent means of livelihood, development areas or challenges faced, including identifying:

  - main economic sectors, and types of livelihoods

  - existing natural resources and their current management

  - resources and opportunities available for livelihood development

  - livelihood activities women and youth engage in, and

  - any major challenges or developments affecting these in the district

- Provide information about how vulnerable groups are included to decision making processes in the district (youth, women, IDPs, PwDs, and other minorities)

- Provide information about the existing of media and communications landscapes and central platforms of sources of information for community.

# COPESA Assessment Scope of work

- Undertake desk review/secondary analysis of documentation, development and finalizing of data collection tools based on inputs from the team

- Develop detail inception report including study design, sampling and detailed work plan

- Train assessment teams on research instruments and ethical standards

- Undertake fieldwork (field data collection), data analysis interpretation, preparation and submission of draft assessment report

- Incorporate the COPESA assessment report with feedback received from FCA, finalize the report, Presentation of key findings, and submission of the final report.

# COPESA Assessment Specific Deliverables

- One (combined for all the 3 districts) COPESA assessment inception report detailing the assessment methodology, sampling strategy, workplans, and data collection tools.

- Three separate (one for each district) COPESA assessment draft reports that summarizes the key findings based on themes, conclusions, and practical recommendations.

- Three separate (one for each district) finalized COPESA report that takes into account the comments from the FCA Somalia team.

- Three separate (one for each district) summarized version of the COPESA assessment report for external audience.

- Three separate (one for each district) PPT slides for the presentation of the COPESA assessment report key findings for relevant individuals.

# Duration of the COPESA Assessment contract

Duration of this contract is one month and 20 days (50 days).

# COPESA Assessment Duty Station

The consultant(s) will undertake in-country field work and reporting based on agreed work-plan and methodology. The assessment will take place in Mahas, Adaale, and Hobyo, Somalia.

# COPESA Assessment Transport & Logistics

The consultant(s) will cover their field transport and accommodation arrangements, translator and/or interpreter needs, focal points and other contact points on the field and other logistical arrangements concerning consultant’s visit(s).

# COPESA Assessment Methodology

The COPESA assessment is expected to use a mixed method design that combines quantitative and qualitative data collection methods. The data collection methods that use an inclusive and participatory process, attempting to get relevant stakeholders to participate in the assessment exercise, are prioritized.

- Desk review: review of project documents, available governmental documents at federal and member state level (i.e. Wadajir Framework, National Stabilization Strategy, National Reconciliation Framework), key academic literature on the ecosystem of state-building, peace-building,  stabilization and reconciliation, and other conflict and context analysis of Lower Shabelle region and as well as district-level assessments and reports, donor guidelines, and any other relevant literatures.

- Household survey: conduct household surveys from a representative sample of the population from the targeted regions.

- Key informant interviews: interview government officials from the relevant ministries, district administrations, local politicians, opinion leaders, traditional elders, women and youth leaders, community leaders and impactful persons, minorities leaders, etc.

- Focus group discussions: hold discussions with community-based structures and groups to establish snapshot of community situation in terms of access to basic services, clan dynamics, local governance, resources and economic opportunities, access to humanitarian services, community engagements, dialogue and reconciliation activities, justice systems, needs and grievances, conflict and security dynamics, and inclusive decision making processes.

Proposed sampling strategy

The COPESA assessment data collection will use both probabilistic and non-probabilistic sampling designs. These will include stratified sampling, purposive and expert sampling methods. The following sample size calculation formula by Taro Yamane commonly known as Yamane’s formula will be used.

n=sample size,

N=Target population size,

ɛ=critical value of 0.05 at 95% confidence interval.

Substitute with assessment target area(s) values, the above computation yields a sample size of xxx which is approximately xxx HHs. This sample size will then be distributed proportionately between community-based structures and groups such as IDPs and host communities (pastoral, agropastoral, and urban poor) with consideration of minorities, marginalized and PLWDs. This will ensure that information on specific group is not left out during the sampling of the households.

# COPESA Assessment Tenders/Offers Validity

Tenders/Offers shall remain valid and open for acceptance for a period of 30 days after the closing date for the submission.

# COPESA Assessment Timetable

The COPESA Assessment is expected to comply with the following indicative timeframe and set deliverables in the table below.

| Activity Description | Output | Responsible | Timeline | Days |
| --- | --- | --- | --- | --- |
| Desk review/secondary analysis of documentation, development and finalizing of data collection tools based on inputs from the team | Tools and inception report | Consultant | 21st – 24th Jan 2024 | 4 |
| Development of detailed inception report including study design, sampling and detailed work plan |  | Consultant |  |  |
| Review of inception report and data collection tools | Reviewed/ approved inception report and tools | FCA Somalia Team | 25th – 29th Jan 2024 | xx |
| Training of the assessment teams and familiarization on the research instruments | data collection team trained | Consultant and enumerators/ research assistants | 30th Jan - 19th Feb 2024 | 21 |
| Actual fieldwork (field data collection) in the field | Dataset and field notes |  |  |  |
| Data analysis and interpretation, and preparation and submission of draft assessment report | Draft report | Consultant | 20th Feb – 8th March 2024 | 21 |
| Review of the COPESA assessment report by relevant FCA members, providing feedback. | Reviewed draft report | Relevant FCA members | 9th – 14th March 2024 | xx |
| Incorporate the COPESA assessment report with feedback received from FCA, finalize the report, Presentation of key findings, and submission of the final report | Final COPESA assessment report, PPT slides, summarized version of COPESA report | Consultant | 15th – 19th March 2024 | 4 |
| Total # of consultancy days |  |  |  | 50 |

# COPESA Assessment Payment Modalities

The purpose of this section is to provide a detailed payment schedule and modalities against the deliverables. The payments will be processed upon completion of the following milestones.

- 20% after completion, submission and acceptance of COPESA assessment inception report – combined for all the 3 districts.

- 30% after completion, submission and acceptance of detailed COPESA assessment draft reports – separate for each district.

- 50% Submission of final COPESA assessment report completion and acceptance of the report – separate for each district.

# Required expertise and qualification

- Experience in conducting assessments, research, baseline reviews and evaluations on governance and reconciliation related projects in Somalia context.

- In-depth knowledge of the Somalia context, and knowledge of conflict, political, economic and security processes and approaches.

- Minimum 10 years of experience in monitoring and evaluation, with particular focus to quality tools development, qualitative and quantitative data analysis and exceptional report writing skills.

- Bachelor’s degree in economic statistics, developmental studies, peace and conflict management, or other relevant field, OR

- Master in economic statistics, developmental studies, peace and conflict management, or other relevant field.

# Contract award criteria

The purpose of this section is to provide a criteria, weight and scoring information for the final evaluation phase. The offers will be evaluated according to the contract award criteria below:

| # | Description | Weight (%) | Scoring methodology | Score (%) |
| --- | --- | --- | --- | --- |
| 1 | Skills/expertise | 20 | 10 years’ experience in M&E | 5 |
|  |  |  | Between 5- and 9-Year M & E experience | 2 |
|  |  |  | Less than 5 Years M & E experience | 0 |
|  |  |  | Bachelor degree as stated in the TOR | 2 |
|  |  |  | Master’s degree as stated in the TOR | 4 |
|  |  |  | In-depth knowledge and experience in Somalia context as stated in the TOR | 3 |
| 2 | Methodology/ rational/ sampling strategy/ research questions | 35 | Based on the technical proposal submitted by the candidate |  |
|  |  |  | Methodology | 6 |
|  |  |  | Rationale | 4 |
|  |  |  | sampling strategy | 4 |
|  |  |  | research questions | 10 |
| 3 | Experience/sample reports | 20 | Similar sample reports by the candidate |  |
|  |  |  | Up to 3 Similar reports as stated in the TOR | 8 |
|  |  |  | 2 Similar reports as stated in the TOR | 5 |
|  |  |  | 1 Similar report as stated in the TOR | 2 |
| 4 | Availability/timeliness | 5 | Consistency with the COPESA timeframe as indicated in the TOR |  |
|  |  |  | Within or Lesser than proposed Timeframe | 5 |
|  |  |  | Beyond than proposed Timeframe | 0 |
| 5 | Budget | 20 | Lowest bid receives highest score. Other candidates’ scores are calculated proportionally based on the lowest bid. | 40 |
| Overall Total |  | 100 |  | 100 |

# Evaluation Process

The evaluation process is managed by FCA’s Procurement Committee. Candidates will be first evaluated according to the requirements in section 13 - Required Expertise and Qualifications. Candidates which are eligible will be allowed to proceed to the evaluation phase and their offers will be evaluated according to the contract award criteria in section 14.

# Application procedure

Deadline for submission of offers is Monday, 15 January 2024 at 23:50 P.M. (East Africa Time Zone) Candidates must send their offers via email to tenders.soco@kirkonulkomaanapu.fi no later than the deadline as aforementioned. Any tenders received after the deadline will not be considered. Candidates must put “Consultantcy to Conduct COPESA Assessment in the districts of Mahas, Adaale, and Hobyo of Somalia” in the subject line of their emails. No tender may be changed or withdrawn after the deadline has passed. The candidate shall bear all costs associated with the preparation and submission of the offer and the Contracting Authority will in no case be responsible or liable for these costs, regardless of the conduct or outcome of the procurement process. Canvassing will lead to automatic disqualification. Please note, only short-listed candidates will be notified for interview. Thank you!

# Questions

Candidates are not allowed to approach the Contracting Authority for verbal clarification. Any prospective candidate seeking to arrange individual meetings with either the Contracting Authority and/or any other organisation with which the Contracting Authority is associated or linked may be excluded from the tender procedure. Candidates may submit questions in writing via email to the address above latest three days before the deadline.

# Terms of contract

- Confidentiality – Highlight any confidentiality concern

- (Optional) The Consultant is responsible for payment of all social costs, other employment related costs and insurance contributions and for all other liabilities of a statutory nature.

- During the assignment, the consultant does not represent FCA Somalia Country Office and has no mandate to negotiate, make commitments or agree on behalf of FCA Somalia Country Office.

- The consultant is expected to use own computer and other equipment required for the works.

- By submitting an offer, the candidate/consultant/service provider confirms to abide by FCA Somalia Country Office Code of Conduct, Child Safeguarding policy and any other relevant FCA Somalia Country Office policies, same applies to possible enumerators that consultant uses

- The ownership and copyright(s) of the report(s) and any other produced material will remain with FCA Somalia Country Office.

- The Contracting authority may for its own convenience and without charge or liability cancel the tender process at any stage.

# Documents comprising this procurement

Purpose of this section is to provide a list of the documents used in the procurement process. The candidate(s) shall complete and submit the following documents with the tender:

- Technical Proposal including an outline of the proposed methodology, data gathering, etc. (maximum 3 pages)

- Financial Proposal including Indicative budget (maximum 1 page) inclusive of the consultant’s daily rate(s) and other related expenses. Rates should be in US Dollars and inclusive of VAT.

- Candidate CV, Certifications, Reference Letters

- Samples of previous work relevant to the assignment (in English)

- Cover letter including a description of suitability of the consultant(s) (maximum 1 page)

# Annex II – COPESA Assessment Question list

Below an exemplary list of areas for information need to be included in the report and a sets of example questions are provided. The list is indicative to the type of information and analysis that the COPESA should provide, however, the list is not comprehensive. The consultant is expected to develop a methodology as described in this tender under “COPESA Assessment Methodology”.

| Assessment Area | Assessment Questions/ Examples |
| --- | --- |
| - Community perception, needs and grievances - Clan conflict drivers and overall conflict dynamics - Peacebuilding and reconciliation efforts. | - What is the community’s perception on the main causes and enablers of the conflict and grievances? - What is needed to achieve consensus, peace building, reconciliation, and community cohesion? - What is the level of social integration between the IDPs, minorities, refugees, returnees, and host community members in the district? |
| - Overall security dynamics - Security actors and security challenges, - Presence of ATMIS, police and SNA forces - Judiciary, access to justice and dispensation of justice. | - What is the security and justice sector dynamics in the district? - Who are the actors involved in the district’s security and justice sector? - Are security and justice institutions in the area central to growth and achievement of sustainable stability and community cohesion? |
| - Existing local administration structure - Key government institutions - Status of available social services - Capacity of local institutions to provide essential basic services. | - What factors are the drivers that influence trust and legitimacy in government institution by improving inclusivity and effective service delivery? - What is the capacity of local institutions to provide essential basic services to community members? |
| - Economic activities in the district engaged by gender - Challenges and opportunities of economic activities - Local economy gatekeepers. | - What is the current status of women in relation to their access to micro-finance, income generation and viability of their businesses in the district? - What are the different livelihoods opportunities that exists within the assessment area? - What are key economic activities that can yield sustainable impact to governance and conflict resolution? |
| - Prevalent livelihood zones, - Main economic sectors - Economic resources and opportunities, - Economic activities engaged by women and youth | - What is the average socio-economic and demographic status of the households in the district? - What livelihood sectors are most critical local economy drivers? Why? - To what extent do women, youth, IDPs, minorities, PLWDs, have access to sustainable economic activities? - What are the major challenges or obstacles that people face in the efforts to provide for their families? |
| - Understanding decision making structures - Inclusivity in decision making | - What factors influence trust and legitimacy in government institutions? Describe the current decision-making structures in the district. What is working well, what are the main challenges? - How inclusive is governance structure and decision making in the area? What is the role of minorities in the decision making? (concrete figures included) |
| - Local media landscape - Preferred sources of information - Media and conflict relations. | - What media platforms/stations are available and preferred in district? - What is the reach of these communication channels in the district? - To what extend can media influence conflict, reconciliation, governance, peacebuilding? - How the media landscape could be improved? What is the level of inclusiveness and neutrality? |

# Annex II – Technical Proposal Template

To be filled-in by the candidates, in compliance with the following instructions

- Rationale (max. 1 page)

Any comments on the Terms of Reference of importance for the successful execution of activities, in particular its objectives and expected results, thus demonstrating the degree of understanding of the contract. Any comments contradicting the Terms of Reference or falling outside their scope will not form part of the final contract. An opinion on the key issues related to the achievement of the contract objectives and expected results (Optional: An explanation of the risks and assumptions affecting the execution of the contract)

- Proposed Methodology (max. 3 pages)

An outline of the approach proposed for contract implementation.

A list of the proposed activities considered to be necessary to achieve the contract objectives;

The related inputs and outputs.

- Timetable of activities (max 1 page)

The timing, sequence and duration of the proposed activities, taking into account mobilisation time.

# Annex II – Financial Proposal Template

Please provide a detailed financial proposal. Applicants’ proposals must include a detailed and competitive budget inclusive of all fees, costs

and taxes.

|  | Unit cost (in USD) | Description/ Number of days | Total (in USD) |
| --- | --- | --- | --- |
| Consultancy fees | (per day) |  |  |
| Travel |  |  |  |
| Incidentals |  |  |  |
| Accommodation / DSA | (per day) |  |  |
| Materials/Interpreter |  |  |  |
| [Xx] (please fill in if needed) |  |  |  |