Request for Proposal

Terms of Reference for Project Midterm Review

| Date of issue: | 19.12.2023 |
| --- | --- |
| Project title: | 12207 - MIDEEYE Project: Support of the National Reconciliation and Local Governance in Somalia |
| Evaluation target locations | Banadir region, Southwest State, Burhakaba district, Hirshabelle, Warsheik district, Somalia. |
| Deadline for submission of offers: | 8th January 2024 at 13:50 p.m. (East Africa Time Zone) |
| Contracting authority: | FCA Somalia Country Office Contact : Procurement Commitee E-mail: tenders.soco@kirkonulkomaanapu.fi |

# Introduction & Background

FCA Somalia Country Office is looking for qualified independent consultant(s) to undertake project midterm review, under 12207 - MIDEEYE Project: Support of the National Reconciliation and Local Governance in Somalia, between 15th of January and 15th of March 2024.

FCA is the biggest development cooperation organization and second biggest humanitarian aid organization in Finland.  FCA is currently operating in 13 countries in Asia, Africa and the Middle East and is specialized in three thematic priority areas: Right to Peace (R2P), Right to Livelihood (R2L) and Right to Quality Education (R2QE). In Somalia, FCA began its operation in 2007 through support to peace building initiatives in Somaliland and Puntland. Following the success of the interventions, FCA Somalia expanded its operation to other parts of South Central of Somalia in 2013, evolving from community level peace building initiatives to state building and state formation interventions at FGS and FMS levels.

## Background information on MIDEEYE project

MIDEEYE project is a joint initiative of FCA Somalia country office and Network for Religious and Traditional Peacemakers (NRTP). The project is aiming to contribute to Somalia’s peacebuilding efforts by addressing grievances and strengthening inclusive governance. MIDEEYE, translates as “unifier” from Somali to illustrate its aim to create trust and social cohesion by strengthening efficiency and inclusivity of governance on several levels. The project’s approach to reconciliation is largely informed by the National Reconciliation Framework (NRF), a strategy document jointly drafted by the FCA, NRTP, and Ministry of Interior, Federal Affairs and Reconciliation (MoIFAR) in 2017 and approved by the FGS and cabinet members in 2019. The NRF frames the reconciliatory process in terms of repair of social relationships and the rebuilding of trust between conflicting communities.

In order to realize key objectives outlined in the NFR and contribute to national peace and state-building, the FCA defined MIDEEYE goals as follows: (i) Outcome 1: Increasing the capacity of the Federal Government and selected FMS to implement the NFR and thereby strengthening the legitimacy and trust in government institutions, and (ii) Outcome 2: Improving inclusive governance and administration in selected Federal Member States (FMS) to achieve more effective service delivery, in line with the NFR and Wadajir National Framework for local governance. The four-year (2021 to 2024) MIDEEYE direct target groups of the project include a variety of government institutions, such as the MoI and district councils, traditional leaders, leaders of women’s groups, and youth representatives in selected FMS. Note that we will also consider an additional institution, the MoRR, that was established to deliver reconciliation programming in target districts.

## Objectives of the project midterm review

The purpose of the mid-term review is to assess the intended and unintended outcomes of the project and determine the level of the project’s contribution to these outcomes.

The specific objectives of the mid-term review are to:

- Review to what extent the project is addressing beneficiaries’ priorities, designed and implemented in a conflict and gender-sensitive manner, and how learning feeds into changes in project related context and adaptation and respective changes.

- Review the performance of the project, against the project outcomes and/ or impact, and set objectives.

- Review how the project intervention and strategy (i.e. capacity building, multi- stakeholders’ partnership, and others) has transformed available resources to expected outcomes in terms of quantity and quality.

- Identify good practices and lessons learnt related to the project operational contexts, actors engaged, strategies applied in the implementation and changes observed

- Review how partners were involved in project and budget design and management and how effective was the partnership.

- Establish what constitutes sustainability in the Somalia context and analyze the sustained effect of the project activities.

- Review the project baseline assessment report and its findings, and revise the baseline report where necessary, to ensure the report can provide necessary information for the final evaluation.

## Evaluation methodology and process

- Desk Review: Review and analyse documents/evidence collected of harvested outcomes and progress towards results, and test this against project theory of change.

- Focus Group Discussions (FGDs): Conduct focus group discussions with various project target beneficiaries in the project target locations, to receive feedback on how beneficiaries and stakeholders perceived the project.

- Key Informant Interviews (KIIs): conduct interviews project management team, MEAL Manager/Coordinator, partners, communities, relevant government officials and different stakeholders the project is working with.

- Analysis workshop: The evaluator will be expected to hold an analysis workshop with relevant colleagues from FCA and partners to critically make sense of the identified findings and substantiated outcomes.

# Deliverables

The independent evaluator(s) will be expected to submit the following deliverables in time in compliance with standard requirements:

A)

- An inception report detailing mid-term review methodology, work plan/schedule and draft data collection tools.

- Facilitate a presentation of key findings meeting for the project stakeholders after generating the draft midterm review report. A short presentation of outcome findings, insights into contribution pathways and feasible recommendation.

- Mid-term review report, and other documents/materials such as raw data files, quantitative data files, transcripts of interviews, FGDs, etc.

B)

Purpose of the Perception Survey

The Purpose of the perception survey is to assess the impact, needs, gaps and priorities of the local governance interventions in the targeted districts.  In order for target districts to have an increased legitimacy and awareness on social reconciliation by strengthening gender and youth inclusive governance.

Objectives of the Perception Survey

The objective of the perception survey is to explore and document opinions and perceptions of the people regarding the local governance interventions in the targeted districts. The survey will used to measure key project indicator and inform future programming.

Specific Objective of the Perception Survey

•	Assess the extent to which relevant community members were engaged in the project interventions.

•	Understand the level of ownership of the people in the district council formation process in the target districts.

•	Assess the satisfaction level of the population in terms of service delivery of the newly established district councils.

•	Understand the level of awareness of the population on social reconciliation component and the overall state building processes; and

•	Assess the change in behaviour and perception of the people following the media campaigns.

Perception Survey Sampling Methodology

•	The perception survey will use non-probabilistic sampling methods like quota sampling and purposive sampling. Quota sampling methods will be used to generate quantitative data from community groups and members of the community across the two districts. In total, 50 persons will be interviewed (i.e. 25 per district). This sampling method is appropriate for diverse group with specific traits and qualities like age, gender, and community representations etc.

•	Purposive sampling technique will be used to select respondents. The district council and community members will be mobilized to participate the survey.

•	Qualitative and quantitative data will be analysed, cross-referred with project reports such as training reports, pre- and post-training evaluation.

•	Key Informant Interviews (KIIs) will be conducted with district council members and key community members including youth, women, elders, religious leader, businessmen/ women, local politicians, and government officials. The main tool will be KIIs with community members

•	Focus group discussions (FGDs) will be conducted with key community members including youth, women, elders, religious leader, businessmen/ women, local politicians, and government officials.

Perception Survey Ethical Standards

Perception survey respondents was informed of the purpose of the data collection and was asked for consent as to whether they agree to participate the interview or not. At any given time, respondents were assured that they can opt out or skip any questions she/he did not want to answer. Respect respondents’ physical condition, economic background, political inclination, culture, and social norms, were ensured. Enumerators were required to sign a short-term contract with code of conduct on data confidentiality emphasizing; personally identifiable data were kept safe for confidentiality purpose.

Approach, scope, and methods of the Perception Survey

The survey methodology will include mixed quantitative and qualitative methods, and that include the following elements among others:

	A desk review of key documents, including project documents, activity reports, training reports, pre- and post-training evaluation, etc.

	A collaborative approach with project staff, partners, other key stakeholders, government, as appropriate in design, implementation, reporting of the survey.

	A participatory survey with emphasis on capturing a cross-section of views from the target groups, and multi-stakeholder quantitative and qualitative assessment techniques (including key informant interviews, focus group discussions, observations, and others as appropriate).

	The survey is expected to be gender-sensitive, rights-based, inclusive, culturally sensitive and comply with professional ethical standards.

# Evaluation Design Matrix

| Criteria | Evaluation Questions |
| --- | --- |
| Relevance | - To what extent has the design of MIDEEYE project in Somalia addressed the needs in terms of inclusive governance, social reconciliation of the targeted population in the targeted districts? - How appropriate was the project design process to the local context? - How did the project adopt to the changing local political conditions? - How relevant were the project organizational structure and partnerships in achieving results? - What was the extent of the identification and incorporation of real gaps by the project? - To what extent were the identified gaps and needs addressed by the project? |
| Effectiveness | - To what extent has the project objectives been attained or closer to being attained? - To what extent has the project results (outcomes and outputs) been realized? - To what extent have perceptions on inclusive diction-making changed? - To what extent have social norms related to inclusion of women and youth in decision-making changed? - What factors have contributed to the success and failures of reaching the project results and objectives? - How true was the envisaged Theory of Change considering the project implementation? - How were the levels of effectiveness of the various implementation methodologies, approaches and tools used? - How were capacities of the different district councils strengthened? - How has this led to improvement in service delivery? - How effective is the project monitoring, evaluation, accountability and learning systems? - To what extent does the project contributes to overall objectives of donor strategy in Somalia and relevant laws/polices like National Reconciliation Framework, Wadajir National Framework and NDP (2020-2024). |
| Efficiency | - What are the different implementation strategies used by the project in attaining its intended outputs and outcomes? - Have resources (funds, human resources, time, expertise etc) been allocated strategically and used efficiently? - Is the intervention implemented in the most efficient way compared to other alternatives? - Is the budget used appropriately, according to original plans and narratives? - Is there a financial control system in place? - What systems were put in place to ensure project inputs provided were of the highest possible quality and were acceptable to beneficiaries? - Is the budget utilization in accordance with original budget/narrative? - Is the staffing structure appropriate to the project? - To what extent does clear understanding between FCA and its partners on roles and responsibilities exists? - How realistic are the project plans and targets? |
| Coherence and Coordination | - What are the key constraints to coherence and coordination and how did the organization deal with them? - What are the mechanisms used to strengthen the linkages between the different actors at different levels? Federal/state/district/ village - How did FCA representatives/staff interact with government institutions and international and local organization? - How did the project coordinate with or compliment other similar actions in the context-geographically and thematically? - How is the project coordinated with other activities of other agencies operating in the same area? What can be done to improve this level of coordination? - With regards to other NGOs and UN’s JPLG are there some coherences with FCA activities, complementarily, synergy etc.? - How did the project contribute to the overall framework, standards, and policies in the context like LG laws, Wadajir, and Wadahadal civic dialogue frameworks |
| Monitoring | - How has FCA monitored the progress and likelihood of impact of the project? - Is the field level monitoring effective? - What is the relevance and efficiency of the monitoring between Mogadishu and partners’ field offices? - Is there MEAL framework in place for the project? - Are the monitoring tools in place efficient? - Does the monitoring contribute to increased effectiveness in programming? - Are appropriate and relevant indicators developed for monitoring? - Is there any lesson learnt from monitoring/evaluation actions of the project? Have they been shared externally? - What indicators were used to evaluate the positive and negative effects of the programme? |
| Impact | - What direct and indirect evidence exists that shows that the action taken has contributed to the general objective of the project? - What was the situation before intervention and how has it changed because of this intervention? - Is there some negative impact of the project that can be noticed now or that can be foreseen? |
| Sustainability | - What is the level of ownership of project results at local level? - To what extent is the project embedded in the local structures and communities? |

# Duration of contract

Duration of this contract is two month (60 days) – 15th of January,2023 to 15th of March 2024.

# Service Terms

FCA Somalia country office intends to contract qualified consultant(s) for one month (60 days)

# Duty Station

The independent consultant(s) will undertake in-country field work and reporting based on agreed work-plan and methodology. The assessment will take place in, selected states of Somalia.

# Transport & Logistics

The consultant(s) will cover field transport and accommodation arrangements, translator and/or interpreter needs, focal points and other contact points on the field and other logistical arrangements concerning consultant’s visit(s).

# Validity

Offers shall remain valid and open for acceptance for a period of 30 days after the closing date for the submission.

# Tentative Timeline (dates subject to change) and expected deliverables

The project evaluation fieldwork is expected to tentatively start from 15th of Jan .2024 to 15th of March 2024.

| Tasks | Product/deliverables | Time frame |
| --- | --- | --- |
| Inception stage |  |  |
| i. Review relevant literature, previous survey reports ii. Prepare a detailed survey and mapping plan including methodological approach (survey protocol, sampling approach/ framework and tools for assessing the project outcomes and outcome indicators as depicted in the project log-frame) iii. Prepare mapping and survey tools/guidelines for primary data collection iv. Guide/manage the baseline data collection exercise | i. Report on literature review/ brief situation analysis ii. Detailed baseline plan including methodology, sample size, research sites, and data analysis plan. iii. Survey tools and guidelines iv. Guide/ work plan to manage the baseline data collection exercise v. Presentation of the field work plan | 10 days |
| Assessment stage |  |  |
| iv. Administer field visits, FGDs and interviews/ meetings to collect information on the assessment and analyse information. | iv. Information collected and analysed, recommendations and suggestions + raw survey data | 25 days |
| Presentation of Assessment Findings |  |  |
| v. Prepare presentation and present the findings to relevant persons vi. Prepare draft report and finalize the report with FCA comment(s). | v. Power point presentation on the findings of the survey vi. Draft Report (Outline to be finalized with consultant). | 25 days |

# Payment Modalities

The purpose of this section is to provide a detailed payment schedule and modalities against the deliverables. The payments will be processed upon completion of the following milestones.

- 20% payment release after completion, submission, and acceptance of project midterm review inception report.

- 30% payment release after completion, submission and acceptance of detailed project midterm review draft report.

- 50% payment release after submission of final project midterm review report completion and acceptance of the report.

# Required Expertise and Qualification

- Experience in conducting project midterm review, evaluation, assessments, research, and baseline reviews on governance and reconciliation related projects in Somalia context.

- In-depth knowledge of the Somalia context, and knowledge of conflict, political, economic and security processes and approaches.

- Minimum 10 years of experience in monitoring and evaluation, with particular focus to quality tools development, qualitative and quantitative data analysis and exceptional report writing skills.

- Bachelor’s degree in economic statistics, developmental studies, peace and conflict management, or other relevant field.

- Master in economic statistics, developmental studies, peace and conflict management, or other relevant field.

# Contract Award Criteria

The purpose of this section is to provide a criterion, weight and scoring information for the final evaluation phase. The offers will be evaluated according to the contract award criteria below:

| # | Description | Weight (%) | Scoring methodology | Score (%) |
| --- | --- | --- | --- | --- |
| 1 | Skills/expertise | 20 | 10 years’ experience in M&E. master’s degree in development studies and related studies. Experience in Somalia context. (10 Years M & E experience) | 5 |
|  |  |  | Between 5- and 9-Year M & E experience | 2 |
|  |  |  | Less than 5 Years M & E experience | 1 |
|  |  |  | Bachelor’s degree as stated in the TOR | 2 |
|  |  |  | Master’s degree as stated in the TOR | 5 |
|  |  |  | In-depth knowledge and experience in Somalia context as stated in the TOR | 5 |
| 2 | Methodology/ rational/ sampling strategy/ research questions | 30 | Based on the technical proposal submitted by the candidate |  |
|  |  |  | Methodology | 10 |
|  |  |  | Rationale | 5 |
|  |  |  | sampling strategy | 7 |
|  |  |  | research questions | 8 |
| 3 | Experience/sample reports | 25 | Similar sample reports by the candidate |  |
|  |  |  | Up to 3 Similar reports as stated in the TOR | 13 |
|  |  |  | 2 Similar reports as stated in the TOR | 8 |
|  |  |  | 1 Similar report as stated in the TOR | 4 |
| 4 | Availability/timeliness | 5 | Consistency with the project midterm review timeframe as indicated in the TOR | 5 |
|  |  |  | Within or Lesser than proposed Timeframe | 5 |
|  |  |  | Beyond than proposed timeframe | 0 |
| 5 | Budget | 20 | Lowest bid receives highest score. Other candidates’ scores are calculated proportionally based on the lowest bid. | 20 |
| Overall Total |  | 100 |  |  |

# Evaluation Process

The evaluation process is managed by FCA’s Procurement Committee. Candidates will be first evaluated according to the requirements in section 13 - Required Expertise and Qualifications. Candidates which are eligible will be allowed to proceed to the evaluation phase and their offers will be evaluated according to the contract award criteria in section 14.

# Application procedure

Deadline for submission of offers is 8th January 2024 at 13:50 p.m. (East Africa Time Zone). Candidates must send their offers via email to tenders.soco@kirkonulkomaanapu.fi   no later than the deadline as aforementioned. Any tenders received after the deadline will not be considered. Candidates must put “Consultancy to Conduct 12207 – MIDEEYE Project Midterm Review” in the subject line of their emails. No tender may be changed or withdrawn after the deadline has passed. The candidate shall bear all costs associated with the preparation and submission of the offer and the Contracting Authority will in no case be responsible or liable for these costs, regardless of the conduct or outcome of the procurement process. Canvassing will lead to automatic disqualification. Please note, only short-listed candidates will be notified for interview. Thank you!

# Questions

Candidates are not allowed to approach the Contracting Authority for verbal clarification. Any prospective candidate seeking to arrange individual meetings with either the Contracting Authority and/or any other organisation with which the Contracting Authority is associated or linked may be excluded from the tender procedure. Candidates may submit questions in writing via email to the address above latest three days before the deadline.

# Terms of contract

- Confidentiality – Highlight any confidentiality concern

- The Consultant is responsible for payment of all social costs, other employment related costs and insurance contributions and for all other liabilities of a statutory nature.

- During the assignment, the consultant does not represent FCA Somalia Country Office and has no mandate to negotiate, make commitments or agree on behalf of FCA Somalia Country Office.

- The consultant is expected to use own computer and other equipment required for works.

- By submitting an offer, the candidate/consultant/service provider confirms to abide by FCA Somalia Country Office Code of Conduct, Child Safeguarding policy and any other relevant FCA Somalia Country Office policies and laws, culture, and customs of the host country.

- The ownership and copyright(s) of the report(s) and any other produced material will remain with FCA Somalia Country Office.

- The Contracting authority may for its own convenience and without charge or liability cancel the tender process at any stage.

- The consultant shall be responsible for the payment of all applicable federal, state, and local income taxes arising from its activities related to this contract.

# Documents comprising this procurement.

Purpose of this section is to provide a list of the documents used in the procurement process. The candidate(s) shall complete and submit the following documents with the tender:

- Technical Proposal including an outline of the proposed methodology, data gathering, etc. (maximum 3 pages)

- Financial Proposal including Indicative budget (maximum 1 page) inclusive of the consultant’s daily rate(s) and other related expenses. Rates should be in US Dollars.

- Candidate CV, Certifications, Reference Letters

- Samples of previous work relevant to the assignment (in English)

- Cover letter including a description of suitability of the consultant(s) (maximum 1 page)

# Annex I – Technical Proposal Template

To be filled-in by the candidates, in compliance with the following instructions

- Rationale (max. 1 page)

Any comments on the Terms of Reference of importance for the successful execution of activities, in particular its objectives and expected results, thus demonstrating the degree of understanding of the contract. Any comments contradicting the Terms of Reference or falling outside their scope will not form part of the final contract.

An opinion on the key issues related to the achievement of the contract objectives and expected results (Optional: An explanation of the risks and assumptions affecting the execution of the contract)

- Proposed Methodology (max. 3 pages)

An outline of the approach proposed for contract implementation.

A list of the proposed activities considered to be necessary to achieve the contract objectives.

The related inputs and outputs.

- Timetable of activities (max 1 page)

The timing, sequence, and duration of the proposed activities, taking into account mobilization time.

# Annex II – Financial Proposal Template

Please provide a detailed budget of the evaluation (at VAT 0). Income tax will be be governed by and construed in accordance with the tax laws of all applicable federal, state, and local income taxes arising from its activities related to this contract.

|  | Unit cost (in USD) | Description/ Number of days | Total (in USD) |
| --- | --- | --- | --- |
| Consultancy fees | (per day) |  |  |
| Travel |  |  |  |
| Incidentals |  |  |  |
| Accommodation / DSA | (per day) |  |  |
| Materials/Interpreter |  |  |  |
| [Xx] (please fill in if needed) |  |  |  |

FCA = FCA