Terms of Reference for a Capacity assessment, Capacity development strategy and monitoring framework development for National Reconciliation Framework implementation

| Date of issue: | 8-Jan-24. |
| --- | --- |
| Project title: | 12207 - MIDEEYE Project: Support of the National Reconciliation and Local Governance in Somalia |
| Assessment target locations | The target institutions to be covered by the Capacity assessment are; The Ministry of Interior, Federal Affairs and Reconciliation (MoIFAR), Mogadishu, the ministry of the internal affairs (MoIs) of the Southwest State (SWS), Galmudug ministry of Interior, Federal Affairs and Reconciliation, and Hirshabelle State ministry of Reconciliation and Peacebuilding (MoRaP) |
| Deadline for submission of offers: | 29th of January 2024 at 5 p.m. (East Africa Time Zone) |
| Contracting authority: | FCA Somalia Country Office Contact: Procurement Committee E-mail: tenders.soco@kirkonulkomaanapu.fi |

# Introduction & Background

FCA Somalia Country Office is looking for qualified independent consultant(s) to undertake a Capacity assessment, develop subsequent capacity development strategy and monitoring tools for the implementation of the National Reconciliation Framework actions geared towards the National Reconciliation Process (NRP). This consultancy is carried to support delivery of the MIDEEYE Project: Support of the National Reconciliation and Local Governance in Somalia, between the 10th of January and the end of February 2024. Duration of the contract is 45 days.

FCA is the biggest development cooperation organization and second biggest humanitarian aid organization in Finland.  FCA is currently operating in 13 countries in Asia, Africa and the Middle East and is specialized in three thematic priority areas: Right to Peace (R2P), Right to Livelihood (R2L) and Right to Quality Education (R2QE). In Somalia, FCA began its operation in 2007 through support to peace building initiatives in Somaliland and Puntland. Following the success of the interventions, FCA Somalia expanded its operation to other parts of South Central of Somalia in 2013, evolving from community level peace building initiatives to state building and state formation interventions at FGS and FMS levels.

National Reconciliation Framework (NRF)

The NRF frames the reconciliatory process in terms of repair of social relationships and the rebuilding of trust between conflicting communities in Somalia. The National Reconciliation Process (NRP) has been adopted as implementation mechanisms of the NRF. It carries 14 milestones and 85 activities under its five pillars.

National Reconciliation Framework goal is to contribute to a sense of sustained peace and stability by laying the ground for genuine, comprehensive national reconciliation for the Somali people by restoring trust among themselves and increasing confidence in all levels of government institutions, resulting in peaceful coexistence, renewed relationships, and social and economic recovery.

Pillar I: Re-imagining a national heshiis bulsho (social contract) by developing a shared vision of an interdependent, fair, and secure society

Pillar II: Acknowledging and dealing with the past

Pillar III: Restoring and transforming community relationships

Pillar IV: Building trust in government institutions and structures

Pillar V: Supporting economic and social recovery activities

To realize key objectives outlined in the NRF and contribute to national peace and state-building, the FCA defined MIDEEYE goals as follows:

MIDEEYE project is a joint initiative of Finn Church Aid (FCA) and Network for Religious and Traditional Peacemakers (NRTP). The project is aiming to contribute to Somalia’s peacebuilding efforts by addressing grievances and strengthening inclusive governance. MIDEEYE, translates as “unifier” from Somali to illustrate its aim to create trust and social cohesion by strengthening efficiency and inclusivity of governance on several levels. The project’s approach to reconciliation is largely informed by the National Reconciliation Framework (NRF), a strategy document approved by the FGS and cabinet members in 2019 and reviewed during 2023, is expected that the NRF under review will be finalized and approved by the cabinet by commence of the consultancy. As a result, the Mideeye project has the following two main outcomes.

Outcome 1: Increasing the capacity of the Federal Government and selected FMS to implement the NRF and thereby strengthening the legitimacy and trust in government institutions, and

Outcome 2: Improving inclusive governance and administration in selected Federal Member States (FMS) to achieve more effective service delivery, in line with the NRF and Wadajir National Framework for local governance.

The four-year (2021 to 2024) MIDEEYE directly supports national reconciliation capacities of variety of government institutions, such as the line ministries, district councils, traditional and religious leaders, leaders of women’s groups, and youth representatives in selected FMS. 
MIDEEYE supports MoIFAR and relevant FMS line ministries to implement the NRF according to their respective mandates.

To this end project will carry out a capacity assessment to identify the level of current capacities of key staff and structures of the key ministries to implement the recommendations and actions outlined in the reviewed NRF geared towards implementation of the National Reconciliation Process, to develop a Capacity building strategy based on findings to strengthen the existing capacities for the same, finally to develop a monitoring framework to support the stakeholders to effectively monitor the implementation of NRF relevant to their mandate. The capacity assessment is carried out in close cooperation with MoIFAR, Ministries of the Interior of Southwest state, and Galmudug and the Ministry of the Reconciliation and peacebuilding in the state of Hirshabelle.

## Objectives of the Capacity assessment, Capacity Development strategy

Capacity assessment:

Identify, assess technical capacities, and develop recommendations;

Identify and asses available resources, and structures, and policies geared towards facilitating processes geared towards national reconciliation process in accordance with implementation of the National Reconciliation Framework and monitoring and evaluating for progress:

- Assesses the current level of staff capacities to effectively implement that NRF as per their role and the mandate in the selected ministries to effectively implement the desired actions regarding NRF; to identify any gaps particularly technical and thematic areas for peacebuilding, social healing, mediation, and related skills.

- This capacity assessment includes the review of existing resources and strategic plans, policies, and other relevant documents for implementing the Somalia National Reconciliation Framework, and reporting, monitoring and evaluation frameworks for tracking progress, by the target ministries.

- Assessment identifies capacities and enabling resources that can support ministries to support the NRF delivery in collaboration with other key stakeholders such as civil society actors.

- Assessment takes stock of best practices and formulates recommendations based on identified gaps and desirable level of capacity.

- Provides recommendations both how to enforce existing capacities, promote knowledge sharing and good practices AND how to bridge the gaps identified to efficient level of delivery.

Capacity Development strategy and monitoring and evaluation framework for its application

- The Consultant will detail in the strategy of how to implement the recommendations and bridge the identified gaps based on the findings and recommendations of the assessment, in the most cost-efficient way, outline potential trainings and other capacity building actions to be undertaken by the respective ministries.

- The Consultant will develop a monitoring and evaluation framework for the Capacity development strategy (CDS) with pre-defined performance indicators to bridge the gaps identified and to enable measurement of capacity improvement over time.  A monitoring framework tool will be developed together with a practical user’s guideline about its application, no more than 5 pages.

# Deliverables

The independent evaluator(s) will be expected to submit the following deliverables/ documents in time in compliance with standard requirements:

- Comprehensive Capacity Assessment report covering the target ministries providing relevant recommendations.

Detailed report provides an overview, followed by detailed assessment of the current capacities, resources, policies and structures, for facilitating processes geared towards national reconciliation under National Reconciliation Framework (reviewed version 2023) regarding the assessed target institutions. The assessment considers as well also the enabling environment and civil society actors, international partners in the overview of the available resources and capacities. Assessment takes stock of best practices and formulates recommendations based on identified gaps and desirable level of capacity to effectively implement actions geared towards the NRP. The report should be maximum 25 pages excluding annexes.

- Capacity development strategy (CDS) with pre-defined performance indicators to enable measurement of capacity improvement over time.

Capacity development strategy (CDS) will provide a detailed blueprint guiding the creation of approaches, guidelines, and tools to systematically build capacities to effectively implement the NRF and operationalize recommendations from the assessment. The CDS should outline prioritized capacity building actions for respective ministries with clearly defined objectives, activities, timelines, resources required based on gaps identified in the assessment findings. It will also include a results framework with indicators to monitor progress.

- Monitoring and evaluation framework toolkit and a practical guidance note

Develop a monitoring and evaluation framework toolkit for the target line ministries responsible for NRF implementation to allow them effectively to monitor and evaluate the implementation:

This monitoring framework formulates measurable performance indicators that allow periodic tracking of progress. The consultant develops a practical guidance note document to guide the users of the application of the monitoring and evaluation framework.

- Develop a Capacity assessment toolkit and a relevant guidance note

The consultant develops tool based on the assessment methodology for the ministries’ future application of assessing their staff capacities of to lead actions geared to operationalise the NRF/NRP. This resource will assist to assess and develop staff capacities in their respective institutions and among key stakeholder groups in future.

# Dissemination and reporting

Presentation (s) of the:

o	Draf Capacity Assessment Report

o	Draft Capacity Development Strategy

o	Draft Monitoring Framework Toolkit & Guidance

o	Draft Capacity Assessment Toolkit & Guidance

Consultant will deliver a one-day for approximately 20 key staff from MOIFAR, Interior Ministries of Southwest state and Hirshabelle, Ministry of Reconciliation and Peacebuilding in Hirshabelle and Galmudug. Training will cover the practical application of the tools developed, Monitoring Framework Toolkit & Guidance and Capacity Assessment Toolkit & Guidance note.

Learning outcome is that participants will be able to apply the tools for the benefit of developing the capacities of their respective institutions and monitoring of the progress of the capacities as well as of the implementation of the NRF/ NRP.

# Duration of contract

Duration of this contract is forty-five (45) days– starting 15th of January 2024.

# Service Terms

FCA Somalia country office intends to contract qualified consultant(s) forty-five days

# Duty Station

The independent consultant(s) will undertake in-country field work and reporting based on agreed work-plan and methodology. The assessment will cover MoIs in of Southwest state and Galmudug, and the MoRaP in Hirshabelle, and the MoIFAR, Mogadishu/ Benadir.

# Transport & Logistics

The consultant(s) will cover field transport and accommodation arrangements, translator and/or interpreter needs, focal points and other contact points on the field and other logistical arrangements concerning consultant’s visit(s) including data collection and

# Validity

Tenders/Offers shall remain valid and open for acceptance for a period of 30 days after the closing date for the submission.

# Tentative Timeline (dates subject to change) and expected deliverables

The project assessment and fieldwork are expected to tentatively start on the 15th of January 2024 and to conclude within 45 days.

| Tasks | Product/deliverables | Time frame |
| --- | --- | --- |
| Inception stage |  |  |
| i. Review relevant literature, previous survey reports, prepare an inception report ii. Prepare a detailed assessment plan including methodological approach (survey protocol, sampling approach/ framework and tools for assessing the project outcomes and outcome indicators as depicted in the project log-frame) iii. Prepare mapping and survey tools/guidelines for primary data collection iv. Guide/manage the baseline data collection exercise | i. Report on literature review/ brief situation analysis ii. Detailed assessment plan including methodology, sample size, research sites, and data analysis plan. iii. Survey tools and guidelines iv. Guide/ work plan to manage the baseline data collection exercise v. Presentation of the field work plan | 5 days |
| Assessment stage; data collection, analysis, formulation of recommendations and drafting the tools |  |  |
| v. Administer field visits, FGDs and interviews/ meetings to collect information on the assessment and analyse information and draft recommendations for bridging the gaps identified to an effective operational capacity level that with means of cost efficiency vi) Formulate capacity development strategy, tools for monitoring& performance-based indicators, practical user guidance note about the same | iv. Information collected and analysed, recommendations and suggestions + raw survey data | 30 days |
| Reporting and dissemination activities |  |  |
| Prepare following presentation(s) and present the findings to finalize these with FCA and relevant staff of the target the MoIs/ MoiFAR - Presentation (s) of the: Draf Capacity Assessment Report Draft Capacity Development Strategy Draft Monitoring Framework Toolkit & Guidance Draft Capacity Assessment Toolkit & Guidance Prepare draft reports and documents/ and finalize these with FCA and relevant staff of the target the MoIs/ MoiFAR: - Comprehensive Capacity Assessment report covering the target ministries providing relevant recommendations. - Monitoring and evaluation framework toolkit and a practical guidance note - Develop a Capacity assessment toolkit and a relevant guidance note - Prepare a Training to relevant stakeholders about the monitoring framework tool developed/ dissemination of the practical guidance note for the tool | Power point presentations/ word documents outlining. Draf Capacity Assessment Report Draft Capacity Development Strategy Draft Monitoring Framework Toolkit & Guidance Draft Capacity Assessment Toolkit & Guidance Final Comprehensive Capacity Assessment report covering the target ministries providing relevant recommendations Final Monitoring and evaluation framework toolkit and a practical guidance note documents. Final Capacity assessment toolkit and a relevant guidance note documents. One-day training delivered to for approximately 20 key staff from MOIFAR, Interior Ministries of Southwest state and Hirshabelle, Ministry of Reconciliation and Peacebuilding in Hirshabelle and Galmudug. Training will cover the practical application of the tools developed; Monitoring Framework Toolkit & Guidance and Capacity Assessment Toolkit & Guidance note. | 10 days |

# Payment Modalities

The purpose of this section is to provide a detailed payment schedule and modalities against the deliverables. The payments will be processed upon completion of the following milestones.

- 20% payment release after completion, submission, and acceptance of the inception assessment report

- 30% payment release after completion, submission, and acceptance of detailed draft documents of all the deliverables, including a draft training plan for dissemination activity.

- 50% payment release after submission of the final deliverables, delivery of the training acceptance of the deliverables.

# Required Expertise and Qualification

- Experience: Conducting institutional capacity assessments, research, and policy-analysis, monitoring and evaluation processes, capacity development strategies and M&E frameworks, and activities in Somalia specifically shows experience in the relevant context and subject matter.

- Knowledge: In-depth knowledge of the Somalia context, including NRF/P related previous expertise and expertise on fields relevant to its operationalisation for example peace and conflict, political economy, and security studies, are crucial for understanding the challenges and opportunities for reconciliation efforts.

- Monitoring and Evaluation: Minimum 10 years of experience in monitoring and evaluation, with a focus on developing quality tools, analysing qualitative and quantitative data, and writing exceptional reports, are essential for accurately assessing capacity gaps, developing effective strategies, and monitoring and evaluation tools to track progress.

- Education:  Master's degree in relevant fields like economics, statistic, public administration, M&E, developmental studies, peace and conflict management, or other relevant field demonstrate strong academic grounding in the subject matter.

- Experience in designing and implementing capacity development programs.

- Proven track record of success in similar projects.

- Fluency in Somali and English languages would be a significant advantage.

# Contract Award Criteria

The purpose of this section is to provide a criteria, weight and scoring information for the final evaluation phase. The offers will be evaluated according to the contract award criteria below:

| # | Description | Weight (%) | Scoring methodology | Score (%) |
| --- | --- | --- | --- | --- |
| 1 | Skills/expertise | 20 | 10 years’ experience in M&E; master’s degree in M& E studies, public administration, peace and conflict and related studies. Experience in Somalia context. 10 Years M & E experience particular skills in monitoring and evaluation frameworks and systems, capacity assessment development | 5 |
|  |  |  | Between 5- and 9-Year M & E experience; 10 Years M & E experience particular skills in monitoring and evaluation frameworks and systems, capacity assessment development | 2 |
|  |  |  | Less than 5 Years M & E experience: 10 Years M & E experience particular skills in monitoring and evaluation frameworks and systems, capacity assessment development | 1 |
|  |  |  | Bachelor degree as stated in the TOR | 2 |
|  |  |  | Master’s degree as stated in the TOR | 5 |
|  |  |  | In-depth knowledge and experience in Somalia context as stated in the TOR | 5 |
| 2 | Methodology/ rational/ sampling strategy/ research questions | 35 | Based on the technical proposal submitted by the candidate |  |
|  |  |  | Methodology | 12 |
|  |  |  | Rationale | 3 |
|  |  |  | Workplan | 10 |
|  |  |  | Research questions & assessment tools / data collection tools | 10 |
| 3 | Experience/sample reports | 25 | Similar sample reports by the candidate |  |
|  |  |  | Up to 3 Similar reports as stated in the TOR | 13 |
|  |  |  | 2 Similar reports as stated in the TOR | 8 |
|  |  |  | 1 Similar report as stated in the TOR | 4 |
| 4 | Availability/timeliness | N/A | Consistency with the project deliverables and timeframe as indicated in the TOR | Unavailability leads to disqualification |
|  |  |  | Within or Lesser than proposed Timeframe | 5 |
|  |  |  | Beyond than proposed timeframe | 0 |
| 5 | Budget | 20 | Lowest bid receives highest score. Other candidates’ scores are calculated proportionally based on the lowest bid. | 20 |
| Overall Total |  | 100 |  |  |

# Evaluation Process

The evaluation process is managed by FCA’s Procurement Committee. Candidates will be first evaluated according to the requirements in section 13 - Required Expertise and Qualifications. Candidates who are eligible will be allowed to proceed to the evaluation phase and their offers will be evaluated according to the contract award criteria in section 14.

# Application procedure

Deadline for submission of offers is 29th of January 2024 at 5 p.m. (East Africa Time Zone). Candidates must send their offers via email to tenders.soco@kirkonulkomaanapu.fi and cc: info@moifar.gov.so  no later than the deadline as aforementioned.

Any tenders received after the deadline will not be considered. Candidates must put “Consultancy to Conduct 12207 – MIDEEYE Capacity assessment, Capacity development strategy and monitoring framework development for National Reconciliation Framework implementation” in the subject line of their emails. No tender may be changed or withdrawn after the deadline has passed. The candidate shall bear all costs associated with the preparation and submission of the offer and the Contracting Authority will in no case be responsible or liable for these costs, regardless of the conduct or outcome of the procurement process. Canvassing will lead to automatic disqualification. Please note, only short-listed candidates will be notified for interview. Thank you!

# Questions

Candidates are not allowed to approach the Contracting Authority for verbal clarification. Any prospective candidate seeking to arrange individual meetings with either the Contracting Authority and/or any other organisation with which the Contracting Authority is associated or linked may be excluded from the tender procedure. Candidates may submit questions in writing via email to the address above latest three days before the deadline.

# Terms of contract

- Confidentiality – Highlight any confidentiality concern

- (Optional) The Consultant is responsible for payment of all social costs, other employment related costs and insurance contributions and for all other liabilities of a statutory nature.

- During the assignment, the consultant does not represent FCA Somalia Country Office and has no mandate to negotiate, make commitments or agree on behalf of FCA Somalia Country Office.

- The consultant is expected to use own computer and other equipment required for works.

- By submitting an offer, the candidate/consultant/service provider confirms to abide by FCA Somalia Country Office Code of Conduct, Child Safeguarding policy and any other relevant FCA Somalia Country Office policies.

- The ownership and copyright(s) of the report(s) and any other produced material will remain with FCA Somalia Country Office.

- The Contracting authority may for its own convenience and without charge or liability cancel the tender process at any stage.

# Documents comprising this procurement

Purpose of this section is to provide a list of the documents used in the procurement process. The candidate(s) shall complete and submit the following documents with the tender:

- Technical Proposal including an outline of the proposed methodology, data gathering, etc. (maximum 3 pages)

- Financial Proposal including Indicative budget (maximum 1 page) inclusive of the consultant’s daily rate(s) and other related expenses. Rates should be in US Dollars and inclusive of VAT.

- Candidate CV, Certifications, Reference Letters

- Samples of previous work relevant to the assignment (in English)

- Cover letter including a description of suitability of the consultant(s) (maximum 1 page)

# Annex I – Technical Proposal Template

To be filled-in by the candidates, in compliance with the following instructions

- Rationale (max. 1 page)

Any comments on the Terms of Reference of importance for the successful execution of activities, in particular its objectives and expected results, thus demonstrating the degree of understanding of the contract. Any comments contradicting the Terms of Reference or falling outside their scope will not form part of the final contract.

An opinion on the key issues related to the achievement of the contract objectives and expected results (Optional: An explanation of the risks and assumptions affecting the execution of the contract)

- Proposed Methodology (max. 3 pages)

An outline of the approach proposed for contract implementation;

A list of the proposed activities considered to be necessary to achieve the contract objectives;

The related inputs and outputs. Please pay attention to explicitly detail the assessment methodology and data collection plan and tools to be utilized for delivery of the objectives.

- Timetable of activities (max 1 page)

The timing, sequence, and duration of the proposed activities, taking into account mobilization time.

# Annex II – Financial Proposal Template

Please provide a detailed budget of the evaluation (at VAT 0). FCA will then add the VAT according to the Finnish/local legislation. FCA will not cover additional costs relating to the execution of the workplan other than detailed in the submitted financial proposal template, please include all costs to be covered in the financial proposal including the dissemination activities.

|  | Unit cost (in EUR) | Description/ Number of days | Total (in EUR) |
| --- | --- | --- | --- |
| Consultancy fees | (per day) |  |  |
| Travel |  |  |  |
| Incidentals |  |  |  |
| Accommodation / DSA | (per day) |  |  |
| Materials/Interpreter |  |  |  |
| [Xx] (please fill in if needed) |  |  |  |