TERMS OF REFERENCE

Procurement and Distribution of Menstrual Hygiene Management (MHM) Kits for Adolescent Vulnerable Girls in GPE Grant Supported Schools

| Assignment | Procurement and distribution of MHM Kits for 20,000 Vulnerable Girls in Schools |
| --- | --- |
| Location | All Federal States and Banaadir Region |
| Target beneficiaries | 20,000 Vulnerable Girls |
| Delivery period | September 2026 |
| Project | Girls Education Accelerator Program (GEA) |

- BACKGROUND INFORMATION

Menstrual hygiene management (MHM) remains a significant barrier to girls' education in Somalia, contributing to absenteeism, reduced participation, and increased risk of school dropout, particularly among adolescent girls who have experienced their first menstrual cycle. Many schools lack adequate support systems, while girls often face limited access to affordable menstrual hygiene products, inadequate sanitation facilities, and stigma surrounding menstruation. These challenges are further compounded for girls who have undergone Female Genital Mutilation (FGM), who may experience additional physical and psychosocial difficulties in managing menstruation at school.

To address these barriers, the Ministry of Education, Culture and Higher Education (MOECHE), through the Girls' Education Accelerator (GEA), will procure and distribute Menstrual Hygiene Management (MHM) Kits (Dignity Kits) to eligible female students, prioritizing areas with the largest gender disparities in access to education. Each kit will include reusable menstrual pads suitable for the local context, soap, and underwear. The intervention will also strengthen the capacity of head teachers and teachers to provide appropriate guidance and support for menstrual hygiene management in schools.

To maximize impact and ensure efficient use of resources, Federal Member State Ministries of Education (FMS MOEs) will verify that beneficiaries are not receiving similar support from other partners before distribution, thereby avoiding duplication. The intervention will be implemented by the Gender and Inclusion Focal Points to harmonize menstrual hygiene management guidelines and support the dissemination of these guidelines through health and hygiene support in schools, focusing on girls' needs. This integrated approach will contribute to improving girls' school attendance, retention, participation, and overall well-being while promoting a safe, inclusive, and gender-responsive learning environment.

- Rationale

The procurement and distribution of Menstrual Hygiene Management (MHM) Kits is intended to eliminate one of the key barriers preventing adolescent girls from accessing and fully participating in education. Lack of menstrual hygiene products and limited knowledge of menstrual health often result in frequent absenteeism, reduced classroom engagement, diminished self-confidence, and increased risk of dropping out of school. By providing essential dignity kits alongside guidance and capacity building for head teachers and teachers, the intervention will enable schools to offer a more supportive and responsive environment for girls, including those facing additional challenges associated with Female Genital Mutilation (FGM). The activity is also expected to promote equitable access to education by prioritizing underserved areas with the greatest gender disparities.

- Target Beneficiaries

The intervention targets 20,000 vulnerable adolescent girls from across GPE supported schools, including:

- Internally displaced girls.

- Girls affected by conflict and natural disasters.

- Orphans and vulnerable girls.

- Girls from extremely poor households.

- Girls with disabilities.

- Girls at risk of dropping out of school.

- Objectives

The primary objective of this assignment is to procure, package, transport, and distribute high-quality Menstrual Hygiene Management (MHM) Kits (Dignity Kits) to 20,000 vulnerable adolescent girls enrolled in GPE-supported schools across the target Federal Member States of Galmudug, Hirshabelle, Jubaland, Southwest, North East, and the Banadir Regional Administration (BRA). The assignment also seeks to support the effective implementation of school-based menstrual hygiene management interventions by ensuring that the kits are contextually appropriate, delivered in a timely and equitable manner, and accompanied by guidance and capacity strengthening for head teachers and teachers to better support girls' menstrual hygiene management needs. The intervention aims to improve girls' attendance, retention, participation, and overall well-being in school while contributing to a safe, inclusive, and gender-responsive learning environment.

- Scope of Work

The selected supplier/service provider shall be responsible for the procurement, packaging, delivery, and distribution of 20,000 Menstrual Hygiene Management (MHM) Kits (Dignity Kits). The scope of work shall include, but not be limited to the following

- Procure all approved Menstrual Hygiene Management (MHM) kit components in accordance with the technical specifications and quality standards approved by MOECHE and CARE.

- Supply reusable menstrual pads suitable for the local context, underwear, soap, and any other approved items as specified in the procurement requirements.

- Submit samples of all kit components and the packaged MHM kit for review, quality verification, and written approval by MOECHE and CARE prior to bulk procurement.

- Assemble and package 20,000 individual MHM kits in durable, discreet, and appropriate packaging suitable for safe transportation, storage, and distribution.

- Ensure all procured items are new, hygienic, safe, durable, and compliant with the agreed quality standards and specifications.

- Manage all transportation, warehousing, inventory management, and logistics required for the delivery of MHM kits to designated distribution points/schools.

- Develop and submit a detailed distribution plan including delivery timelines, distribution locations, and logistical arrangements.

- Coordinate closely with MOECHE, Federal Member State Ministries of Education (FMS MOEs), Gender and Inclusion Units, school headteachers throughout the distribution process.

- Conduct the distribution of MHM kits in a safe, confidential, culturally appropriate, and gender-sensitive manner that protects the dignity and privacy of beneficiaries.

- Maintain accurate records and complete documentation throughout the distribution processes.

- Collect signed distribution lists, delivery notes, and all other required supporting documentation as evidence of successful distribution.

- Provide regular progress updates to MOECHE and CARE on procurement, logistics, distribution status, challenges encountered, and mitigation measures undertaken.

- Submit a comprehensive final completion report detailing procurement distribution outcomes, beneficiary coverage, lessons learned, and all supporting documentation required for payment process purposes.

- Hygiene Kit Contents (Minimum Requirements)

Each Menstrual Hygiene Management Kit shall contain:

| # | Description of items | Unit of measurements | Quantity |
| --- | --- | --- | --- |
| 1 | Sanitary pads | Packet (One packet contains 12 reusable pad) | 20,000 Packets |
| 2 | Underwear | Pairs (Pairs each containing six pairs of underwear, appropriate sizes (16,000 set medium size and 4,000 set large size) | 20,000 Pairs |
| 3 | Dettol Soap | Pair (One pair containing 6 pieces bath soap, Dettol 70g) | 20,000 Pairs |
| 3 | Bar Soap | Pair (One pair containing 3 pieces of laundry soap 200g) | 20,000 Pairs |
| 4 | Pouch/handbag | Discreet, durable, waterproof pouch/bag with at least two compartments (for clean and used pads) or 2 separate bags. | 20,000 Pcs |
| 5 | Print MHM guideline leaflet (contents will be provided) | Print 10,000 leaflets (MHM guideline). Information will be shared later | 20,000 pcs |
| 6 | Transportation/packaging/distribution cost | Items will be delivered to selected schools. See attached annex. | Transportation cost |

Selection criteria – Pass/Fail

| # | Preliminary selection criteria | Category |
| --- | --- | --- |
| 1 | Valid certificate of registration from Ministry of Commerce | Federal level |
| 2 | Valid Tax Compliance Certificate, (Quarter 3 of 2026) | Federal level |

- Selection criteria

|  | Technical evaluation criteria |  | Scoring Marks |  |
| --- | --- | --- | --- | --- |
| 1 | Delivery duration/Workplan/ distribution workplan to all the state locations (Ability to Manage all transportation, warehousing, inventory management, and logistics required for the delivery of MHM kits to designated distribution points/schools and previous experience of similar assignment in the past) see the list of schools the attached excel sheet below. |  | 20 marks |  |
|  | Sufficient experience and references from similar projects in the field of assignment (Proof of two similar contracts undertaken by the supplier in the last five years) |  | 20 Marks |  |
| 4 | Two client references with complete contact information. The reference should be updated and linked to the POs/Contracts provided to contracting authority (care international) |  | 10 Marks |  |
| 5 | Updated company profile, with contact details and physical address. |  | 10 marks |  |
| 6 | Bank/Financial statement (for the last six months with a minimum balance of $300,000) sign and stamp by the bank. Crae might verify to confirm the supplier capacity. |  | 20 Marks |  |
|  |  |  | 80 Marks |  |
|  |  | Financial Evaluation criteria |  | Scoring Marcks |
| 1 |  |  |  | 20 |

NOTE: All items must be new, safe, culturally appropriate, and of good quality.

Note: The suppliers with a score of at least 50 marks and above will be considered for financial evaluation. The financial evaluation carries a score of 20 marks.

Refer to Annex 1: List of 526 schools.