INVITATION TO BID FOR CONSULTANCY

| 1 | Title of Consultancy |  | TERMS OF REFERENCE FOR RESEARCH ON SUSTAINABLE FINANCING FOR ANTICIPATORY ACTION AND ENHANCING THE VALUE OF EARLY WARNING INFORMATION SERVICES. |  |
| --- | --- | --- | --- | --- |
| 2 | SCI Contracting Office |  | Save the Children Somalia/land Country Office |  |
| 3 | Period of Consultancy |  | The duration of the assignment will be from November 2025 to April 2026 including travel days. This is also inclusive of weekends. |  |
| 4 | Consultant type required |  | Consultancy Firm/ Individual. |  |
| 5 | Responsibility for Logistics arrangements and Costs |  | Save the children will pay the consultant fee in a lump sum and will not reimburse any incurred costs during the assignment. The consultant will cover their own Logistical arrangements, costs; including food, accommodation, local transport and all cost associated with data collection work and whole activities. |  |
| 6 | Taxation Provisions |  | The applicant shall be responsible for all taxes arising from the consultancy in line with the local Tax regulations applicable at the SCI contracting office, Hargeisa. |  |
| 7 | Travel requirements |  | The applicant will cover all travel costs (tickets) and arrange local travel to field sites. |  |
| 8 | Security requirements |  | The consultancy firm/individual will comply with standard of Save the Children Security procedures, including the completion of SCI online security training (applicable to international consultants) prior to travel to Somalia. |  |
| 9 | Professional quality and Expertise |  | The following are the minimum requirements for the Consultant Firm/individual to be considered for carrying out the assignment: - Advanced degree (master’s or PhD preferred) in Economics, Development Finance, Public Policy, Business Administration, climate change, anticipatory action, Disaster Risk Reduction, Climate Science, Environmental Studies, Development Studies, Social Sciences, or related disciplines. - Training in innovative financing mechanisms, Islamic finance, or private sector engagement is an asset. - Strong expertise in financing models for humanitarian and development initiatives, including private sector contributions, zakat, remittances, and philanthropy. - Knowledge of corporate social responsibility (CSR), impact investing, and blended financing approaches. - Proven ability to analyze market trends, regulatory environments, and opportunities for private sector engagement in AA. - Understanding of Islamic finance principles and their potential application in humanitarian financing. - Minimum of 7–10 years of experience in research or practice related to development financing, humanitarian funding, or private sector engagement. - Experience engaging with banks, private firms, diaspora organizations, and philanthropic foundations. - Demonstrated ability to produce high-quality research outputs, including policy papers and donor briefs. - Previous work in Somalia, or similar fragile and conflict-affected contexts, is a strong asset. - Excellent quantitative and qualitative research skills, including stakeholder mapping, inclusive collection and analysis of data through KII and FGD and financial analysis. - Strong networking and stakeholder engagement skills with private sector and civil society actors. - Ability to identify innovative financing opportunities and recommend practical models for scaling. - Excellent communication and presentation skills for diverse audiences, including donors and policymakers. - Specialized training in risk communication, community-based early warning systems, or disaster risk management is an advantage. - Strong expertise in design, implementation, and evaluation of Early Warning Systems (EWS) and anticipatory action frameworks. - Knowledge of climate and hazard modeling, information dissemination systems, and community-level risk communication. - Proven ability to conduct participatory research with communities to assess information needs and accessibility barriers. - Experience integrating gender, age, disability, and socio-economic perspectives into risk communication and early warning design. - experience in early warning systems, disaster preparedness, or humanitarian programming. - Demonstrated experience working with governments, humanitarian agencies, and local communities on risk-informed programming. - Track record of conducting applied research and producing high-quality, peer-reviewed publications or policy briefs on early warning and anticipatory action - Strong participatory research and facilitation skills for engaging diverse communities. - Excellent analytical and writing abilities to translate findings into actionable recommendations. - Competence in GIS, climate data analysis, or digital platforms for early warning dissemination is desirable. - Ability to work collaboratively with multidisciplinary teams and stakeholders |  |
|  | KEY PROFESSIONAL STAFF REQUIREMENT |  |  |  |
|  | Description |  | Minimum Qualification and professional experience |  |
|  |  | - Advanced degree (Master’s or PhD preferred) in Economics, Development Finance, Public Policy, Business Administration, or related disciplines. - Training in innovative financing mechanisms, Islamic finance, or private sector engagement is an asset. |  |  |
|  | 11 EVALUATION CRITERIA The proposals submitted by consulting companies will be evaluated based on the following criteria: |  |  |  |
|  | Essential Criteria |  |  | Pass/Fail |
| 1 | The Bidder and its staff agree and Sign to comply with SCI policies embedded below at this ITB. The Bidder is to download below listed items, read, understand and sign off appropriate section in below. a) Terms & Conditions of Bidding b) Supplier Sustainability Policy and the included mandatory policies |  |  | Pass/Fail |
| 2 | The bidder must provide official documentation that demonstrates their legal status and professional registration, including but not limited to: - Valid certifications related to the field of expertise - Registration certificates issued by relevant authorities Any other legal documents verifying the entity's authorization to operate, such as business licenses or accreditation from recognized regulatory bodies. NB: This is only applicable to firms and not individual consultants. A valid Tax Compliance Certificate the relevant ministry of Finance/Revenue Authority in Somalia/land. NB: This is only applicable to firms and not individual consultants. |  |  | Pass/Fail |
|  | Capability Criteria (Technical Evaluation): |  |  |  |
| 1 | Detailed technical proposal with clear understanding of the TOR and Methodology of how the consultant intends to conduct assignment with detailed work plan, clear milestones, methodologies, data analyses plan including any software to be used for analysis. This to be evaluated based on: - Understanding of the problem and context (Somalia, Anticipatory Action, Financing and early warning information services): 10 marks - Robustness and feasibility of proposed methodology that have: 15 marks • Clear justification of methods (qualitative, quantitative, mixed). - Presents a clear theory of change or analytical framework linking anticipatory action triggers, financing mechanisms, early warning information services and outcomes. • Demonstrates understanding of anticipatory action concepts (risk analysis, trigger thresholds, financing flow, early warning information services pre-agreed action protocols). - Integrates resilience, early warning, and humanitarian-development nexus perspectives - Clarity and realism of work plan: 10 marks |  |  | 35 marks |
| 2 | Experience in conducting similar activity on research developing a new form of sustainable financing for AA activities through the private sector and value for early warning information services: - Submission of at least two (2) contracts or LPOs demonstrating prior experience in conducting financial flow mapping or private sector engagement research and value for early warning information services in fragile states (10 marks). Provide two contract examples. - CVs of proposed team, with clear demonstration of expertise in Islamic Finance/Zakat and Diaspora Finance/Remittances and early warning information services (10 marks) - Cover letter and company profile demonstrating specific knowledge of the Somali private and diaspora landscape (5 marks). |  |  | 25 Marks |
| 3 | Submit official and genuine official bank statement from 1st August 2024 to 30th September 2025. (10 marks). |  |  | 10 Marks |
| 4 | Two Copies of the previous similar reports relevant with the subject matter with presentation of their findings. (10 marks –with each similar report being awarded 5 marks). |  |  | 10 Marks |
|  | Commercial Criteria (Financial Evaluation): |  |  |  |
| 1 | Detailed financial proposal with budget breakdown including all expenses, fees, and taxes. 100% x Lowest bid valueCurrent value bid x 0.20 |  |  | 20 marks |
|  | Total |  |  | 100 marks |
| Note: For the technical analysis, a company must pass the essential criteria and score 60% and above on the capability to be considered in the next evaluation process and the ultimate decision will be based on interview performance. |  |  |  |  |
| 1 | Application Procedure |  | - Interested consultant (s) who meet the consultancy requirements are requested to submit their bid and each application package should include the above required minimum requirements. Applications can be submitted by: Protected Email box below - Email should be addressed to Somalia.Tenders@savethechildren.org - Should you need any clarifications please direct your queries to Somalia.procurement@savethechildren.org and expect responses within maximum of two working days. - Note – this is a sealed tender box which will not be opened until the tender has closed. Therefore, do not send tender related questions to this email address as they will not be answered. - The subject of the email should be TERMS OF REFERENCE (TORs) FOR RESEARCH ON SUSTAINABLE FINANCING FOR ANTICIPATORY ACTION AND ENHANCING THE VALUE OF EARLY WARNING INFORMATION SERVICES. - All attached documents should be clearly labelled so it is clear to understand what each file relates to. - Emails should not exceed 15mb – if the file sizes are large, please split the submission into two emails. - Do not copy other SCI email addresses into the email when you submit it as this will invalidate your bid. All applications MUST be submitted on or before the closing date below to be considered for the assignment. Only shortlisted Candidates will be contacted for Interview. |  |
| 1 | Closing date for Applications |  | Interested consultants shall submit their applications through the above procedures on or before 18th November 2025. |  |

| We, the Bidder, hereby confirm we compliance with the following policies and requirements: |  |  |
| --- | --- | --- |
| Policy | Policy / Document | Signature |
| Terms & Conditions of Bidding |  |  |
| Supplier Sustainability Policy and the included mandatory policies | Click Here to Access |  |

| We confirm that Save the Children may in its consideration of our offer, and subsequently, rely on the statements made herein. |  |
| --- | --- |
| Signature: | ………………………………………………….. |
| Name: | ………………………………………………….. |
| Title: | ………………………………………………….. |
| Company: | ………………………………………………….. |
| Date: | ………………………………………………….. |

# TERMS OF REFERENCE (TORS) FOR PRODUCTION AND DISSEMINATION OF RESEARCH PAPERS.

# PROJECT BACKGROUND.

Natural disasters pose a significant threat to the populations in our target locations and can have devastating humanitarian consequences. The increase in extreme weather events, caused by climate change, exacerbates existing vulnerabilities, and negatively impacts the livelihoods of poor communities, leading to loss of life, livelihoods, and displacement.

To address these challenges, Save the Children is currently implementing a project in Somaliland (Burao district - Togdheer) and Somalia (Beletwyene and Banderbeyle districts), in collaboration with relevant agencies in line with national plans and priorities. This project is funded by Germany and focuses on strengthening local and national systems and capacities in early warning and anticipatory action programming. It provides valuable learning opportunities for disaster preparedness, early warning systems, data collection, and trigger development for anticipatory action. The regions of Somaliland and Somalia (Togdheer, Bari, and Hiran) serve as a suitable case study to understand how anticipatory action can shift the focus from reacting to hazards to actively anticipating them in the context of a protracted crisis.

- Research Areas.

The consultant is expected to conduct two research activities:

## Research Agenda One: To develop a new form of sustainable financing for AA activities through the private sector.

Research Question One: To what extent do private donations from firms, from zakat and through remittances currently engage with the AA agenda and what opportunities exist to increase that engagement when appropriate?

## Research Agenda Two: To improve the value of Early Warning Information services.

Research Question Two: How can early warning information (EWI) be tailored to best meet the needs of various types of individuals?

Methods summary for both researches: This research will employ a sequential mixed-methods approach, beginning with recipient-level data collection and proceeding to upstream provider engagement.

- Phase 1: Recipient-level mapping: Through FGDs and KIIs with community members (aligned with RA1), we will map the types, sources, and timing of financial and in-kind support they receive.

- Phase 2: Upstream provider engagement: From this mapping, we will identify and, with informed consent, contact the providers of support (e.g., diaspora members, private firms, Zakat committees). We will then conduct in-depth interviews with these providers to understand their decision-making processes and explore the potential for AA.

Steps:

- Stakeholder mapping and workshops: Conduct 1-2 high-level stakeholder workshops/roundtable discussions across the three project sites to map the ecosystem of private sector and diaspora actors involved in humanitarian assistance.

- Recipient-level data collection (Integrated with RA1):

  - Conduct approx. 12-15 Focus Group Discussions (FGDs) (4-5 per district) with diverse community members to understand the flow of private support.

  - Conduct approx. 15-20 Key Informant Interviews (KIIs) with local leaders, money transfer agents, and Zakat committee members to triangulate findings.

- Upstream provider interviews:

  - Diaspora: Conduct approx. 15-20 in-depth interviews with diaspora remittance senders in key locations (e.g., UK, Scandinavia), identified and consented via recipient tracing.

  - Private Sector: Conduct approx. 10-15 KIIs with identified private firms (e.g., Hormuud Telecom, other major businesses).

  - Religious Institutions: Conduct approx. 5-10 KIIs with leaders of Zakat collection committees.

- Data analysis and validation: Employ thematic analysis for qualitative data. Present preliminary findings in a validation workshop with key stakeholders.

- ACTIVITIES OF THE STUDY.

Deliverable 1: Inception report and ethical protocols

- Submit a detailed Inception Report within the first 3 weeks, including a refined methodology, detailed work plan, data collection tools (FGD/KII guides), and a comprehensive risk mitigation plan.

- Secure ethical approval from a recognized Ethical Review Board for all human subject research, with protocols specifically addressing the informed consent process for the sensitive "upstream tracing" component.

Deliverable 2: Five draft research manuscripts

- Produce five high-quality, publishable draft research papers. The drafts must include a full analysis, discussion, and conclusion, formatted for submission to a peer-reviewed journal.

Deliverable 3: Dissemination and submission

- Present findings in at least one national-level dissemination workshop.

- Submit the finalized manuscripts to two reputable, peer-reviewed journals relevant to humanitarian finance, disaster risk reduction, or development studies.

Deliverable 4: Draft advocacy and communication strategy

- In coordination with the SCI ACCM team, produce a draft evidence-based advocacy and communication strategy. This document will outline key messages, target audiences, and actionable recommendations for engaging the private sector and diaspora in AA financing.

Consultancy Profile – Research Agenda One.

The lead consultant for the research agenda One should possess the following qualifications:

  - Education

- Advanced degree (master’s or PhD preferred) in Economics, Development Finance, Public Policy, Business Administration, or related disciplines.

- Training in innovative financing mechanisms, Islamic finance, or private sector engagement is an asset.

  - Technical Expertise

- Strong expertise in financing models for humanitarian and development initiatives, including private sector contributions, zakat, remittances, and philanthropy.

- Knowledge of corporate social responsibility (CSR), impact investing, and blended financing approaches.

- Proven ability to analyze market trends, regulatory environments, and opportunities for private sector engagement in AA.

- Understanding of Islamic finance principles and their potential application in humanitarian financing.

  - Professional Experience

- Minimum of 7–10 years of experience in research or practice related to development financing, humanitarian funding, or private sector engagement.

- Experience engaging with banks, private firms, diaspora organizations, and philanthropic foundations.

- Demonstrated ability to produce high-quality research outputs, including policy papers and donor briefs.

- Previous work in Somalia, or similar fragile and conflict-affected contexts, is a strong asset.

  - Skills and Competencies

- Excellent quantitative and qualitative research skills, including stakeholder mapping, inclusive collection and analysis of data through KII and FGD and financial analysis.

- Strong networking and stakeholder engagement skills with private sector and civil society actors.

- Ability to identify innovative financing opportunities and recommend practical models for scaling.

- Excellent communication and presentation skills for diverse audiences, including donors and policymakers.

Consultancy Profile – Research Agenda Two.

The lead consultant for the research agenda Two should possess the following qualifications:

- Education

- Advanced degree (Master’s or PhD preferred) in Disaster Risk Reduction, Climate Science, Environmental Studies, Development Studies, Social Sciences, or related fields.

- Specialized training in risk communication, community-based early warning systems, or disaster risk management is an advantage.

- Technical Expertise

- Strong expertise in design, implementation, and evaluation of Early Warning Systems (EWS) and anticipatory action frameworks.

- Knowledge of climate and hazard modeling, information dissemination systems, and community-level risk communication.

- Proven ability to conduct participatory research with communities to assess information needs and accessibility barriers.

- Experience integrating gender, age, disability, and socio-economic perspectives into risk communication and early warning design.

- Professional Experience

- Minimum of 7 years of experience in early warning systems, disaster preparedness, or humanitarian programming.

- Demonstrated experience working with governments, humanitarian agencies, and local communities on risk-informed programming.

- Track record of conducting applied research and producing high-quality, peer-reviewed publications or policy briefs on early warning and anticipatory action.

- Skills and Competencies

- Strong participatory research and facilitation skills for engaging diverse communities.

- Excellent analytical and writing abilities to translate findings into actionable recommendations.

- Competence in GIS, climate data analysis, or digital platforms for early warning dissemination is desirable.

- Ability to work collaboratively with multidisciplinary teams and stakeholders

# Timeline:

|  | 2025 |  |  |  |  |  | 2026 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activities | Oct | Nov | Dec | Jan | Feb | Mar |  | Apr | May | Jun | Jul | Aug | Sep | Oct |
| Contracting and Consultant on boarding. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Study design. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ethical Approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data collection RA1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data collection RA2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Manuscript 1 drafted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Manuscript 2 drafted |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Research Dissemination and Publication. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Advocacy and communication on AA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |