INVITATION TO BID FOR CONSULTANCY

| 1 | Title of Consultancy | TERMS OF REFERENCE FOR UNDERTAKING A HUMAN CAPITAL AASSESSMENT FOR MCRO, SMALL AND MEDIUM ENTERPRISES IN SOMALIA AND SOMALILAND |  |
| --- | --- | --- | --- |
| 2 | SCI Contracting Office | Save the Children Somalia/land Country Office |  |
| 3 | Period of Consultancy | The duration of the assignment will be 30 calendar days, inclusive of travel days and weekends |  |
| 4 | Consultant type required | Consultancy Firm/Individual consultant |  |
| 5 | Responsibility for Logistics arrangements and Costs | Save the children will pay the consultant fee in a lump sum and will not reimburse any incurred costs during the assignment. The consultant will cover their own Logistical arrangements, costs; including food, accommodation, local transport and all cost associated with data collection work and whole activities. |  |
| 6 | Taxation Provisions | The consultancy firm/Consultant shall be responsible for all taxes arising from the consultancy in line with the local Tax regulations applicable at the SCI contracting office, Hargeisa. |  |
| 7 | Travel requirements | The consultancy firm/Individual will cover all travel costs (tickets) and arrange local travel to field sites. |  |
| 8 | Security requirements | The consultancy firm/individual will comply with standard of Save the Children Security procedures, including the completion of SCI online security training (applicable to international consultants) prior to travel to Somalia. |  |
| 9 | Professional quality and Expertise | The following are the minimum requirements for the Consultant Firm/individual to be considered for carrying out the assignment. - Post-graduate degree in economics, Statistics, development studies, Social Sciences or other related qualifications. - Minimum of 8-10 years of relevant professional experience in research and studies focusing on human capital development, economic empowerment, market systems development for marginalized populations, demand driven employability and green skills or entrepreneurship. - Strong background and experience in data collection and evidence-based analysis with the use of digital aided platforms/tools. - Demonstrable experience in conducting similar assignments in Somalia. Knowledge of local context is highly preferred - demonstrated ability to produce clear, compelling, and succinct analytical reports from multiple sources that inform quality programming. - Excellent communication and report writing skills |  |
|  | KEY PROFESSIONAL STAFF REQUIREMENT |  |  |
|  | Description | Minimum Qualification and professional experience |  |
|  | Human Capital Assessment expert/Technical Team Lead | - Post-graduate degree in economics, Statistics, development studies, Social Sciences or other related qualifications. - Minimum of 8-10 years of relevant professional experience in research and studies focusing on human capital development, economic empowerment, market systems development for marginalized populations, demand driven employability and green skills or entrepreneurship. - Strong background and experience in data collection and evidence-based analysis with the use of digital aided platforms/tools. - Demonstrable experience in conducting similar assignments in Somalia. Knowledge of local context is highly preferred - demonstrated ability to produce clear, compelling, and succinct analytical reports from multiple sources that inform quality programming. - Excellent communication and report writing skills. |  |
|  | 11 EVALUATION CRITERIA The proposals submitted by consulting companies will be evaluated based on the following criteria: |  |  |
|  | Essential Criteria |  | Pass/Fail |
| 1 | The Bidder and its staff agree and Sign to comply with SCI policies embedded below at this ITB. The Bidder is to download below listed items, read, understand and sign off appropriate section in below. a) Terms & Conditions of Bidding b) Supplier Sustainability Policy and the included mandatory policies |  | Pass/Fail |
| 3 | A valid Certificate of Registration from the relevant Ministry of Commerce in Somalia/land. NB: This is only applicable to firms and not individual consultants. |  | Pass/Fail |
| 4 | A valid Tax Compliance Certificate the relevant ministry of Finance/Revenue Authority in Somalia/land. NB: This is only applicable to firms and not individual consultants. |  | Pass/Fail |
|  | Capability Criteria (Technical Evaluation): |  |  |
| 5 | Detailed technical proposal with clear understanding of the TOR and Methodology of how the consultant intends to conduct assignment with detailed work plan, clear milestones, methodologies, data analyses plan including any software to be used for analysis. This to be evaluated based on: - Overall quality, clarity, organization and relevance of the technical proposal document – (20 marks max.) - The level of work plan detail and how it is related to the proposed methodology - (10 marks max.) |  | 30 marks |
| 6 | Two Copies of the previous similar reports relevant to the subject matter. (15 marks – with each similar report being awarded 7.5 marks) |  | 15 Marks |
| 7 | Submit official and genuine signed official bank statement from 1st August 2024 to 31st July 2025. |  | 10 Marks |
| 8 | Experience in conducting similar assignments related to the subject matter as proven experience. This to be evaluated based on: - Prior experience in design and development Human capital assessments/labor market, market systems or MSMEs - (10 Marks) - Two CVs for the proposed technical team detailing qualifications and experience (10 Marks) - Cover letter introducing the company, outlining their technical expertise and interest for the assignment including their technical suitability. (5 marks max). - Updated Company Profile (Optional) |  | 25 Marks |
|  | Commercial Criteria (Financial Evaluation): |  |  |
| 9 | Detailed financial proposal with budget breakdown including all expenses, fees, and taxes. 100% x Lowest bid valueCurrent value bid x 0.20 |  | 20 marks |
|  | Total |  | 100 marks |
| Note: For the technical analysis, a company must pass the essential criteria and score 60% and above on the capability to be considered in the next evaluation process and the ultimate decision will be based on interview performance. |  |  |  |
| 11 | Application Procedure | - Interested consultant (s) who meet the consultancy requirements are requested to submit their bid and each application package should include the above required minimum requirements. Applications can be submitted by: Protected Email box below - Email should be addressed to Somalia.Tenders@savethechildren.org - Should you need any clarifications please direct your queries to Somalia.procurement@savethechildren.org and expect responses within maximum of two working days. - Note – this is a sealed tender box which will not be opened until the tender has closed. Therefore, do not send tender related questions to this email address as they will not be answered. The subject of the email should be TERMS OF REFERENCE FOR UNDERTAKING A HUMAN CAPITAL AASSESSMENT FOR MCRO, SMALL AND MEDIUM ENTERPRISES IN SOMALIA AND SOMALILAND - All attached documents should be clearly labelled so it is clear to understand what each file relates to. - Emails should not exceed 15mb – if the file sizes are large, please split the submission into two emails. - Do not copy other SCI email addresses into the email when you submit it as this will invalidate your bid. All applications MUST be submitted on or before the closing date below to be considered for the assignment. Only shortlisted Candidates will be contacted. |  |
| 12 | Closing date for Applications | Interested consultants shall submit their applications through the above procedures on or before 29th August 2025. |  |

| We, the Bidder, hereby confirm we compliance with the following policies and requirements: |  |  |
| --- | --- | --- |
| Policy | Policy / Document | Signature |
| Terms & Conditions of Bidding |  |  |
| Supplier Sustainability Policy and the included mandatory policies | Click Here to Access |  |

| We confirm that Save the Children may in its consideration of our offer, and subsequently, rely on the statements made herein. |  |
| --- | --- |
| Signature: | ………………………………………………….. |
| Name: | ………………………………………………….. |
| Title: | ………………………………………………….. |
| Company: | ………………………………………………….. |
| Date: | ………………………………………………….. |

TERMS OF REFERENCE FOR UNDERTAKING A HUMAN CAPITAL AASSESSMENT FOR MCRO, SMALL AND MEDIUM ENTERPRISES IN SOMALIA AND SOMALILAND

1.    INTRODUCTION

Save the Children is the world’s leading independent organisation for children. We work in 120 countries. We save children’s lives; we fight for their rights; we help them fulfil their potential.

We work together, with our partners, to inspire breakthroughs in the way the world treats children and to achieve immediate and lasting change in their lives. Following a major transition, our international programmes are now delivered through a merged operation with 15,000 staff, managed through seven regional hubs and reporting to a relatively small, central office. We’re changing to become more efficient, more aligned, a better partner, a stronger advocate, a magnet for world-class people and relevant for the 21st century.

Save the Children has worked in Somalia since 1951 when we set up a vocational school for orphaned boys in Somaliland. From the early 1970s we have provided emergency assistance when the needs demand. Each year, about 650,000 people benefit from our longer-term development work in Health, Nutrition, Water, Sanitation & Hygiene (WASH), Education, Food Security and Livelihoods (FSL), Child Protection and Child Rights Governance

Somalia faces a protracted climate crisis marked by prolonged droughts, floods, and environmental degradation, which continue to affect livelihoods, exacerbate displacement, and heighten the urgency for climate-resilient and inclusive durable solutions. According to the ND-GAIN Country Index, Somalia ranks 164th in terms of readiness for climate induced shocks, highlighting the severe gaps in its ability to adapt and mitigate the effects of a changing climate. The rapid urbanization resulting from these factors has significantly altered the demographic landscape of the country, leading to crowded IDP settlements forming in or near urban centers. Uncontrolled urbanization has brought challenges of congestion, unsustainable land consumption, inaccessible service provision, overstretched resources, disconnected, poor and limited infrastructure, public space deficit and environmental degradations in target districts.

Urban areas are increasingly strained under the weight of new arrivals who often lack essential skills and resources to thrive in their new environments. In the absence of climate adaptive and inclusive urban planning, these city dwellers with majority being youth, women and children are extremely exposed to increased climate change risks like floods, disease outbreaks and excess mortality, loss of household and livelihood assets. It is estimated that 73 percent of the Somali population is aged under 30. Within this group, internally displaced youth and young returning refugees are considered among the most marginalized and at-risk groups in the country.

It is against these overlapping shocks and deprivations, affecting displaced affected communities that, Save the Children in Somalia/Somaliland, the Norwegian Refugee Council (NRC) and Gargaar Relief and Development Organization (GREDO) are currently implementing a 4 year long urban resilience project (URGANISE) funded by Danish Royal Embassy in Somalia (RDE). The project aims to focus on building human capital of displaced affected communities to tap into green sectors and integrate nature-based solutions into urban service delivery and climate resilience in Somalia and Somaliland.  The target Project locations are Kismayo, Baidoa and Dhusamareb, Burao and Las’anod as being locations affected by climate induced urban poverty.

As such, URBANISE has three intertwined outcomes that will contribute to enhancing the adaptive capacity and resilience of urban communities towards climatic shocks, variability and change. These outcomes are

- Outcome 1. Mandated government structures are more inclusive and better advocate for and manage community priorities that promote self-reliance, including in the face of conflict and climate-related risks

- Outcome 2. Urban and peri-urban displacement-affected communities (DACs), particularly minorities, women and youth, engage in diversified livelihood opportunities and financial inclusion pathways, applying rural-urban linkages to conflict-, and climate-related risks

- Outcome 3. Wellbeing of urban and peri-urban DAC residents, including minorities, women and youth, is preserved through more responsive, climate adapted services at neighbourhood-level

The project works with key government agencies including the Ministry of Planning, Investment, Economic Development (MOPIED) and the Ministry of Labour and Social Affairs.

2.Overall OBJECTIVE OF THE STUDY

Save the Children seeks a qualified consulting firm with a strong and demonstrable background in human capital development, including employment creation, business development or SME support, life skills and , acces to finance). Under this assignment, the firm will assess and identify priority life and business skills among DACs by mapping existing and under-recognized skillsets, analyzing market demand and opportunities for green economic transition, and understanding access to financial services. This exercise will identify existing, relevant curricula and/or to inform the design of supplementary, climate-resilient human capital development curricula and interventions for URBANISE. URBANISE will give deference to existing materials that are of sufficient quality for the intervention and does not seek solely to establish new materials for the sake of it.

The firm will achieve this by starting with a comprehensive desk-based  analysis about existing climate resilient small scale enterprises that present opportunities for DACs(-), followed by examining enabling factors such as access to financial services, availability and relevance of business development or enterprise support centers and the broader financial inclusion landscape. In addition, the study will assess the life skills needed for employability and personal development and aspirations of DACs for participating in identified demand skills and sectors. Uniquely, this should include consideration of “green life skills” or alternatively adaptive lifestyle and livelihood measures that are possible within an individual household and are informed by local climate and disaster risk scenarios. The insights generated will directly inform the design of inclusive, climate-resilient human capital development curricula that integrate technical, business, and life skills aligned with current and future market demands, in clear consideration of future climate scenarios. The firm shall ensure insights and recommendations are equally reflecting the needs of men,women and persons with disabilities including the curricula. URBANISE aims to provide equitable integration of DACs to IGAs and markets and hence picking the dissagregated needs and priorities of different groups helps in identifying and implementing targetted interventions.

The firm should possess proven experience in Somalia synthesizing secondary information and undertaking human capital diagnostics

3. SPECIFIC OBJECTIVES OF THE STUDY

1.Conduct a desk-based assessment and where necessary, primary data about climate resilient existing or emerging small scale business opportunities, for DACs. These include including agribusiness and other promising value chains or IGAs identified in prior analyses—with the aim of evaluating their livelihood and income-generation potential for displacement-affected communities in target locations (Dhusamareb, Baidoa, Kismayo, Burao, and Las’anod). For a quality and localized diagnosis, the Consultant will diagnose the following documents among others looking at key economic dimensions namely (revenue or growth, market expandability, employability potential, Inclusive to women, youth or persons with disability, and potential contribution to community adaptation/risk management and climate mitigation/environmental benefits). The list is non-exhaustive, and the consultant is expected to update the list during the inception stage.

        - GIZ developed labor market study and curricula including Agri-business modular curricula

        - Previous labor market assessments conducted by NRC, Save the Children ((including IMPACT), Somalia National Bureau of Statistics (SNBS), UN-Habitat under Saamaynta Project, among others.

        - Baseline assessments conducted by BRCIs focusing on productive sectors and Durable solutions assessments conducted by Danwadaag (IOM) and MOPIED.

        - Baseline Assessment by IMPACT project (Save the Children0

        - Resilience Design Training (RDT) modules developed under BRCiS.

        - Human Capital Development (HCD) strategies/policies or other evidence developed by Heritage Institute,

        - Somalia Joint Education Sector Strategic Plan, SOM-INVEST green sector plans under MOPIED.

        - SCI’s life skills curricula, Literacy and Numeracy by GREDO

        - SCI’s impact evaluation for Horumarinta Elmiga (human capital development components).

        - Green Skills assessment conducted by GREDO in Baidoa under Danida SPA programme (Save the Children).

        - Financial inclusion assessments and modules/curricula developed by partner organizations, Gargaara Fund or other entities including financial service providers in target locations.

        - Local climate and disaster risk scenarios and action/adaptation plans

2.Find out what specific human capital skill sets (entrepreneurial and life skills) are needed in each of the identified MSMEs so that they can be upskilled to youth/women DACs. The consultant shall validate identified skill sets with target stakeholders under URBANISE Consortium members and government agencies. The diagnosis should be smart i.e.: specific human capital skills, their supply and demand needs, human capital skill specification requirements, and options for skilling, re-skilling for DACs.

3.Assess what financial options (both formal and informal) are available for MSMEs owned by displaced affected communities (DACs) focusing on the MSME sector. These shall include existing financial service providers including informal micro-lenders or saving structures at community level, available credit and grant products, lending criteria, payback period or other financing conditions.

4. Assess the ecosystem of small-scale business development and life skills training support in target project locations. To ensure there is an availability of service providers for entrepreneurship and life skills training for DACs in target locations, the consultant will undertake the following.

- Map out human capital development service providers (both formal and informal) in target locations in relation to the provision of identified small scale business skills and associated life skills and transforming challenges identified into opportunities.  When service providers are identified, the consultant will dive deep into.

- Availability of curricula. These include life skills, entrepreneurship and curricula pertaining to the micro and small-scale business opportunities identified. The consultant will consult with a range of documents to extrapolate available curricula and gaps related to the micro and small-scale business landscape.

- Infrastructure of the human capital skills providing institution (gender sensitive training classrooms, innovation spaces if any, arrangement of other associated rooms e.g. gender sensitive washrooms, emergency facilities and accessibility/proximity for marginalized youth and women).

- Availability of qualified trainers including business development/coaching or mentors, their technical, facilitation or pedagogical skill levels and gaps related to providing identified human capital skills.

- Management and relationship: Board and management structure and linkage with responsible government agencies (MOPIED and Ministry of Labor), in relation to collaborating on market actors (employers, financial service providers, or associations).

- Linkage potential or partnership structures with other human capital or income generation actors. These include but not limited to, assessing the post service support provided to women and youth DACs, (etc value chain market actors linkages), or financial service including mobile money saving accounts)

- Other post follows up/ post support provided to graduates including mentorship, investment readiness, technical assistance. These services enable DACs access bespoke and personalized assistance.

- Diagnose the existing policies, strategies, and regulatory frameworks that support the development of human capital within identified green sectors. These include life skills, entrepreneurship, financial or other market-oriented policies and regulations that underpin transition to sustainable self-employment

NB: as this is an inclusive study, the study will develop specific research questions relating to gender per specific objective. The study shall specifically draw the gender disparity between the two groups and recommend future actions for fostering equitable human capital development for the MSME sector. Focus should also consider other intersectionality including minorities, disabled, ethnic minorities of the DACs and their host communities.

4.    SCOPE OF WORK

The study will be implemented in pre-identified target locations (Dhusamareb, Baidoa, Kismayo, Burao, and Las’anod). The study will focus on a number of stakeholders including incubations/enterprenourship hubs or business development services,financial institutions (both formal and informal including VSLAs, and government (MOPIED, MOLSA etc). Both formal and informal life skills providers will also be consulted. The study shall also generate insights from youth/women DAC participants to generate their aspirations in accessing sustainable IGAs.

5.   METHODOLOGY

The consulting firm is expected to conduct a desk assessment including those listed above and combine (qualitative) and complement with primary data where necessary. The information will be collected from stakeholders stated in the scoping section i.e. both public and private and target youth/women DACs in target project locations. The following guiding approaches should be applied throughout the assessment period.

- Desk review of secondary data including existing human capital curricula/manuals, reports of recent labour market studies, project documents, reports of assessments/evaluations conducted by URBANISE Partners or other like-minded organizations or companies (refer to the above desk information listing). A heavy junk of the assessment will be spent on desk study ideally 70% or above.

- Interviews with the youth and women DAC groups including those with or without disabilities who live in pre-selected project locations (Dhusamareb, Baidoa, Kismayo, Burao, and Las’anod) about their aspirations on the demanded green life skills, entrepreneurship and financial, linking to future climate resilient income generation choices or livelihood scenarios informed by climate.

- Interviews with key staff from URBANISE consortium members (Save the Children, NRC, GREDO and BRCiS CMU). Where necessary, interviews will be conducted with target ministries (MOLSA, MOPIED), -, business development services providers/ green life skills training providers, financial institutions and other community-based groups or associations supporting the project.

6. DATA ANALYSIS:

Data gathered using various methods and tools will be collated, analyzed and interpreted systematically. Qualitative data will be analyzed for key themes and used to supplement quantitative data organized into an array of sections.  Analyzed data should be used to find empirical findings for all the objectives of the study in a more succinct and compelling manner. Information presentations should be done in a coherent and consistent manner and presented in a structured report.

7. KEY DELIVERABLES

- Inception report: detailing the methodology including the main research methods, research matrix with substantive research questions, a sampling framework, workplan, proposed sources of data, procedures for data collection and analysis, and a draft but detailed table of contents. The proposed research tools will be discussed and approved by Save the Children and URBANISE CMU before data collection commences.

- Revised first Draft Final Report, incorporating suggestions and recommendations from URBANISE Partners.

- Organize a validation workshop to get inputs and views from all relevant stakeholders of the project. The workshop should be designed in a participatory manner to obtain objective inputs.

- A second round of revision may be required before the producing the final version of the report can be produced, ideally due to inputs from the validation workshop.

- A final report (one electronic copy in PDF Format and one in DOC format)

- An electronic copy of all data collection tools of the study with data sets including photos or other graphic captures made during field work.

8. DURATION OF THE ASSIGMENT:

The duration of the assignment will be 30 calendar days including travel days. This is inclusive of weekends

9. QUALIFICATIONS AND EXPERTISE REQUIRED

- Post-graduate degree in economics, Statistics, development studies, Social Sciences or other related qualifications.

- Minimum of 8-10 years of relevant professional experience in research and studies focusing on human capital development, economic empowerment, market systems development for marginalized populations, demand driven employability and green skills or entrepreneurship.

- Strong background and experience in data collection and evidence-based analysis with the use of digital aided platforms/tools.

- Demonstrable experience in conducting similar assignments in Somalia. Knowledge of local context is highly preferred

- demonstrated ability to produce clear, compelling, and succinct analytical reports from multiple sources   that inform quality programming.

- Excellent communication and report writing skills.

10.   APPLICATION PROCEDURE AND REQUIREMENTS:

Interested bidders are expected to provide the following documentation:

- A technical proposal of no more than 10 pages with detailed response to the TOR, with specific focus on understanding the TOR and presenting a succinct scope of work, methodology, sampling procedure and data. The proposal should also include team composition including their CVs and qualifications

- Initial work plan based on methodology outlined an indication of availability

- Itemized financial proposal including all associated costs (daily fee, logistics etc)

- Samples (minimum 2) of similar work completed.

11.   CODE OF CONDUT:

Save the Children's work is based on deeply held values and principles of child safeguarding, and it is essential that our commitment to children's rights and humanitarian principles is supported and demonstrated by all members of staff and other people working for and with Save the Children. Save the Children's Code of Conduct sets out the standards which all staff members must adhere to, and the consultant is bound to sign and abide to the Save the Children’s Code of Conduct.

A contract will be signed by the consultant before commencement of the action. The contract will detail terms and conditions of service, and aspects on input and deliverables. The Consultant will be expected to treat as private and confidential any information disclosed to her/him or with which she/he may come into contact during her/his service.  The Consultant will not therefore disclose the same or any particulars thereof to any third party or publish it in any paper without the prior written consent of Save the Children. Any sensitive information (particularly concerning individual children) should be treated as confidential.

An agreement with a consultant will be rendered void if Save the Children discovers any corrupt activities have taken place either during the sourcing, preparation and implementation of the consultancy agreement.