# INVITATION TO BID FOR CONSULTANCY

| 1 | Title of Consultancy | Provision of Consultancy Services for the Development on Safer, Greener and Inclusive School Infrastructure Guideline |  |
| --- | --- | --- | --- |
| 2 | SCI Contracting Office | Save the Children Somalia Country Office |  |
| 3 | Period of Consultancy | The assignment will be conducted 90 working days |  |
| 4 | Consultant type required | Consultancy Firm/individual consultant. |  |
| 5 | Responsibility for Logistics arrangements and Costs | Save the Children will pay the fees for the consultancy in a lump sum and will not reimburse any incurred costs during the assignment. The consultant will cover their Logistical arrangements and costs in the country to coordinate and implement the consultancy. |  |
| 6 | Taxation Provisions | The consultant shall be responsible for all Taxes arising from the consultancy in line with the local Tax regulations applicable at the SCI contracting office named above. |  |
| 7 | Travel requirements | The consultant will cover their travel costs (tickets) and arrange local travel to field sites if needed |  |
| 8 | Security requirements | The consultant will comply with standards of Save the Children Security procedures, including the completion of SCI online security training prior to travel to Somalia. |  |
| 9 | Professional quality and Expertise | The following are the minimum requirements for the consultant to be considered for carrying out the assignment Education: - The team leader and associates should have, at least, a BSC in Architecture, Civil Engineering, or a related field. Experience: - Demonstrated knowledge of construction practice in Somalia, ideal in school construction. - A minimum of 5 years' experience in the design and implementation of passive deign approaches. - Demonstrated experience of leading similar work preferably In Somalia. - Proof registration with relevant authorities and work permits. (Valid commercial and tax compliance certificate issued by the relevant Federal Ministries (Finance and Commerce) This requirement applies to consultancy firms only. - Demonstrated experience with quantitative and qualitative research, data management, and statistical data analysis. - Demonstrated experience in applying universal design and accessibility standards in low resource settings. - Fluency in Somali and English and good communication and reporting skills. |  |
|  | EVALUATION CRITERIA The proposals submitted by consultant firms/Individual will be evaluated based on the following criteria: |  |  |
|  | Essential Criteria |  | Pass/Fail |
|  | The Bidder and its staff agree and Sign to comply with SCI policies embedded below at this ITB. The Bidder is to download below listed items, read, understand and sign off and stamp appropriate section in below. a) Terms & Conditions of Bidding b) Supplier Sustainability Policy and the included mandatory policies |  | Pass/Fail |
| 1 | If the consultant operates as a firm, a valid Commercial License issued by the Ministry of Commerce and Industry of the Federal Government of Somalia is required- This requirement does not apply to individual consultants. |  | Pass/Fail |
| 2 | A valid Tax Compliance Certificate from the Ministry of Finance and Industry - Federal Government of Somalia is required from the Firm with good standing of Q4 2025- This requirement does not apply to individual consultants. |  | Pass/Fail |
|  | Capability Criteria (Technical Evaluation): |  |  |
| 3 | The technical proposal shall clearly and concisely present the bidder’s understanding of the assignment and its objectives. It should demonstrate a sound comprehension of the scope of work and outline the proposed technical approach to successfully carry out the task. The proposal must include a detailed description of the methodology to be applied, including the technical processes, tools, and strategies that will be used to achieve the expected results. Additionally, a comprehensive and well-structured work plan should be provided, detailing the sequence of activities, timelines, and key deliverables. The proposal will be evaluated based on, (A). The overall quality, clarity organization and relevance of the technical proposal including understanding of the TOR, objectives and scope of the assignment (10 marks) (B). A comprehensive and well-structured work plan, detailing the sequence of activities, timelines, and key deliverables (10 marks) C, |  | 35 marks |
|  | (C)Detailed description of the approach / methodology to be applied, including the technical processes, tools, and strategies that will be used to achieve the expected results with clear approach to monitoring, evaluation and detailing how progress and results will be tracked ,analyzed and communicated through effective reporting to enhance accountability (15 marks) Experience in conducting similar assignments related to Development of Safer, Greener and Inclusive School Infrastructure Guidelines or related fields. This to be evaluated based on: - Prior experience in conducting Consultancy on Consultancy for the Development of Safer, Greener and Inclusive School Infrastructure Guideline or related activity– Please provide at least two contracts and/or LPOs - (15 Marks each carry 7.5 marks) - Submission of at least two curriculum vitae (CVs) for the proposed technical team—specifically the Team Leader and Co-Lead—clearly outlining their relevant academic qualifications and professional experience in Architecture, Civil Engineering, or a closely related discipline. (Total: 10 marks; each CV carries 5 marks) - Cover letter introducing the company, outlining their technical expertise and interest in the assignment as well as their availability and commitment. (5 marks max). - Updated Company Profile (Optional) |  | 30 marks |
|  | Sample of previous work: The consultant must share at least Two Copies of the previous similar reports relevant with the subject matter. (15 marks – with each similar report being awarded 7.5 marks) |  | 15 marks |
|  | Financial proposal: submit a signed financial proposal/ budget of the tasks should be broken down into modules, detailing the following: Consultancy fees, tools development cost, Data processing & analysis, Communication, and Reporting costs and other Miscellaneous (stationery, printing, etc.), inclusive of the Mandatory taxes as per the laws of Somalia. (20 marks) Detailed financial proposal with budget breakdown including all expenses, fees, and taxes. 100% x Lowest bid valueCurrent value bid x 0.20 |  | 20 marks |
|  | Total |  | 100 marks |
| Note: For the technical analysis, the Firm must score 70% and above on the capability to be considered in the next evaluation process and the ultimate decision will be based on interview performance. |  |  |  |
| 11 | Application Procedure | - Interested firms/individuals who meet the requirements are requested to submit their bid and each application package should include the above required minimum requirements. Applications can be submitted by either: Electronic Submission via ProSave (Recommended) - Submit your response in accordance with the guidance provided in the below document: - Bidders are encouraged to apply via Ariba system. Please request the Ariba link via email sending your company profile and Business registration certificate/CV. Please address your Ariba link request to css.logistics@savethechildren.org - Note – this is a sealed tender box which will not be opened until the tender has closed. Therefore, do not send tender related questions to this email address as they will not be answered. Electronic Submission via Protected Email box (Optional) - Applications must be submitted via email should be addressed to Somalia.GPEProcurement@savethechildren.org The subject of the email should be Provision of Consultancy Services for the Development on Safer, Greener and Inclusive School Infrastructure Guideline - Applicants must submit a technical proposal and financial proposal as a single PDF document. - All attached documents should be clearly labelled so it is clear to understand what each file relates to. - Emails should not exceed 15mb – if the file sizes are large, please split the submission into two emails. - Do not copy other SCI email addresses into the email when you submit it as this will invalidate your bid. Applicants should also indicate the date they are available to start working on the consultancy All applications MUST be submitted on or before the closing date below to be considered for the assignment. Only shortlisted Candidates will be contacted. |  |
| 12 | Closing date for Applications | Interested consultants shall submit their applications through the above procedures on or before 14th January 2026. |  |

| We, the Bidder, hereby confirm we compliance with the following policies and requirements: |  |  |
| --- | --- | --- |
| Policy | Policy / Document | Signature |
| Terms & Conditions of Bidding |  |  |
| Supplier Sustainability Policy and the included mandatory policies | Click Here To Access |  |

| We confirm that Save the Children may in its consideration of our offer, and subsequently, rely on the statements made herein. |  |
| --- | --- |
| Signature: | ………………………………………………….. |
| Name: | ………………………………………………….. |
| Title: | ………………………………………………….. |
| Company: | ………………………………………………….. |
| Date: | ………………………………………………….. |

Terms of Reference (TOR) for Consultancy for the Development of Safer, Greener and Inclusive School Infrastructure Guideline

Background:

The Federal Government of Somalia Ministry of Education, Culture and Higher Education (MoECHE) is implementing the Global Partnership for Education (GPE) funded Climate Smart Education Systems Initiative (CSESI) with Save the Children, UNESCO and UNESCO’s IIEP. CSESI seeks to enhance countries’ capacities to mainstream climate change adaptation and environmental sustainability into education sector plans, budgets and strategies, as well as to enhance education ministry capacity for cross-sectoral coordination on climate and environment-related policy and programming. Somalia is one of the priority countries for the Initiative. CSESI is built around seven component areas outlined further in the work program which are underpinned by the principles of equity, inclusion and resilience. The components include 1) Evidence-based policies and planning, 2) Cross-sector and internal coordination, 3) Access to climate finance, 4) Climate data and evidence for education planning, 5) Safer and greener infrastructure, 6) School safety and educational continuity and 7) Curricula, pedagogy and teacher training.

This work program was developed following a two-day consultative workshop held on the 7th and 8th April 2025 in Mogadishu. The workshop was led by the federal Ministry of Education, Culture and Higher Education (MoECHE), especially the MOECHE Climate Change Education Unit, with the Ministry of Environment and Climate Change, the Somali Disaster Management Agency (SODMA), civil society, UN agencies, universities and other partners from the Education Sector Committee (ESC) and CSESI partners. The feedback from the group discussions fed directly into the proposed interventions included within this document.

Assignment overview

CSESI will support the preparation of safer, greener, and inclusive school infrastructure guidelines. The scope of this guideline will be agreed with MoECHE and will be developed using a participatory approach with key partners in Somalia. The guideline will be used in the GPE Systems Transformation Grant (STG), and as a resource for use in other programmes, and will drive evidence to influence existing school construction standards in Somalia in the long term.

Purpose of the consultancy assignment

The purpose of this assignment is to contribute to efforts in Somalia to ensure education infrastructure is safer, greener, inclusive and more resilient to the impacts of climate change.  The assignment will strengthen the capacity of MoECHE and key sector partners to plan, budget for, and manage safer and greener, and more climate-resilient education infrastructure.

Specific objectives to be achieved.

The consultancy aims to achieve the following objectives.

1) To conduct a comprehensive climate risk-informed review of Somalia's existing school infrastructure policies and guidelines, identifying gaps and opportunities for enhancement. This review will incorporate a gender sensitivity and disability-inclusive lens.

2) To co-develop with MoECHE and partners context-specific, costed technical guidelines for climate-resilient and environmentally sustainable school construction, retrofitting, and maintenance, tailored to Somalia's primary ecological zones.

3) To integrate these guidelines into MoECHE's core planning and financing processes, specifically the Systems Transformation Grant (STG) and School Improvement Plans.

4) To build the technical and managerial capacity of the Department of Physical Planning and Construction and key partners for the ongoing implementation and future updating of the guidelines.

Proposed activity descriptions.

- Hold a series of consultations with MoECHE technical teams and specialists with expertise in safer, greener and inclusive infrastructure to agree on the focus for this assignment – new construction, retrofitting or maintenance of existing school infrastructure

- Review and analyse the Somalia School Construction Guidelines and other key resources and their suitability to respond to climate change impacts across different ecological zones

- Recommend modifications to the school construction, retrofitting and maintenance guidelines appropriate for the identified hazard zone associated with the specified ecological zones and utilizing the universal design principles of safer, gender inclusive and disability inclusion.

- Prepare training materials and provide training to MoECHE and education sector partners in Somalia, including the GPE STG team, on how to implement the guidelines.

Scope of work

- Inception phase

- Preparation of the inception report, including consultative work with MoECHE and education sector partners in Somalia ensuring the technical work is grounded in a shared understanding of the policy landscape and existing capacities.

- Code and standards review

  - Review the Infrastructure policy, construction and maintenance guidelines, identifying gaps concerning how the guidelines accommodate projected climate change impacts such as increased extreme heat, droughts, cyclones, higher wind loads and flooding. Note that the successful applicant will be provided with scientifically agreed-upon climate change impacts in Somalia.

  - Benchmark school infrastructure standards and maintenance guidelines against regional and international best practices for climate-resilient design, inclusive construction and maintenance practices.

- Desk review and stakeholders’ consultations on Climate impacts on school infrastructure in different ecological and climate zones of Somalia

  - Conduct a desk-based review and stakeholder consultations to identify current gaps in school infrastructure from a climate change perspective and where the CSESI project could best contribute. The consultations will also identify prevailing climate impacts on school infrastructure (e.g., what have the historic impacts of wind loads, cyclones, floods, high temperatures been on schools and school attendance in different zones of the country) and develop a set of climate impact scenarios for the different ecological and climate zones of the country (e.g. dry zones, flood zones, windy areas etc).

- Construction Guidelines Modifications

  - Based on the climate impact scenarios developed, prepare a comprehensive set of inclusive, resilient infrastructure guidelines for modifying current school designs, or retrofitting and maintenance of existing schools to enhance the resilience of school infrastructure to climate change impacts in the different ecological and climate zones of Somalia. The exact scope of this work will be dependent on findings from the consultations to ensure CSESI contributes to where there are gaps in current guidelines.

  - Include safety, durability, environmental sustainability, gender sensitivity and disability inclusive in the modified designs.

- Cost Estimation for guidelines modifications, retrofits and maintenance

- Provide Bill of Quantities (BoQs) and detailed cost estimates for:

  - proposed design modification to the construction guidelines; and

  - the retrofitting of existing schools to meet enhanced climate standards

  - the maintenance of the school infrastructures

- Include analysis of the most impactful cost-effective options and potential phased implementation to optimise budget use.

- Capacity Building

  - Provide awareness-raising and training sessions to MoECHE and education sector partners in Somalia, including the GPE STG team, on how to implement, train others and advocate for the guidelines increasing their knowledge and understanding of how infrastructure can be made more resilient, inclusive to the projected impact of climate change.

Key stakeholders:

The Department of Physical Planning and Construction in MoECHE, and the Engineering Unit in the Ministry of Housing, Education Sector Committee and Education cluster members involved in school construction and retrofit, climate change task force, Meteorological department of Somalia to support with both current and future data predictions, architects, structural engineers, geotechnical engineers, and environmentalists, gender and disability inclusion experts, School administration and staff, learner and parents, will be among the key stakeholders in this activity. Other partners involved in school construction (temporary and permanent) will also be engaged. The end beneficiaries will be all school facility users – including students (including learners with disabilities, teachers, and school support staff.

Reporting: Regular progress report to be submitted to the project stakeholders, including regular updates and a final project completion report.

Evaluation: The assignment will be evaluated based on:

- The technical robustness, practicality, and inclusivity of the final Safer, Greener and Inclusive School Infrastructure Guideline.

- Evidence of successful capacity transfer to MoECHE staff, as measured by post-training assessments and feedback.

- The development of a clear action plan for integrating the guideline into the STG and School Improvement Plans.

- Formal endorsement and validation of the guideline by the MoECHE Technical Working Group and the Education Sector Committee.

Deliverables:

1. Inception Report (including stakeholder map, detailed methodology, and work plan).

2. Draft Climate Risk and Infrastructure Gap Analysis Report.

3. Draft Safer, Greener, and Inclusive School Infrastructure Guideline (the main deliverable, containing all technical specifications, BoQs, costing, and drawings), along with operation and maintenance planning considering different designs and ecological zones.

4. Validation Workshop Report (documenting feedback from the ESC and other stakeholders).

5. Final Safer, Greener, and Inclusive School Infrastructure Guideline (incorporating all feedback).

6. Training Modules and Workshop Report (including pre/post-training evaluations).

7. Final Consultancy Report (summarizing the entire process, lessons learned, and recommendations for rollout and future updates).

Budget and Payment Terms

The budget for the consultancy will be allocated based on a detailed cost breakdown provided by the consultant or consultancy firm. Payments will be disbursed in instalments upon satisfactory completion and approval of agreed upon milestones and deliverables between Save the children and the consultant.

Duration and Timeframe

The duration of the assignment will be a total of 90 working days from the date of the contract signing.

APPLICATION PROCESS AND REQUIREMENTS

Qualifications, Experience and Skills

SCI Somalia invites competent and experienced individuals or firms to submit their technical and financial proposals. Interested individuals or firms must possess the following qualifications as a minimum.

- The team leader and associates should have, at least, a BSC in Architecture, Civil Engineering, or a related field.

- Demonstrated knowledge of construction practice in Somalia, ideal in school construction.

- A minimum of 5 years' experience in the design and implementation of passive deign approaches.

- Demonstrated experience of leading similar work preferably In Somalia.

- Proof registration with relevant authorities and work permits. (Valid commercial and tax compliance certificate issued by the relevant Federal Ministries (Finance and Commerce) (Compulsory and any firm without it will not be considered for shortlisting and rating).

- Demonstrated experience with quantitative and qualitative research, data management, and statistical data analysis.

- Demonstrated experience in applying universal design and accessibility standards in low resource settings.

- Fluency in Somali and English and good communication and reporting skills.