# TERMS OF REFERENCE

Oxfam is a global movement of people who are fighting inequality to end poverty and injustice. Across regions, from the local to the global, we work with people to bring change that lasts.

| OVERVIEW |  |
| --- | --- |
| Title and brief description of the assignment | Market Assessment for Viable Livelihoods and Economic Opportunities in 20 IDPs and Host Communities in Burao District |
| Assignment location | Burao, Somaliland |
| Contract start date | 24th July 2025 (tentatively) |
| How to apply | Interested applicants (individual consultants or consulting firms) are invited to submit the following documents: - Technical Proposal (maximum 15 pages), outlining the understanding of the assignment, proposed methodology, work plan, and team structure. - Financial Proposal, clearly detailing the total cost of the assignment, inclusive of all fees, taxes, travel, and other related expenses. - Curricula Vitae (CVs) of key technical personnel who will be involved in the assessment, highlighting relevant experience and qualifications. - Two samples of previous relevant work, preferably market assessments or similar consultancies undertaken in humanitarian or displacement contexts. See section ‘7. Application Process’ for further details |
| Application deadline | 23rd JULY 2025 |
| Specific considerations |  |

# PURPOSE OF THIS CONSULTANCY

The purpose of this consultancy is to explore and identify viable livelihood opportunities with strong economic growth potential within 20 selected IDP camps and host communities in the Togdheer region. The assessment will adopt a market systems approach to examine existing and potential sources of livelihood, identify market gaps, and analyse key barriers and enabling factors.

The consultancy will generate practical and actionable recommendations to support the development of sustainable livelihoods, with a particular focus on youth and women. It will also outline a clear pathway to reduce aid dependency and promote the transition towards self-reliant, resilient communities.

# SCOPE OF WORK

The selected consultant or firm will be expected to undertake the following tasks:

- Conduct an in-depth desk review of relevant reports, assessments, and existing secondary data related to livelihoods, market systems, and displacement-affected communities in the region.

- Design and implement a comprehensive field data collection exercise across 20 IDP camps and host communities in Burao, ensuring appropriate sampling and methodological rigour.

- Apply market systems analysis tools to examine selected sub-sectors, and where relevant, facilitate sub-sector workshops to deepen analysis and stakeholder engagement.

- Interview key market actors, including micro, small and medium-sized enterprises (MSMEs), producers, financial service providers, government and regulatory institutions, NGOs, and other relevant stakeholders.

- Conduct focus group discussions (FGDs) and key informant interviews (KIIs) with IDP community members, ensuring disaggregation by gender and age to capture diverse perspectives.

- Validate preliminary findings with stakeholders by organising and facilitating a validation workshop.

- Prepare and submit a final comprehensive report that includes detailed findings, analysis of priority sectors, recommended business models, and practical programmatic options tailored to the local context.

# EXPECTED OUTPUTS

## Overall objective

conduct a market assessment to identify viable livelihood opportunities for IDPs and host communities in Burao, Togdheer region. The assessment will inform the development of context-specific and impactful business models aimed at fostering economic growth, generating employment, and increasing income—especially for young people and women.

## Specific outputs

- Map existing livelihood sources and activities among internally displaced households and host communities in the selected locations.

- Identify high-potential economic sectors and value chains with opportunities for scaling up, particularly for youth and women.

- Analyse the market systems related to these potential livelihoods, including core value chains, supporting services, and the relevant rules and regulatory environment.

- Identify key market gaps, constraints, underperformance, and opportunities within the targeted sectors and value chains.

- Assess the skills, knowledge, and capacities of IDP populations in relation to the identified economic sectors and potential livelihood opportunities.

- Provide actionable and context-specific recommendations, including alternative livelihood solutions and adaptable business models. These should guide Oxfam and stakeholders in designing inclusive, market-driven livelihood interventions that promote sustainability and resilience.

# METHODOLOGY

The assessment should employ a mixed-methods approach, integrating both qualitative and quantitative data collection, supported by an in-depth desk review of existing literature, reports, and datasets. All tools and methodologies used must be inclusive, conflict-sensitive, and context-specific, considering the socio-cultural dynamics of the target population, including gender, age, and vulnerability status.

The following methodological components are recommended:

- Quantitative household surveys among IDP populations, using structured questionnaires to collect data on livelihood activities, income sources, market access, and related indicators.

- Qualitative interviews, including Key Informant Interviews (KIIs) and Focus Group Discussions (FGDs), with diverse community members, local leaders, and relevant stakeholders to gain deeper insights into market dynamics, social norms, and perceived livelihood opportunities.

- Market mapping and value chain analysis to identify existing and potential economic sectors, their structure, key actors, supporting services, and regulatory frameworks.

- Livelihood and skills profiling of IDP and host community members to assess capabilities, experience, and training needs relevant to target sectors.

- SWOT and gap analysis of key sectors to determine strengths, weaknesses, opportunities, and threats, and to highlight critical capacity and service gaps.

- Gender and social inclusion analysis to assess the differential impact of market systems on women, youth, and marginalised groups, and to identify strategies for their meaningful participation in economic activities.

The consultant is encouraged to refine the methodology and propose additional context-appropriate tools as needed, in consultation with Oxfam.

## Planned timeline

The assignment will be conducted with an estimated duration of 30 days from the date of signing the contract

# DELIVERABLES AND PAYMENT SCHEDULE

Remuneration is based on submission of final deliverables according to the schedule below.

| No. | Deliverables or Documents to be delivered | Estimated Dates | % Payment |
| --- | --- | --- | --- |
| 1 | DELIVERABLE 1 - Inception Report: A detailed report outlining the proposed methodology, data collection tools, sampling strategy, fieldwork plan, and ethical considerations. The report should also include a work plan and timeline and demonstrate readiness for field-level implementation. | 30th July,2025 | 30% |
| 2 | DELIVERABLE 2 - Fieldwork Summary: A concise report capturing fieldwork activities, including locations covered, data collection methods employed, challenges encountered, and a summary of the raw data gathered using both qualitative and quantitative tools. | 10th August 2025 |  |
| 3 | DELIVERABLE 3 - Stakeholder Validation Workshop: Design and facilitate a validation workshop to present and discuss key preliminary findings with Oxfam and relevant stakeholders and incorporate feedback into the final report. | 17th August 2025 |  |
| 4 | DELIVERABLE 4 - Final Assessment Report: A comprehensive report that includes detailed findings, analysis, and actionable recommendations. The report should also provide context-specific, inclusive business models and programmatic options aimed at enhancing sustainable livelihoods for IDPs and host communities, particularly youth and women. | 23rd August 2025 | 70% |
| TOTAL |  |  | 100% |

# PROFILE REQUIREMENTS

The company/ individual(s) should have the following competencies:

Essential

- Advanced university degree in Economics, Development Studies, Business Administration, Livelihoods, or a related field.

- Proven experience (minimum 5 years) conducting market assessments, value chain analysis, and/or livelihoods studies, preferably in fragile or displacement-affected settings.

- Sound knowledge of market systems approaches, value chain development, and inclusive economic growth strategies.

- Strong understanding of gender and social inclusion dynamics, with experience integrating these considerations into research and programme design.

- Demonstrated capacity in both qualitative and quantitative research, including development of tools, data collection, analysis, and report writing.

- Familiarity with the Somali/Somaliland context, including cultural, economic, and displacement dynamics, is a strong asset.

- Excellent facilitation and communication skills, with the ability to engage diverse stakeholders, including community members, government actors, and private sector representatives.

- Fluency in English is required; working knowledge of Somali is highly desirable.

Desired

- Experience in using technology for research.

# APPLICATION PROCESS

## Submission deadline

Quotations and applications must be submitted to Oxfam not later than [ 23rd July 2025].

## Submission instructions

- Responses must be submitted electronically to: SOM-Consultancies@oxfam.org

The subject of the mail should be Call for expressions of interest: Market Assessment for Viable Livelihoods and Economic Opportunities in 20 IDPs and Host Communities in Burao District

- All attached documents should be clearly labelled so it is clear to understand what each file relates to.

## Clarifications

Any questions, remarks or requests for clarification can be sent up to 5 days before the submission deadline in writing. The (anonymised) questions will be answered to all applicants.

## Administrative compliance (list of documents to be submitted)

Responses must be submitted and prepared in [English] and received by the deadline.

To be shortlisted for evaluation against award criteria, the following documents must be included in the application:

| Administrative Criteria |  | Importance |
| --- | --- | --- |
| 1 | Technical Proposal (maximum 15 pages), outlining the understanding of the assignment, proposed methodology, work plan, and team structure. | Mandatory |
| 2 | Financial Proposal, clearly detailing the total cost of the assignment, inclusive of all fees, taxes, travel, and other related expenses. | Mandatory |
| 3 | Curricula Vitae (CVs) of key technical personnel who will be involved in the assessment, highlighting relevant experience and qualifications. | Mandatory |
| 4 | Two samples of previous relevant work, preferably market assessments or similar consultancies undertaken in humanitarian or displacement contexts. | Mandatory |
| 5 | Two relevant references (minimum) for previous comparable assignments | Mandatory |
| 6 | Proof of registration: The bidders also must include a copy of their registration at the relevant authority. | Mandatory |
| 7 | Evidence of conducting previous Similar work by providing minimum two Signed Contracts / Purchase Orders - (Preferably from UN agencies and INGOs). | Mandatory |

## Evaluation and award criteria

Incomplete applications will not be assessed, only quotations that meet the administrative criteria will be assessed.

Award decisions will be based on best value for money criteria covering both technical quality and price.

The award criteria are assessed according to the following distribution of points:

| Award Criteria |  | Max. points |
| --- | --- | --- |
| Technical offer/ approach paper evaluation |  |  |
| Experience/ competencies | Relevant experience with the NGO sector | 5% |
|  | Positive references/reputation | 5% |
|  | Relevance and quality of sample previous work, reporting etc. | 5% |
|  | Knowledge of country, context | 5% |
|  | Knowledge of team languages | 5% |
|  | Clearly indicated alignment with Oxfam values | 5% |
| Technical quality | Quality of application: complete, good presentation and format, etc. | 9% |
|  | Understanding of the assignment and the scope of the project | 9% |
|  | Quality of the methodology, workplan and feasibility of the timeline (concrete and realistic) | 9% |
|  | Quality and experience of staff resources assigned to the services + sufficient assigned resources (where relevant) | 9% |
|  | Ability to lead/manage a team (where relevant) | 9% |
| TOTAL: |  | 75% |
| Financial offer |  |  |
| Financial offer | Submission of realistic and acceptable financial proposal – reasonable budget breakdown and cost consideration detailing the daily rate expected including travel, accommodation, transportation, stationery, taxes arising from the consultancy service (6% tax for National consultant and 12 % tax for international consultants), and all other costs related to this assignment. (Operational and consultancy fees). The lowest evaluated financial proposal that meets the administrative criteria will be awarded the maximum point (25%). The points for all other Applications will be prorated. | 25% |
| GRAND TOTAL: |  | 100% |

Oxfam withholds the right to conduct interviews with one or more potential applicants before an award decision is made. The purpose of the interview is to seek further clarification on the submitted documents and learn more about the background and previous experiences of the potential suppliers and their teams.

# OTHER CONDITIONS

Issuance of this Terms of Reference does not constitute an award commitment on the part of Oxfam, nor does it commit Oxfam to pay for costs incurred in the preparation and submission of a bid.

The attached Annexes are an integral part of this Request for Proposals – see section 13.

Oxfam may contact bidders to confirm contacts, addresses, bid amount and to confirm that the bid was submitted for this solicitation.

OXFAM has the right to undertake due diligence to verify the references, and very details submitted before award.

## Quotation validity

- The quotation shall be valid for 90 days from the submitted. If this is not possible, the bidder may propose a different timeframe.

- If the bidder is awarded the contract, all information provided in the quotation and negotiation process is contractually binding.

## Right to Select/ Reject

Oxfam reserves the right to select and negotiate with those firms it determines, in its sole discretion, to be qualified for competitive proposals and to terminate negotiations without incurring any liability. Oxfam also reserves the right to reject any or all proposals received without explanation.

## Reserved rights

All applications and quotes become the property of Oxfam, and Oxfam reserves the right in its sole discretion to:

- Disqualify any offer based on applicant’s failure to follow solicitation instructions.

- Waive any deviations by the applicant from the requirements of these terms of reference that, in Oxfam’s opinion, are considered immaterial defects requiring rejection or disqualification; or where such a waiver will promote increased competition.

- Extend the time for submission of responses after notification to all applicants.

- Terminate or modify the process at any time and re-issue the request for quotation to whomever Oxfam deems appropriate.

- Issue an award based on the initial evaluation of offers without discussion.

- Award only part of the activities in the solicitation or issue multiple awards based on solicitation activities.

# CODE OF CONDUCT

Oxfam is committed to integrity in its operations and supply chains and ensuring high ethical standards. Complying with all laws and regulations and ensuring fair competition are fundamental to this commitment. We actively promote these principles and standards and expect all Oxfam suppliers to demonstrate commitment towards them.

All consultants/applicant are required to agree and adhere to the Oxfam Supplier Code of Conduct, whereas individuals (including consultants) must sign the Oxfam Non Staff Code of Conduct. These Codes of Conduct set out the specific standards and principles in the areas of human and labour rights, environmental impact and anti-corruption that suppliers must follow.

Oxfam has the following requirements of its service providers, to ensure integrity in its supply chain:

## Bribery and collusion

Oxfam does not tolerate fraud, including bribery or kickbacks, collusion among bidders, bribery or kickbacks. Any firm or individual violating these standards will be disqualified from this procurement and barred from future procurement opportunities.

Employees and representatives of Oxfam are strictly prohibited from asking for or accepting any money, fee, commission, credit, gift, gratuity, object of value or compensation from current or potential vendors or suppliers in exchange or as a reward for business.

## False statements

Bidders must provide full, accurate and complete information as required by this solicitation and Annexes. False statements in bids constitutes grounds for immediate termination of any agreement with the supplier. OXFAM takes misstatements, falsification, manipulation, alteration of facts and/or documents very seriously, has a zero-tolerance policy to such behaviours, and may choose to take legal action in a case of misrepresented disclosures by

## Conflict of interest

Bidders must provide disclosure of any past, present or future relationships with any parties associated with the issuance, review or management of this solicitation and anticipated award.  Failure to provide full and open disclosure may result in Oxfam having to re-evaluate the selection of a potential bidder.

## Diversion of funds

Oxfam is determined that all its funds and resources should only be used to further its mission and shall not be subject to illicit use by any third party nor used or abused for any illicit purpose. Suppliers (and their affiliates/group companies, employees, officers, owners, agents and sub-contractors) may be subject to formal screening against global lists of individuals subject to designation or proscription under financial sanctions or counter terrorism regulations.

# Monitoring

Due diligence: As a charitable organisation, Oxfam must take care to protect its assets and funds, as well as the communities that we work with. One of the steps that Oxfam takes to comply with this legal duty is to conduct adequate and proportionate due diligence on suppliers prior to entering a contract. This includes checking legal registration and financial solvency, but may also include other checks, such as misconduct/performance reference checks and if working with children or vulnerable adults, a criminal records check.

Important note: Oxfam performs a regular screening check of all suppliers against international sanctions lists.

Audit: Any audit requirements are detailed in the terms and conditions of business

Data protection: Oxfam is legally bound to ensure that all personal details held by the organisation relating to any individual or entity are kept secure and according to international data protection standards.

# MISCONDUCT REPORTING AND WHISTLEBLOWING

Oxfam’s reporting and whistleblowing mechanisms are available for Service Providers as well Oxfam employees, to ensure that Oxfam continues to operate under the highest ethical standards and principles.

You can use these reporting channels confidentially, anonymously, and in your own language to report any concerns involving fraud, corruption, waste, abuse or safeguarding concerns.

| Speak up |  |  |  |
| --- | --- | --- | --- |
|  | Oxfam GB | Oxfam Novib | Oxfam Intermón |
| Email: | SpeakUp@oxfam.org.uk | integrity@oxfamnovib.nl | buzon.etico@oxfam.org |
| Online: | Oxfam Misconduct Reporting Webform (including possibility for anonymous reporting) https://oxfam.clue-webforms.co.uk/webform/misconduct/ |  |  |
| Phone: | Global phone number: +44 1249 661808 Check https://speakup.oxfamnovib.nl for local numbers (you can request interpretation) |  |  |

# ANNEXES

- Oxfam Supplier Code of Conduct: https://oxfam.box.com/v/Oxfam-Supplier-CodeConduct

- Oxfam Non-Staff Code of Conduct: https://oxfam.box.com/v/Nonstaff-CodeConduct

- Conflict of interest declaration form: https://oxfam.box.com/v/Supplier-COI-declaration

- Safeguarding policy

- (If applicable) Oxfam child safeguarding policy

- (Edit if applicable) Example privacy notice: https://oxfam.box.com/s/mo8artt9l8a2x0cnpqrqqrugt8k0r773

Non-Staff Code of Conduct applies for any self-employed individuals or contracted employees of suppliers who are working on Oxfam sites, or who have access to Oxfam materials, or who may represent Oxfam in any manner but are not part of Oxfam’s legal entity)