JAMHUURIYADDA FEDERAALKA SOOMAALIYA

WASAARADDA BEERAHA & WARAABKA

جـمـهــو رية الصـومـال الفيدراليه

وزارة الزراعه والري

Federal Republic of Somalia

Ministry of Agriculture & Irrigation

Rural Livelihoods Resilience Program (RLRP)

Expression of Interest

(By the consulting firm in response to the REOI issued by the procuring entity)

For

CSA Innovation and Biofortified Crop Demo Plots

Ref No: SOM-2000004325-0169-CS-CQS

Issue Date: 16/07/2026

Instructions to Consultants

Assignment Title: CSA Innovation and Biofortified Crop Demo Plots

Ref No: SOM-2000004325-0169-CS-CQS

The Ministry of Agriculture and Irrigation of Federal Government of Somalia has received financing from the International Fund for Agricultural Development (IFAD) towards the cost of Rural Livelihoods Resilience Program (RLRP) and intends to apply part of the proceeds for the recruitment of consulting services.

The use of any IFAD financing shall be subject to IFAD’s approval, pursuant to the terms and conditions of the financing agreement, as well as IFAD’s rules, policies and procedures. IFAD and its officials, agents and employees shall be held harmless from and against all suits, proceedings, claims, demands, losses and liability of any kind or nature brought by any party in connection with Rural Livelihoods Resilience Program (RLRP).

The consulting services (the "Services") comprise Climate-Smart Agriculture (CSA) research, on-farm field trials, knowledge product development, training of trainers, validation and knowledge-sharing activities, and establishment of biofortified crop demonstration plots.

This request for expressions of interest (REOI) follows the general procurement notice that appeared on the IFAD website on November 2nd, 2024, on UNDB on November 2nd, 2024 and on the ministry of agriculture and irrigation’s Website on November 2nd, 2024.

The Ministry of Agriculture and Irrigation of Federal Government of Somalia (“the client”) now invites eligible consulting firms (“consultants”) to indicate their interest in providing the services. Interested consultants should provide information demonstrating that they have the required qualifications and relevant experience to perform the services. Interested firms should fill the template for expressions of interest and submit found at https://somalijobs.com/ and send it to the address indicated below.

The attention of interested consultants is drawn to IFAD’s Anti-Money Laundering and Countering the Financing of Terrorism Policy and the Revised IFAD Policy on Preventing Fraud and Corruption its Activities and Operations. The latter sets forth IFAD’s provisions on prohibited practices. IFAD further strives to ensure a safe working environment free of harassment, including sexual harassment, and free of sexual exploitation and abuse (SEA) in its activities and operations as detailed in its IFAD Policy to Preventing and Responding to Sexual Harassment, Sexual Exploitation and Abuse. By entering in this document, you certify to have read, understood, and agreed to be bound by the Privacy Policy of IFAD.

The consultant shall not have any actual, potential or reasonably perceived conflict of interest. A consultant with an actual, potential or reasonably perceived conflict of interest shall be disqualified unless otherwise explicitly approved by the Fund. A consultant including their respective personnel and affiliates are considered to have a conflict of interest if they a) have a relationship that provides them with undue or undisclosed information about or influence over the selection process and the execution of the contract, b) participate in more than one EOI under this procurement action, c) have a business or family relationship with a member of the Purchaser’s board of directors or its personnel, the Fund or its personnel, or any other individual that was, has been or might reasonably be directly or indirectly involved in any part of (i) the preparation of this REOI, (ii) the shortlisting or selection process for this procurement, or (iii) execution of the contract. The consultant has an ongoing obligation to disclose any situation of actual, potential or reasonably perceived conflict of interest during preparation of the EOI, the selection process or the contract execution. Failure to properly disclose any of said situations may lead to appropriate actions, including the disqualification of the consultant, the termination of the contract and any other as appropriate under the IFAD Policy on Preventing Fraud and Corruption in its Projects and Operations.

The following conflict of interest rules shall apply with respect to recruitment of government/client staff within the consultant’s proposed team:

(a)	No member of the client’s board of directors or current employees of the client (whether part time, or full time, paid or unpaid, in leave status, etc.) shall be proposed or work as, or on behalf of, any consultant.

(b)	No current employees of the government shall work as consultants or as personnel under their own ministries, departments or agencies.

(c)	Recruiting former client or government employees to perform services for their former ministries, departments or agencies is acceptable provided no conflict of interest exists.

(d)	If a consultant proposes any government employee as personnel in their technical proposal, such personnel must have written certification from the government confirming that: (i) they will be on leave without pay from the time of their official proposal submission and will remain on leave without pay until the end of their assignment with the consultant and they are allowed to work full-time outside of their previous official position; or (ii) they will resign or retire from government employment on or prior to the contract award date. Under no circumstances shall any individuals described in (i) and (ii) be responsible for approving the implementation of this contract. Such certification shall be provided to the client by the consultant as part of its technical proposal.

(e)    In the case where a consultant seeks to engage the services of any person, who may have left the client within a period of less than twelve (12) months of the date of this RFP, it must obtain a written “no-objection” from the client for the inclusion of such a person, prior to the consultant’s submission of its proposal.

A consultant will be selected in accordance with the based on Consultant Qualifications Selection (CQS) set out in IFAD’ project procurement handbook that can be accessed via the IFAD website at www.ifad.org/project-procurement. The client will evaluate the EOIs using the criteria provided in Annex 2. The shortlisted consultant(s) will be provided with the detailed TORs and asked to submit a detailed technical and financial offer. The evaluation will include a review and verification of qualifications and past performance, including a reference check, prior to the contract award.

Consultants may associate with other firms to enhance their qualifications but should indicate clearly whether the association is in the form of a joint venture and/or a sub-consultancy. In the case of a joint venture, all the partners in the joint venture shall be jointly and severally liable for the entire contract, if selected.

The shortlisting criteria are

| Item | Criteria | Points |
| --- | --- | --- |
| i | Minimum five (5) years of professional experience in agricultural research or crop agronomy or climate-smart agriculture (CSA) or resilience programming, and Farmer Field School (FFS) methodologies. | 30 |
| ii | Proven experience in designing and implementing on-farm field trials and adaptive research in dryland, semi-arid, or climate-vulnerable agricultural systems. | 25 |
| iii | Proven experience working in Somalia or similar fragile and conflict-affected contexts, including engagement with government institutions, rural communities, and agricultural value chains. | 25 |
| IV | Strong expertise in data analysis, training, and social inclusion, including statistical analysis of agronomic trial data, development of farmer training materials, and integration of gender and youth-responsive approaches. | 20 |
|  | Total Points | 100 |
|  | Minimum points required to pass | 70 points |

Any request for clarification on this REOI should be sent via e-mail to the address below no later than 10:00 AM 23/07/2026 Somalia local time. The client will provide responses to all clarification requests by 12:00 PM 25/07/2026 Somalia local time.

Expressions of Interest, along with all supporting and requested documents (to demonstrate experience in line with the criteria outlined above), must be submitted in written form using the designated forms provided for this purpose.

EOIs shall be submitted to the address below no later than 11:00 AM 31/07/2026 Somalia local time.

Expressions of Interest that will be delivered via email the packages should be clearly marked: REF: SOM-2000004325-0169-CS-CQS: CSA Innovation and Biofortified Crop Demo Plots to: Consultants must submit all documents in PDF format, compressed into a single password-protected ZIP or RAR file. password should be sent no later than 12:00 PM 31/07/2026 Somalia local time in a separate email to aabyan@rlrp.gov.so  and cc: amuhumad@rlrp.gov.so Submissions received after the deadline or without secure password transmission will be deemed non-compliant and rejected.

# Form EOI-1

# EOI Submission Form

To: Rural Livelihoods Resilience Program (RLRP)

Ministry of Agriculture and Irrigation MOAI

Federal Government of Somalia

Re: CSA Innovation and Biofortified Crop Demo Plots

Ref No: SOM-2000004325-0169-CS-CQS

We, the undersigned, declare that:

- We are expressing our interest in providing the consulting services for the above-mentioned assignment and have no reservations to the REOI, the instructions to the consultants and any addenda thereto.

- Our expression of interest is open for acceptance for a period of ninety (90) days.

- Our firm, its associates, including any subcontractors or suppliers for any part of the contract, have not been declared ineligible by the Fund and have not been subject to sanctions or debarments under the laws or official regulations of the client’s country or not been subject to a debarment recognized under the Agreement for Mutual Enforcement of Debarment Decisions (the "Cross-Debarment Agreement"), beyond those declared in paragraph 9 of this EOI submission form.

- We acknowledge and accept the IFAD Revised Policy on Preventing Fraud and Corruption in its Activities and Operations. We certify that neither our firm nor any person acting for us or on our behalf has engaged in any prohibited practices as provided in ITC Clause 6. Further, we acknowledge and understand our obligation to report to anticorruption@ifad.org any allegation of prohibited practice that comes to our attention during the selection process or the contract execution.

- No attempt has been made or will be made by us to induce any other consultant to submit or not to submit an EOI for the purpose of restricting competition.

- We acknowledge and accept the IFAD Policy on Preventing and Responding to Sexual Harassment, Sexual Exploitation and Abuse. We certify that neither our firm nor any person acting for us or on our behalf has engaged in any sexual harassment, sexual exploitation or abuse. Further, we acknowledge and understand our obligation to report to ethicsoffice@ifad.org any allegation of sexual harassment, sexual exploitation and abuse that comes to our attention during the selection process or the contract execution.

- The following commissions, gratuities, or fees have been paid or are to be paid with respect to the selection process: [Insert complete name of each recipient, its full address, the reason for which each commission or gratuity was paid and the amount and currency of each such commission or gratuity.]

| Name of Recipient | Address | Reason | Amount | Currency |
| --- | --- | --- | --- | --- |

(If none has been paid or is to be paid, indicate “none.”)

- We declare that neither our consulting firm nor any of its directors, partners, proprietors, key personnel, agents, sub-consultants, sub-contractors, consortium and joint venture partners have any actual, potential or perceived conflict of interest as defined in ITC Clause 5 regarding this selection process or the execution of the contract. [insert if needed: “other than the following:” and provide a detailed account of the actual, potential or perceived conflict]. We understand that we have an ongoing disclosure obligation on such actual, potential or perceived conflicts of interest and shall promptly inform the client and the Fund, should any such actual, potential or perceived conflicts of interest arise at any stage of the procurement process or contract execution.

- The following criminal convictions, administrative sanctions (including debarments) and/or temporary suspensions have been imposed on our consulting firm and/or any of its directors, partners, proprietors, key personnel, agents, sub-consultants, sub-contractors, consortium and joint venture partners:

| Nature of the measure (i.e., criminal conviction, administrative sanction or temporary suspension) | Imposed by | Name of party convicted, sanctioned or suspended (and relationship to the consultant) | Grounds for the measure (i.e., fraud in procurement or corruption in contract execution) | Date and time (duration) of measure |
| --- | --- | --- | --- | --- |

If no criminal convictions, administrative sanctions or temporary suspensions have been imposed, indicate “none”.

- We acknowledge and understand that we shall promptly inform the client about any material change regarding the information provided in this EOI submission form.

- We further understand that the failure to properly disclose any of information in connection with this EOI submission form may lead to appropriate actions, including our disqualification as consultant, the termination of the contract and any other as appropriate under the IFAD Policy on Preventing Fraud and Corruption in its Projects and Operations.

- We understand that you are not bound to accept any EOI that you may receive.

| [Authorized signatory] |  |
| --- | --- |
| [Name and title of signatory] |  |
| [Name and address of firm] |  |

## Form EOI-2 
Organization of the Consultant

Re: CSA Innovation and Biofortified Crop Demo Plots

Ref No: SOM-2000004325-0169-CS-CQS

[Provide a brief description of the background and organization of your firm/entity and of each associated firm for this assignment. Include the organization chart of your firm/entity. The EOI must demonstrate that the consultant has the organizational capability and to carry out the assignment. The qualifications document shall further demonstrate that the consultant has the capacity to field and provide experienced replacement personnel on short notice. Key staff CVs are not required at the shortlisting stage.]

| Name of the firm |  |
| --- | --- |
| Date of establishment |  |
| Country of registration |  |
| Full address of the firm |  |
| Focal point: name, position, contact information (telephone, email): | Name: |
|  | Tel: |
|  | Email: |
| Number of branches in the country |  |
| Country(ies) of operations with number of branches in each country |  |
| Number of full-time employees |  |
| Number of part-time employees |  |
| Field(s)of expertise of the firm |  |
| Number of professional staff with experience related directly to the assignment |  |
| Subsidiary and associated companies (wherever applicable): (details in the following format to be provided for all associates) – - Name of the company - Nature of business - Address of the company - Website of the company - Brief description of company (maximum of 120 words) |  |
| Any other information that the consultant would like to add: |  |

Maximum 10 pages

## Form EOI-3

## Experience of the Consultant

Re: CSA Innovation and Biofortified Crop Demo Plots

Ref No: SOM-2000004325-0169-CS-CQS

[Using the format below, provide information on each relevant assignment for which your firm, and each associate for this assignment, was legally contracted either individually as a corporate entity or as one of the major companies within an association, for carrying out consulting services similar to the ones requested under the preliminary terms of reference included in this EOI. The EOI must demonstrate that the consultant has a proven track record of successful experience in executing projects similar in substance, complexity, value, duration, and volume of services sought in this procurement.

Maximum 20 pages]

| Assignment name: | Approx. value of the contract (in current US$): |
| --- | --- |
| Country: Location within country: | Duration of assignment (months): |
| Name of client: | Total No. of staff-months of the assignment: |
| Address, and contact details (including email address(es)): | Approx. value of the services provided by your firm under the contract (in current US$): |
| Start date (month/year): Completion date (month/year): | No. of professional staff-months provided by associated consultants: |
| Name of associated consultants, if any: | Name of proposed senior professional staff of your firm involved and functions performed (indicate most significant profiles such as project director/coordinator, team leader): |
| Narrative description of project: |  |
| Description of actual services provided by your staff within the assignment: |  |

Name of Firm: _________________________________

ANNEX 1

Terms of Reference for Consulting Services

For

CSA Innovation and Biofortified Crop Demo Plots

Ref No: SOM-2000004325-0169-CS-CQS

Submission date: 16/07/2026

1. Background

Somalia, situated in the Horn of Africa, is highly susceptible to the adverse impacts of climate change. The nation experiences recurrent and severe climate-related disasters, including prolonged droughts, devastating floods, and extreme temperature variations. These events have far-reaching consequences, affecting agricultural productivity, water availability, food security, and the overall livelihoods of millions of Somalis. Given the country's dependency on natural resources, the effects of climate change exacerbate existing vulnerabilities, making it imperative to build resilience across all sectors.

Somalia’s agriculture sector faces extreme climate vulnerability, recurrent droughts, water scarcity, degraded soils, weak input systems, and limited extension capacity. While CSA practices are increasingly recognized as essential for resilience, adoption remains uneven due to structural barriers such as limited finance, weak seed systems, labour constraints, and inadequate water infrastructure. The RLRP aims to strengthen household and community resilience by scaling feasible, context appropriate CSA innovations that reduce climate risks, improve productivity, and enhance livelihoods.

The CSA Rapid Assessment conducted under the RLRP provides a comprehensive, evidence-based analysis of agricultural and livestock systems across Kismayo, Bardhere, Baidoa, Afgoye, and Elbarde districts in Somalia, where recurrent climate shocks, fragile institutions, and limited access to inputs, services, and markets continue to constrain productivity and resilience.

This research consultancy will utilize existing FFS platforms for field trials, demonstrations, and training activities.

The consultancy has two complementary parts:

- Part A: Comprehensive CSA research, on-farm field trials, knowledge product development, and training of trainers (ToT) covering a wide range of climate-smart practices across all five target districts.

- Part B (Simple Demonstration Only): RLRP will partner with public and private research institutions to introduce biofortified sorghum, biofortified sweetpotato, and hybrid maize in irrigated areas through simple demo plots only – no research trials, no complex tasks, no training delivery.

2. The Rural Livelihoods Resilience Programme

Rural Livelihoods Resilience Program is an 8-year program (March 2024 – March 2032). RLRP's development objective is to sustainably increase productivity, incomes and nutrition security and enhance resilience of rural smallholder families in Somalia.

This research consultancy directly supports RLRP's objective to sustainably increase productivity and resilience by building institutional capacity for CSA scaling across all five target districts.

3. Overall Objective of the Assignment

The overall objective of this research consultancy is to strengthen the institutional and technical capacity of the Ministry of Agriculture and Irrigation (MoAI), the Ministry of Livestock, Forestry and Range (MoLFR), and RLRP implementation teams to plan, deliver, and scale Climate Smart Agriculture (CSA) interventions across targeted agro ecological zones.

Part A Objectives (Core CSA):

- Develop and deliver a comprehensive Training of Trainers (ToT) curriculum and knowledge products.

- Produce a complete suite of CSA knowledge products (training modules, manuals, demonstration protocols, assessment tools).

- Design and implement on-farm field trials for key climate-resilient crops using existing Farmer Field Schools (FFS).

- Identify and prioritize feasible CSA innovations for crops, livestock, water management, soil fertility, and natural resource management.

- Strengthen institutional systems for CSA scaling.

- Provide technical backstopping and quality assurance for field level training.

- Support validation, knowledge sharing, and demonstration activities.

Part B Objectives:

- Establish public-private research partnerships for germplasm supply.

- Demonstrate (simple demo plots only) biofortified sorghum, biofortified sweet potato, and hybrid maize in irrigated areas.

- Produce a brief partnership sustainability plan.

4. Scope of Work

PART A: Core CSA Research, Field Trials, Knowledge Products & Training

The Consulting Firm will undertake the following research, knowledge generation, and on-farm validation tasks.

4.1 Knowledge Product Development

The Firm will lead the development of a complete suite of CSA training and learning materials tailored to Somalia's agro ecological zones and institutional needs.

Key Tasks

- Review existing CSA literature, the CSA Rapid Assessment findings, MoAI extension materials, and existing RLRP FFS curricula.

- Develop CSA training modules, tools, and innovation packages aligned with global CSA standards and Somalia's national policies (NDC, NAP, National Agriculture Development Framework).

- Prepare facilitator guides, participant manuals, demonstration protocols, and assessment tools for MoAI, MoLFR, and RLRP field teams for use within existing FFS.

- Prioritize feasible CSA innovations for each agro ecological zone, covering crops, livestock, water management (rainfed and riverine), soil fertility, and natural resource management.

- Prepare practical demonstration protocols and field techniques to guide trainers in using existing FFS platforms.

- Field-test draft materials with at least 5 extension staff per district before finalization.

Knowledge Products to be Delivered (Part A)

- CSA training manuals and facilitator guides (Somali language with English versions; visual aids for low-literacy users) – designed for FFS use

- Demonstration protocols and field implementation tools for FFS

- CSA assessment and monitoring tools

- Extension materials and district specific guidance notes for FFS facilitators

- Field trial protocols and data collection tools for integration into existing FFS

4.2 Design and Implementation of Field Trials for Key Crops Using Existing FFS

The Firm shall design and oversee on-farm field trials for key climate-resilient crops conducted through existing Farmer Field Schools (FFS) in each of the five target districts. No new FFS will be established.

4.2.1 Existing FFS Inventory

At inception, the firm shall:

- Map existing FFS in each target district (number, location, membership composition, crops currently used)

- Select FFS for trial participation based on criteria (e.g., active membership, representative agro-ecology, presence of both men and women members)

- Document FFS facilitator names and contact details for coordination

4.2.2 Crop Selection

Based on the CSA Rapid Assessment and consultation with MoAI and FFS facilitators, the firm shall select 3–4 key crops per district for field trials. Indicative crops by district:

| District | Agro-ecological Zone | Indicative Key Crops for Trials |
| --- | --- | --- |
| Baidoa | Agropastoral (Bay region) | Sorghum, cowpea, sesame, maize (drought-tolerant varieties) |
| Kismayo | Coastal/irrigated (Jubaland) | Maize, sesame, cowpea, vegetables (tomato, onion) |
| Bardhere | Riverine (Jubaland) | Maize, sorghum, cowpea, sesame |
| Afgoye | Riverine/flood-prone (Lower Shabelle) | Maize, sorghum, cowpea, vegetables (flood-tolerant varieties) |
| Elbarde | Pastoral/agropastoral (Bakool) | Sorghum, cowpea, millet, fodder crops |

4.2.3 CSA Practices to Be Tested

For each crop, the firm shall design trials comparing:

| Treatment | Description |
| --- | --- |
| Control (farmer practice) | Existing farmer practices within FFS plot (no additional CSA intervention) |
| Treatment 1 | Improved drought-tolerant variety only |
| Treatment 2 | Improved variety + water harvesting (e.g., tie ridges, planting basins, small-scale irrigation) |
| Treatment 3 | Improved variety + water harvesting + soil fertility management (compost, manure, micro-dosing of fertilizer) |
| Treatment 4 (optional) | Improved variety + water harvesting + soil fertility + integrated pest management |

4.2.4 Trial Design and Methodology

- Number of trial plots: Minimum 3 FFS per district, with each FFS implementing all treatments on separate plots within the FFS demonstration site

- Plot size: Minimum 10m x 10m (100 sqm) per treatment per FFS

- FFS member involvement: FFS members (both women and men) shall participate in planting, monitoring, and data collection as part of FFS learning activities

- Duration: One full growing season (Gu or Deyr rains, depending on timing of assignment)

- Data to be collected (by FFS members with firm oversight):

  - Germination rate

  - Plant height and growth stages

  - Days to maturity

  - Yield (kg per plot, extrapolated to kg/ha)

  - Water use / irrigation frequency

  - Pest and disease incidence

  - Input costs (seeds, fertilizer, labour)

  - Farmer preference and acceptability (end-of-trial survey using FFS group discussion)

- Data collection frequency: Weekly during growing season (integrated into regular FFS meeting schedule); final harvest assessment

4.2.5 Trial Management Roles (Part A)

| Responsibility | Research Consultant | RLRP | MoAI | FFS Facilitators |
| --- | --- | --- | --- | --- |
| Provide trial protocols and data tools | Lead | Review | Approve | Receive |
| Train FFS facilitators on trial setup and data collection | Lead | Coordinate | Co-train | Receive training |
| Select FFS for trial participation | Advise on criteria | Lead | Support | N/A |
| Procure trial inputs (seeds, tools, etc.) | Provide specifications | Yes | Support | N/A |
| Establish trial plots within existing FFS | Oversee | Support | Support | Lead (with members) |
| Conduct weekly data collection | Oversee quality | Support | Support | Lead (with members) |
| Conduct site visits at key growth stages | Lead | Accompany | Accompany | Participate |
| Analyze trial data | Lead | Support | Support | N/A |
| Facilitate end-of-trial FFS learning sessions | Lead | Organize | Co-facilitate | Lead |

4.2.6 FFS-Based Participatory Evaluation

At the end of the growing season, the firm shall facilitate special FFS learning sessions at each trial site where:

- FFS members compare treatments side-by-side within their existing FFS plot

- Members rank practices by preference (yield, labour, input cost, taste, marketability)

- Women and men provide separate rankings (using separate small group discussions within the FFS)

- Selected practices are identified for scaling through the FFS

4.3 Design and Development of CSA Packages (Informed by Field Trials)

The Firm will design district specific CSA innovation packages and adoption enabler packages informed by field trial results and designed for integration into existing FFS curricula.

Key Tasks

- Develop district specific CSA innovation packages, including:

  - Drought tolerant crops (with evidence from FFS trials)

  - Fodder production and dry season feeding

  - Water harvesting and small scale irrigation

  - Integrated Pest Management (IPM)

  - Soil fertility and conservation practices

  - Improved animal health and nutrition

  - Post harvest handling and storage

- Using the barrier analysis already completed in the CSA Rapid Assessment, the firm shall develop solution-oriented adoption enabler packages directly informed by FFS trial evidence.

- Propose a CSA sequencing model for FFS integration.

- For each of the five districts, produce a one-page district profile showing agro-ecological conditions, current CSA adoption levels, FFS trial results summary, and priority practices with evidence.

- Recommend FFS-based inclusive CSA delivery models targeting women, youth, IDPs, and persons with disabilities.

- Propose district level coordination platforms for CSA scaling and knowledge exchange among FFS facilitators.

4.4 Training of Trainers (ToT) Curriculum Design (Informed by FFS Field Trials)

The Firm will design a comprehensive ToT curriculum and provide technical oversight for its delivery. The curriculum shall integrate FFS field trial findings as core learning content and be designed for FFS facilitators.

Key Tasks

- Develop a 5-day ToT curriculum (see outline below) with detailed session plans, facilitator notes, and participant materials.

- Incorporate FFS trial results into training modules (e.g., "Evidence from Baidoa FFS: Which sorghum variety performed best?")

- Develop pre-test and post-test assessment tools to measure learning gain.

- Provide master trainers to deliver the ToT sessions in Baidoa and Kismayo (2 master trainers per location).

- Provide quality assurance and technical backstopping during ToT delivery.

- Produce a ToT Training Report analyzing participant performance and recommending improvements for FFS integration.

ToT Curriculum Outline (5 days) – Designed for FFS Facilitators

| Day | Topic | Key Input from FFS Field Trials |
| --- | --- | --- |
| 1 | CSA fundamentals + using FFS for CSA learning | Overview of FFS trial design and purpose |
| 2 | Water harvesting + small-scale irrigation + FFS trial results on water use | District-specific water use data from FFS trials |
| 3 | Soil fertility + drought tolerant crops + fodder + FFS yield results | Yield comparisons by treatment per district from FFS |
| 4 | Livestock health + dry season feeding + IPM | Pest/disease observations from FFS trials |
| 5 | FFS facilitation methods + using trial evidence in FFS sessions + action planning | How to present FFS trial results to FFS members |

ToT Participants
ToT participants will be drawn from all five RLRP target districts, specifically:

- FFS Facilitators (MoAI extension staff and RLRP field staff who currently run existing FFS)

- RLRP technical staff

- MoAI district officers

| ToT Venue | Participants From | Number |
| --- | --- | --- |
| Baidoa | Baidoa, Afgoye, Elbarde (FFS facilitators from these districts) | 12 |
| Kismayo | Kismayo, Bardhere (FFS facilitators from these districts) | 8 |
| Total |  | 20 |

4.5 Validation and Knowledge Sharing (Informed by FFS Field Trials)

The Firm shall facilitate validation workshops BEFORE finalizing ToT modules, where FFS field trial results are presented to stakeholders.

Key Tasks

- Facilitate validation workshops with MoAI, FMS authorities, FFS facilitator representatives, NGOs, and private sector actors.

- Present preliminary FFS trial results at validation workshops for stakeholder feedback.

- Validation workshops shall include: MoAI district officers, MoLFR representatives, at least 2 FFS facilitators per district, 2 NGO partners, 2 private sector actors.

- Produce user friendly CSA extension materials and district specific guidance notes designed for FFS facilitators.

- Ensure alignment with global CSA standards and Somalia's national priorities.

PART B: Biofortified Sorghum, Biofortified Sweetpotato & Hybrid Maize – Simple Demonstration Only in Irrigated Areas

Part B is strictly limited to simple demonstration. No research trials, no complex data collection, no training delivery, and minimal tasks.

4.6 Simple Demonstration Activities (Part B Only)

The Firm will carry out the following simple demonstration tasks in irrigated areas using existing FFS platforms:

| # | Task | Description |
| --- | --- | --- |
| 1 | Establish partnerships | Facilitate MoUs with public research institutions and private seed companies for germplasm supply (one-time engagement) |
| 2 | Source germplasm | Obtain biofortified sorghum seed, biofortified sweetpotato vines, and hybrid maize seed for demo plots |
| 3 | Select irrigated FFS | Identify minimum 3 existing FFS per district with access to irrigation (riverine, pump, gravity, solar) |
| 4 | Plant demo plots | Establish one demo plot per crop per FFS (3 demo plots per FFS). No treatments, no controls, no replication. |
| 5 | Observe crops | FFS facilitators make simple visual observations (crop looks good / moderate / poor). No measurements. |
| 6 | Collect farmer feedback | At end of season, hold one discussion per FFS to ask: "Did you like this crop? Would you grow it?" |
| 7 | Write brief sustainability plan | Produce 2–3-page plan for post-project seed/vine multiplication and partnership handover to MoAI |

What Part B does NOT include:

- No research trials or treatment comparisons

- No formal data collection sheets

- No training of any kind (ToT, facilitator training, farmer training)

4.7 Demo Plot Specifications

| Element | Specification |
| --- | --- |
| Plot type | Single demonstration plot per crop (no control) |
| Crops | Biofortified sorghum, biofortified sweetpotato, hybrid maize |
| Plot size | Sorghum/maize: 10m x 10m (100 sqm); Sweetpotato: 5m x 10m (50 sqm) |
| Water source | Irrigated only (riverine, pump, gravity, solar) |
| Management | Farmer's current practice (no experimental interventions) |
| Number of FFS | Minimum 3 per district |
| Total demo plots | 3 FFS × 3 crops × 5 districts = 45 demo plots |

4.8 Simple Observation (No Formal Data)

| What to note | How |
| --- | --- |
| Crop establishment | Did it grow? (yes/no) |
| General vigor | Good / Moderate / Poor |
| Pests or diseases seen? | Yes/No (list if yes) |
| Farmer interest | Would you grow this again? (show of hands) |
| Taste test (informal) | Verbal feedback only |
| Yield | Harvest per unit area |

4.9 Roles

| Responsibility | Research Consultant | RLRP | Partners | MoAI | FFS Facilitators |
| --- | --- | --- | --- | --- | --- |
| Facilitate MoUs | Lead | Lead negotiation | Sign | Co-sign | N/A |
| Source germplasm | Coordinate | Support | Supply | Approve | N/A |
| Select irrigated FFS | Advise | Lead | N/A | Support | Provide info |
| Plant demo plots | Oversee | Support | N/A | Support | Lead |
| Simple observations | None (FFS does it) | None | None | None | Lead (verbal/visual) |
| Farmer feedback discussion | Facilitate (1 per FFS) | Organize | Optional | Optional | Lead |
| Write sustainability plan | Lead | Review | Input | Input | N/A |

5. Duration and Schedule

The assignment will be implemented over 130 days.

| Phase | Activities | Timeline |
| --- | --- | --- |
| Phase 1: Setup | Inception Report, FFS mapping, trial protocols, training, Part B: MoUs, germplasm sourcing, demo site selection | Days 1–15 |
| Phase 2: Establishment | Trial planting, Part B: demo plot planting | Days 16–30 |
| Phase 3: Monitoring | Weekly data collection, site visits, Part B: simple visual observations | Days 31–80 |
| Phase 4: Harvest | Harvest, analysis, FFS learning sessions, Part B: farmer feedback discussions | Days 80–90 |
| Phase 5: Knowledge Products | Draft materials, validation workshops, final packages, Part B: sustainability plan | Days 90–105 |
| Phase 6: ToT Delivery | ToT sessions (Part A only) | Days 105–115 |
| Phase 7: Finalization | Final reports, adoption framework | Days 115–130 |

6. Required Qualifications

The selected firm shall possess the following qualifications:

- Minimum five (5) years of professional experience in agricultural research or crop agronomy or, climate-smart agriculture (CSA) or resilience programming, and Farmer Field School (FFS) methodologies.

- Proven experience in designing and implementing on-farm field trials and adaptive research in dryland, semi-arid, or climate-vulnerable agricultural systems.

- Proven experience working in Somalia or similar fragile and conflict-affected contexts, including engagement with government institutions, rural communities, and agricultural value chains.

- Strong expertise in data analysis, training, and social inclusion, including statistical analysis of agronomic trial data, development of farmer training materials, and integration of gender and youth-responsive approaches.

7. Key Personnel

#### 1. Team Leader / Climate-Smart Agriculture (CSA) Specialist (Key Expert 1)

Qualifications and Experience

- Bachelor degree in in Agronomy, Climate-Smart Agriculture, Agricultural Sciences, Rural Development, or related field.

- Minimum 7 years of experience in agricultural research or CSA programming or, resilience building, and rural development

Responsibilities

- Lead overall assignment implementation and quality assurance.

- Supervise field trials, knowledge product development, and validation processes.

- Coordinate with MoAI, MoLFR, RLRP, and partners.

- Lead preparation of inception, interim, and final reports.

#### 2. Agronomist and Field Trial Specialist (Key Expert 2)

Qualifications and Experience

- Bachelor degree in Agronomy, Crop Science, Agricultural Research, or related field.

- Minimum 5 years of experience in crop production, varietal evaluation, and on-farm trials.

Responsibilities

- Design and oversee field trials across the five districts.

- Develop trial protocols and monitoring tools.

- Supervise field data collection and field visits.

- Support analysis of agronomic performance and trial results.

#### 3. Training, Extension and FFS Specialist (Key Expert 3)

Qualifications and Experience

- Bachelor degree in Agricultural Extension, Rural Development, Education, or related field.

- Minimum 5 years of experience in FFS implementation, adult learning, and curriculum development.

Responsibilities

- Develop CSA training manuals, facilitator guides, and extension materials.

- Design the ToT curriculum and assessment tools.

- Lead ToT delivery and capacity-building activities.

- Support validation workshops and knowledge-sharing events.

#### 4. Monitoring, Evaluation and Data Analysis Specialist (Key Expert 4)

Qualifications and Experience

- Bachelor degree in Agricultural Economics, Statistics, Biostatistics, M&E, or related field.

- Minimum 5 years of experience in agricultural data analysis and impact assessment.

Responsibilities

- Develop data collection templates and quality assurance procedures.

- Analyze field trial data and farmer feedback.

- Support preparation of district trial reports and adoption framework.

- Contribute to final reporting and evidence generation.

#### 5. Gender and Social Inclusion Specialist (Key Expert 5)

Qualifications and Experience

- Bachelor degree in Gender Studies, Social Sciences, Rural Development, or related field.

- Minimum 5 years of experience in gender mainstreaming and social inclusion.

Responsibilities

- Ensure gender-responsive trial implementation and participatory evaluations.

- Support inclusion of women, youth, IDPs, and persons with disabilities.

- Review training materials and knowledge products from a gender perspective.

- Contribute to gender and inclusion recommendations for CSA scaling.

8. Deliverables

| Deliverable | Description | Part A Content | Part B Content |
| --- | --- | --- | --- |
| Deliverable 1 | Inception Report | Work plan, FFS mapping, trial protocols | List of MoUs, demo sites, germplasm sourced |
| Deliverable 2 | Draft CSA Knowledge Product Package | Manuals, guides, protocols | None |
| Deliverable 3 | Trial Protocols & Data Tools | Full trial protocols | Simple 1-page observation template (optional) |
| Deliverable 4 | Interim Progress Report | Mid-season trial data | Brief note on demo planting |
| Deliverable 5 | Validation Workshop Report | Stakeholder feedback on trials | Brief mention of demo feedback |
| Deliverable 6 | Final Knowledge Product Package | Revised manuals, guides | None |
| Deliverable 7 | District Trial Reports (5 reports) | Full trial results per district | One paragraph per district on demo observations |
| Deliverable 8 | ToT Curriculum & Training Report | Full curriculum and report | None |
| Deliverable 9 | Adoption Monitoring Framework | Indicators, tools, tracking plan | None |
| Deliverable 10 | Final Consolidated Report | Complete summary | Short annex (2-3 pages) on demo and partnerships |
| Deliverable 11 (NEW) | Partnership Sustainability Plan | None | 2-3 page plan: seed/vine multiplication, handover to MoAI |

Reporting and Coordination

The consultant shall report to the National Program Coordinator and work closely with RLRP State Coordinators and District Officers.

The SP will be responsible for providing their own office space, transport, equipment, and training materials and logistics. This includes, meeting venues in the communities, notebooks, pens, flipcharts and marker pens for the group work.

They will be expected to deploy a technically competent team with the required expertise and ensure that all tools, software, and resources for data collection, analysis, and reporting are available. It is expected that the SP already possesses this equipment and software and therefore it should not be included in the proposal cost.

Payment Schedule

Payment shall be issued only after the assignment has been completed and the deliverables have been reviewed and accepted by the RLRP Coordinator.

ANNEX 2

Qualification and Evaluation Criteria

| Item | Criteria | Points |
| --- | --- | --- |
| i | Minimum five (5) years of professional experience in agricultural research, or crop agronomy, or climate-smart agriculture (CSA), or resilience programming, and Farmer Field School (FFS) methodologies. | 30 |
| ii | Proven experience in designing and implementing on-farm field trials and adaptive research in dryland, semi-arid, or climate-vulnerable agricultural systems. | 25 |
| iii | Proven experience working in Somalia or similar fragile and conflict-affected contexts, including engagement with government institutions, rural communities, and agricultural value chains. | 25 |
| IV | Strong expertise in data analysis, training, and social inclusion, including statistical analysis of agronomic trial data, development of farmer training materials, and integration of gender and youth-responsive approaches. | 20 |
|  | Total Points | 100 |
|  | Minimum points required to pass | 70 points |

This document refers to legally constituted consulting firms as “consultant”.

The policy is accessible at https://www.ifad.org/en/document-detail/asset/41942012.

The policy is accessible at www.ifad.org/anticorruption_policy.

The policy is accessible at https://www.ifad.org/en/document-detail/asset/40738506.

The policy is accessible at https://www.ifad.org/en/privacy.

The Cross-Debarment Agreement was entered into by the World Bank Group, the Inter-American Development Bank, the African Development Bank, the Asian Development Bank and the European Bank for Reconstruction and Development, additional information may be located at: http://crossdebarment.org/.