Request for Proposal

End-line Infant, Young Child Feeding Practice (IYCF) Knowledge, Attitude & Practice (KAP) Survey for Sool, Sanaag, Bari and Lower Juba regions  .

July 2024

RFP DOCUMENT # 36490

RFP Issue Date:  30/06/2024

Proposal submission Deadline: 10/07/2024

CARE USA

151 Ellis Street NE

Atlanta, GA 30303-2440

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of submitted proposal

- To award another type of contract other than that described herein, or to award no contract;

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions, and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.B. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Consultant/Firm Name: |  |
| --- | --- |
| Title/Designation: |  |
| Contact Person |  |
| Telephone & email |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All applications should be sent to som.consultant@care.org latest by Wednesday 10 July 2024 in one email, with separate attachments for the technical and financial proposals in pdf and a Subject line ‘Endline IYCF Feeding Knowledge, Attitude & Practice Survey’.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in proposals must be all-inclusive to include any outsourced or contracted work.  Any proposals which call for outsourcing or contracting work must include a name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

# CARE is implementing integrated Health and Nutrition targeting vulnerable women, children and displaced populations in Sool, Sanaag, Bari and Lower Juba funded through USAID/BHA.  The Nutrition sub sector include  infant and young child feeding(IYCF) interventions that is aimed at improving awareness and behavior of  mothers/caregivers and the general community as well as promotion of best feeding and  care practices at household and community level to support improved nutrition practices for children and women of child bearing age.

# CARE aims to conduct an in-depth Knowledge, Attitudes, and Practices (KAP) survey to monitor changes in MIYCN behavior including exclusive breastfeeding rates for children under six (6) months and appropriate complementary feeding practices for children aged 6 to 24 months in CARE areas of operation. The survey results are expected to help the Organization determine the changes in knowledge, attitudes, and practice since the last KAP in 2021 following interventions through the 36-month BHA-supported Somalia Multi-Sectorial Humanitarian Response Program.

# SCOPE OF WORK.

# The Consultant will be responsible for reviewing existing project documents and reports to get the required information on the indicators. The Consultant will also review previous KAP surveys on IYCF in the same geographical areas to get parameters for sample size calculation, develop a protocol for the planned KAP survey and manage the assessment. This will allow a comprehensive analysis of the progress of the IYCF KAP survey, using both quantitative indicator estimations; program information over the years, and qualitative data to be collected. The KAP will cover key IYCF indicators in line with the Ministry of health and cluster guidelines

# OVERALL OBJECTIVE OF THE ASSESSMENT

# The main objective of this survey is to determine knowledge, attitude, and practice of infant and young child feeding practices in selected districts of Sool and Sanaag regions. The study will also identify feasible implementation strategies in terms of program quality and community involvement to scale up the most effective approach to promote better child feeding practices.

# SPECIFIC OBJECTIVES

# To determine mothers/caretaker’s knowledge and caring practices regarding infant and young child feeding (among children aged 0-23 months) in our project areas.

# To assess number and percentage of infants 0<6 months of age who are exclusively breastfed in the project area

# To assess the consumption of the different types of food for children aged from 6- 23 months and estimate the food diversity within the last 24hours.

# Ascertain level of IYCF integration into other sectors and assess the skill and knowledge capacity of key staff undertaking IYCF interventions

# Identify knowledge gaps, cultural beliefs or behavioral patterns and practices that create barriers to infant and young child feeding and care practices and  design appropriate behavior change communication and provide sustainable recommendations to strengthen the nutrition activities based on the survey findings.

# To ascertain the impact of nutrition activities in relation positive IYCF, hygiene practices and set new baseline for anticipated USAID/BHA funded program in Sool, Sanaag, Bari and Lower Juba.

# STUDY AREA

The survey will be conducted in villages in Badhan, Erigavo, Ceelafweyn, Caynabo, Lascaanod, and Afmadow Districts where CARE implements IMAM/MIYCN interventions.

Study population: Mothers with children aged 0-23 months and under 5 years will be interviewed to estimate the infant and young child feeding practices in all selected villages.

# STUDY METHODOLOGY

The consultant is expected to propose and an appropriate study design involving both quantitative and qualitative data collection entailing beneficiary household survey; Health Facility document reviews, focused group discussions, beneficiary, Key informant and stakeholder interviews. A comparative analysis approach will be used to report on project achievements for selected sub sector indicator values.

Consultant role and responsibilities

- Assume overall responsibility for design and implementation of the KAP, including daily supervision of KAP teams and daily data collection quality assurance.

- Develop and design KAP survey protocol and questionnaires, including sample size estimation, population size, clustering of the villages and validate contextual tools

- Present the KAP Methodology at Nutrition Cluster Assessment and information Management Working Group (AIMWG)  for validation.

- Train the KAP data collection teams and data clerks in data collection standards and use of the tools (including field testing)

- Implement the KAP survey in Sool, and Sanag.

- Be responsible for data cleaning and analysis using appropriate software (i.e. Epi Info, Stata, ENA for SMART, and ODK).

- Prepare a draft KAP survey report for review by CARE Somalia , ensuring that the assessment is comprehensive and includes all relevant indicators

- Prepare and lead a validation workshop (debriefing) for CARE Somalia Team

- Prepare a final report including background, methodology, results, limitations, conclusions, and recommendations incorporating feedback from CARE Somalia staff and other Nutrition stakeholders on the draft report and tools.

CARE’s role and responsibilities

- Facilitate logistic arrangements including travel, accommodation, etc.

- Recruit Enumerators

- Mobilize the target groups for interviews

- Provide input to the inception report, tools and KAP draft report.

# IMPLEMENTATION WORK PLAN

| No | Activity | Number of days per camp |
| --- | --- | --- |
| 1 | Preparation of survey tools, inception report and sharing with CARE and finalization after feedback | 3 days |
| 2 | Presentation to AIM WG and validation of tools | 1 Day |
| 3 | Training of survey enumerators and field testing | 2 days |
| 4 | Data collection (Quantitative and qualitative) | 6 days |
| 5 | Data cleaning and analysis | 2 days |
| 6 | Report Writing | 3 days |
| 7 | Technical review and comments by CARE team | 2 days |
| 9 | Final Report | 2 days |
|  | Total Days | 20 Days |

Deliverables.

- Inception report that includes the design, implementation and supervision    strategy of the KAP survey including data collection tools

- Data Collectors training power point

- First draft KAP survey report including raw data set in Excel spreadsheet/stata do files

- Submit power point presentation of key findings

- Final detailed report with recommendations

Ethical considerations.

The consultant is required to uphold the 7 GDPR (General Data Protection Regulation) principles throughout the study; these include lawfulness, fairness and transparency; purpose limitation; data minimization; accuracy; storage limitation; integrity and confidentiality (security); and accountability.

The consultant should;

- Take all reasonable steps to ensure that the survey is designed and conducted to respect and protect the rights and welfare of the people and communities involved and DO NO HARM principle is adhered to.

- Ensure that the evaluation is accurate and reliable, is conducted in a transparent and impartial manner and contributes to organizational learning and accountability.

- Commit to adhering to CARE’s Safeguarding Policy and Code of Conduct.

All products arising from this evaluation will be owned by CARE Somalia. The evaluators will not be allowed without prior authorization in writing to present any of the analytical results as his or her own to make use of the evaluation results for publication purposes.

# PROFILE OF THE CONSULTING TEAM

The potential consultant/expertise required to meet the following minimum requirements to qualify for the submission of his/her proposal.

- Advanced degree in Nutrition, Public Health, Nursing or related field

- At least five years of work experience at national or international levels in maternal infant and young child feeding and nutrition.

- Sound understanding of the international standards on IYCF-E

- Experience in conducting IYCF-E surveys in Somalia/Somaliland.

- Experience in design and implementation of IYCF-E programs

- Experience in organizing and leading IYCF-E trainings

- Strong communication and training skills

- Experience working in Somalia/Somaliland and understanding of the dynamics

- Experience and knowledge of IYCF data collection, analysis using EPI Info, SPSS and KOBO.

- Fluent Somali language speaking is a pre-requisite

- Submission Information / How to Apply

All applicants must download the attached request for proposals along with ToR and compete accordingly. applicants must meet the minimum requirements described above, and those unable to meet these requirements will not be considered.

Each application package should include the following:

- A technical and financial proposal highlighting their understanding of the ToR and how they propose to respond to the ToR requirements including the evaluation design, tools and technologies in place for them to perform the assignment, implementation plan etc and financial quote.

- Team structure: details of consultant’s capacity and how they structure the evaluation team. This also includes the CVs of key evaluation teams including the lead consultant(s).

- Sample work: at least three (3) samples of similar work (evaluation reports) performed for peer organization in Somalia or in the Horn of Africa region for the last 3 years.

- References: Names and contact details of at least three (3) organizations that has been performed similar work.

NB: Proposed key personnel used for bidding are expected to be the people executing the work of this contract.

Please send completed RFP, technical, financial proposals (professional costs only) and other requirements mentioned above to this email address:  SOM.Consultant@care.org clearly marking the subject line ‘Endline IYCF Feeding Knowledge, Attitude & Practice Survey’. no later than Wednesday 10 July 2024 11:59 PM EAT.

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible | Remarks |
| --- | --- | --- | --- |
| RFP Issued | 30 June 2024 | CARE |  |
| Supplier to notify CARE of intention to participate in bidding | 30 June 2024 - 10 July 2024 | Supplier | Deadlines must be strictly observed. |
| Deadline for submission of clarification questions to CARE | 9 July 2024 | Supplier | Deadlines must be strictly observed. |
| Evaluation of Proposal | 11-13 July 2024 | CARE |  |
| Vendor presentation (if required) | N/A | Supplier |  |
| Finalists selected | 15-July-2024 | CARE | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

- PROJECT REQUIREMENTS

  - Technical Requirements

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Overall Proposal Suitability |  |  |
| 1 | Provide bidders’ approach and methodology for assignment |  |
| 2 | Bidders’ workplan with milestones for the implementation lead times. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Previous Works and Awards |  |  |
| 1 | Provide 3 client experiences referees |  |
| 2 | A sample of recently written report for a similar assignment (at least 3) |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Technical Expertise and Organizational Experience |  |  |
| 1 | Updated CVs for all consultants including relevant work experience and qualifications |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Others |  |  |
| 1 |  |  |

  - VALUE & COST (Financial Requirements)

(Provide below requirements, payment terms, etc., if there’s any)

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery/Implementation Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

# EVALUATION CRITERIA

CARE will evaluate all proposals based on the following criteria.  To ensure consideration for this Request for Proposal, your proposal should be complete and include all of the following criteria:

- Overall Proposal Suitability: proposed solution(s) must meet the scope and needs included herein and be presented in a clear and organized manner

- Previous Work and Awards: Bidders will be evaluated on examples of their work pertaining to the requirement as well as client testimonials and references

- Technical Expertise and Organizational Experience: Bidders must provide descriptions and documentation of staff technical expertise and experience. Bidders should provide updated CVs for all consultants including relevant work experience and qualifications.

- Value and Cost: Bidders will be evaluated on the cost of their solution(s) based on the work to be performed in accordance with the scope of this project Including the detailed breakdown of professional costs including payment terms, quotation period validity, and payment schedule.

CARE will review proposed budgets and pricing after the initial review of the criteria above is done.