Request for Proposal

TERMS OF REFERENCES FOR THE MIDTERM REVIEW OF THE WAXBARASHADU WAA IFTIIN IV (EDUCATION IS LIGHT IV) PROJECT

RFP DOCUMENT # [1355]

RFP Issue Date:  15/02/2024]

Proposal submission Deadline :  [25/02/2024]

CARE USA

151 Ellis Street NE

Atlanta, GA 30303-2440

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of submitted proposal

- To award another type of contract other than that described herein, or to award no contract;

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions, and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.A. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Supplier Name: |  |
| --- | --- |
| Title/Designation: |  |
| Company Name: |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All applications should be sent to som.consultant@care.org latest by Tuesday 25 February 2024 in one email, with separate attachments for the technical and financial proposals in pdf and a Subject line ‘Mid-term Review of Education is Light IV project’.

Any questions about the TOR can be emailed to ahmed.abdullahi@care.org copying CARE Somalia procurement som.consultant@care.org clearly marking the subject line with ‘Question Midterm Review WWI IV’.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in proposals must be all-inclusive to include any outsourced or contracted work.  Any proposals which call for outsourcing or contracting work must include a name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

CARE is issuing this RFP (Request for Proposal) soliciting qualified bidders to submit proposals intended for midterm review of the Waxbarashadu Waa Iftiin IV (Education Is Light IV) project.

This RFP is an invitation to bid, not an offer of contract.  Bidders must submit a response that complies with the minimum requirements contained herein.

# PROJECT OVERVIEW

CARE is seeking a provider to submit proposals intended for the provision of services for mid-term review of Education is Light IV project.

- BACKGROUND INFORMATION

1.1.	About CARE International

CARE is a leading humanitarian organization fighting global poverty and providing lifesaving assistance in emergencies. Its programs go beyond meeting basic needs at the onset of an emergency to helping affected communities recover and rebuild their lives long after the crisis ends. CARE has been assisting communities in Somalia since 1981. CARE works in partnership with the government, international NGOs, civil society, leaders and local authorities in order to bring effective and lasting change to the most vulnerable communities. CARE currently works through three main programs: firstly, the Rural Women program which supports poor, rural women and girls in addressing long term underlying causes of poverty and vulnerability as well as social, cultural, political and economic obstacles towards positive change. We help women and girls improve their economic status, access education and support them to play a greater role in local leadership and conflict resolution. Secondly, the Urban Youth program focuses on job creation and livelihood opportunities for poor youth through interventions such as secondary education, vocational training, small business development and microfinance. Thirdly, the Emergency program provides direct humanitarian relief to victims of drought and conflict in Puntland, Mogadishu, Lower Juba and Galmudug state. This project falls under Urban Youth Program.

The Puntland State of Somalia is in the midst of momentous political, social and economic transformation since its leaders declared the territory an autonomous region in 1998. The region has managed to maintain relative peace and security in recent years, which has enabled it to establish political and administrative institutions, basic social services, an active civil society, and a growing private enterprise community. In addition, much progress has been made in the education sector in the last few years. Despite these improvements, educational provision, participation and completion in Puntland are among the lowest in the world. The Gross Enrolment Rate (GER) for primary and secondary education as per the Ministry of Education and Higher Education (MoE&HE) latest EMIS data stands at 32.1% (Boys:35.26%; Girls:28.8%) and12.2% (Boys:16.1%; Girls:9.1%) respectively.

The major challenges experienced in the education sector still relates to weak institutional and technical capacity leading to poor service delivery as well as limited oversight. Weaknesses are evident in inadequate database for policy formulation, monitoring and performance evaluation; low access to quality, relevant and equitable education exists at all levels as well as limited pedagogical skills and the availability of teachers, especially in rural and nomadic areas.

It is against this backdrop that a consortium comprising of CARE and Save the Children  are implementing three-year EU-funded Waxbarashadu Waa Iftiin IV  (Education is Light IV) project which began on 13 June 2022  and will end on 12 June 2025) to address educational challenges in close coordination, support and guidance of the MoE&HE in the Puntland. State of Somalia. Through this ToR, CARE (lead agency) is planning for a midterm evaluation(13 June 2022 – 12 December 2023) of the 3 year consortium project to ascertain the achievements and implementation levels against the set indicators of the EU funded consortium project.

The Overall objective(impact) of the project is “Improve the educational attainment and the employability of relevant target groups” whilst the specific objective(outcome) is ‘The governance, quality, relevance and inclusiveness of education and training sector are improved’. The project is being implemented in all the 9 regions of Puntland namely Nugaal, Sanag, Hayland, Sool, Ayn, Karkar, Mudug, Bari, and Gardafu and targets children, youth and adults including vulnerable groups and public systems/institutions for effective education service delivery. The project focuses on primary education, special needs, secondary education, Alternative Basic Education (ABE), Non Formal Education (NFE), TVET and capacity building of the Ministry of Education and Higher Education (MoE&HE). The project aims to achieve the overall and specific objectives through the following three results areas namely:

- Result 1:Increased access to inclusive and equitable quality education at primary and secondary levels

- Result 2: increased inclusive participation of youth and adults in quality technical and vocational education; training linked to employment and economic opportunities

- Result 3: Enhanced capacity of public institutions to lead, monitor, and manage the education system

The project activities are as follows.

The activities being implemented broadly include the construction of new schools, construction of additional classrooms in existing schools, rehabilitation of classrooms; construction of toilets/WASH facilities for schools, provision of teaching/learning materials, community Education Committee (CEC) training, scholarships for children in need;  teacher training (pre-service/in-service), capacity building of MoE&HE, post-COVID19 safe return to schools, enrollment drives and awareness, TVET training; curriculum development for Non-Formal Education (NFE) and Joint Review of the Education Sector(JRES).

The project stakeholders involved in the implementation of the project are divided into three namely the holders of obligations, holders of responsibilities and rights holders. The holders of obligations consist of the Ministry of Education and Higher Education, Regional Education Officers, CARE and Save the Children while the holders of responsibilities comprise the teachers, District Education Officers (DEOs) and the schools in the intervention area. The last category comprises of the project beneficiaries such as parents, students, and communities.

- OBJECTIVE OF THE MIDTERM REVIEW:

The Waxbarashadu Waa Iftiin midterm review is seeking to procure the services of a consultant to conduct a midterm review to assess the progress made towards the project outputs, outcomes and impact levels. The midterm review will be inclusive by having full participation of the project staff and stakeholders such as Ministry of Education & Higher Education (MoE&HE), European Union(EU), CARE International and Save the Children and beneficiary communities.The midterm review will be implemented by an external consultant identified/selected by the Country office procurement committee in close coordination with the MoE&HE. It is considered to be external to ensure the objectivity and impartiality, but this does not exclude the technical support from MoE&HE, the Consortium and CARE Netherlands.

  - Overall objective

The main objective of this mid-term review/evaluation is to assess the degree of progress in the implementation of the expected results of Waxbarashadu Waa Iftiin IV/Education Is Light IV intervention as well as establish recommendations about the intervention design and implementation and its application to improve on the interventions. Further, ensure adaptation of informed strategies where the project may have experienced risk/challenges affecting achievement of targets. This review will cover a set of activities related to the project and as outlined in the project’s result framework and implementation plans.

  - Specific Objectives:

- The review must put a special emphasis on the quality of running processes including the design of the project. The findings and recommendations of the review/evaluation will be used by the consortium partners to inform the project’s relevance, effectiveness, efficiency, impact, sustainability, appropriation, harmonization, alignment and coherence.

- Identify the challenges and lessons learned in the context of the development of the Project.

- Note the degree of participation and involvement of all the key stakeholders in the intervention.

  - The Scope of the MTR

The MTR will look into the progress, achievements, constraints and lessons of the project under the expected results and cover project implementation from the start to date. The consultant will be expected to travel to all regions of program implementation (security permitting). The Waxbarashadu Waa Iftiin Phase IV program is implemented in all regions of Puntland State of Somalia.The assignment will involve a visit to the target schools based on samples derived in consultations with MoE&HE and the implementing partners. The consultancy will conduct a desk review, field data collection, data analysis and report writing and presentation of findings during a validation workshop to be organized for partners and the Donor.

  - Evaluation criteria used and key questions.

The MTR will focus on the expected results with due consideration of the support received from EU and implementing partners; CARE, Save the Children and MoE&HE throughout the project implementation period. In doing so, the MTR shall follow the OECD/DAC Criteria and include evidence under each criterion supported by qualitative and quantitative data. Specifically, the mid-term review seeks to answer the questions highlighted in the table below;

Table 1:      OECD/DAC Criteria

| S/n | OECD/DAC Criteria | Key questions |
| --- | --- | --- |
| 1 | Relevance | To what extent did the project intervention conform to the needs and priorities of target groups, and education policies? |
| 2 | Effectiveness | To what extent were the project objectives achieved at the results level? Did the benefits reach the target group as intended? Were benefits distributed fairly between gender and across social and cultural barriers? |
| 3 | Efficiency | To what extent are the costs of project intervention justified by its results, taking alternatives into account? Analyze the quality of day-to-day management (adequacy of project budget, management of personnel, project properties, communication, relation management with community leaders, other development partners, etc).ell |
| 4 | Appropriateness | How well did the activities respond to education service demands; considering the requirements for adaptation, ownership, accountability, and cost-effectiveness? |
| 5 | Sustainability | How and to what extent did the activities take into account longer-term needs and the interconnectedness of the existing human resources for education problems? To what extent were the stakeholders consulted and involved in selection processes for beneficiaries, and implementation? Assess the degree of commitment of stakeholders and the extent to which the capacity of beneficiaries and partners were built and strengthened and Suggest improvements for future interventions. |
| 6 | Coordination | Has coordination/planning been effective within and between consortia? Was the division of labour (sectoral, geographical) within the consortia appropriate/effective? How effective was the coordination with authorities through the Steering Committee? Did this improve the day to day implementation of the programme? |
| 7 | Impact | What processes led to the attribution of the results? What are the effects of the project on the beneficiaries? |

  - Lessons learnt:

The objective of this component of the MTR will be to document key lessons learnt to contribute to organizational learning; To establish and describe the best practices/promising practices in management of program that can be shared and replicated and bad practices/weakness to be avoided in future programs/projects; The consultant/team should provide information on the economic/political/financial conditions that should exist, qualifications of CARE required stakeholder participation, and other factors that should be in place to/to inform the re-design of operations.

- TECHNICAL APPROACH AND METHODOLOGY

The consultant shall use a mixed-method approach, combining qualitative and quantitative techniques. A qualitative approach will adopt data collection methods such as in-depth interviews, key informant interviews, focus group discussions and case studies, whereas quantitative approach will adopt the use of school-level questionnaires to collect primary data from schools and literature review for secondary data from project documents such as the proposal, Indicator performance tracking tool, log frame, evaluation framework and implementation plans. The sample size must be statistically representative of the population. The analysis will involve statistical and content analysis using appropriate packages as deemed fit by the consultant. The analysis among others should show trends and to the extent, possible should disaggregate data by gender and location. Unless otherwise, the consultant shall use the sampling techniques consistent with the baseline for ease comparability of performance and targets.

- EXPECTED DELIVERIES

The consultant will be responsible for defining and carrying out the evaluation tasks. This will include the design of the evaluation methodology (specification of the techniques for data collection and analysis), development of data collection tools, structured field visits and interactions with beneficiaries. The methodology and data collection tools will be reviewed and validated with the consortium partners, CARE Netherlands and approved by the European Union Representatives. Specifically, the consultant shall carry out the following activities

- Conduct desk review of internal materials including progress reports, project designs and log frame

- Prepare and present an inception report detailing their understanding of the ToR and how the assignment will be carried out for discussion with WWI IV project team and management. The inception reports must include proposed methodologies for data collection, analysis, report writing and dissemination

- Develop data collection tools and materials for executing the task and share it with the client for approval.

- Design a logical plan for the data collection, management and analysis based on context and consultations with CARE, SCI, and MoE&HE

- Recruit qualified staff to collect, analyze, write and submit the review report.

- Organize and implement the evaluation

- Compile both the secondary and primary data collected.

- Analyze the findings.

- Develop a draft report and submit to CARE, SCI,  MoE&HE and the donor for feedback

- Submit a final report by incorporating all comments given by the consortium, MoE&HE  and others

- Make powerpoint slides on the summary of the findings and present during the validation workshop

- And all the fill copies questionnaire/tools use during the process remain to be the property of CARE International.

The consultant is expected to work closely with the CARE International, Save the Children and MoE&HE management team to ensure all relevant information is included in the documents to ensure the development of quality documents.

- ROLE OF  CARE AND ITS PARTNERS

CARE will have the following functions: provide oversight, supervision and coordination of the assignment; coordinate document reviews and approval of all deliverables as per the terms of reference; provide linkages between the consultant and the project stakeholders and arrange for logistics for field visits. The consultant will report to the Consortium Coordinator and work closely with MEAL departments of the consortium partners and MoE&HE. During the assignment, dedicated project staff will be assigned to support the assessment team in coordinating the collection of data and to provide necessary information for planning purposes. Logistical and administrative support will be provided for example, office working space, transportation or associated expenses.

- CONSULTANT’S RESPONSIBILITIES

During the period of carrying out this assignment, the consultant will need to establish close coordination arrangements with the Head office in Puntland. In particular, the evaluator will be expected to work closely with the Consortium Coordinator, Program Coordinator and Project Managers of the consortium partners (SAVE the Children and CARE.  The consultant under this assignment will: -

- Be available for the assignment;

- Prepare all their travel documents;

- Commits to complete a fully satisfactory end product within the agreed time frame;

- Provides the necessary material for use during and after the evaluation.

INTELLECTUAL PROPERTY RIGHTS

All documentation related to the assignment shall remain the sole and exclusive property of CARE and the consortium partners.

- DOCUMENTS AND SOURCES OF INFORMATION

Documents and sources of information to which the evaluator will have access:

| Document | Location |
| --- | --- |
| Project Document | CARE Somalia |
| Logframe | CARE Somalia |
| Budget | Education Manager/Consortium Coordinator |
| Baseline study and Needs Assessment | CARE Somalia (MEAL Manager) |
| Follow up reports | CARE Somalia (Project/MEAL Manager) and Consortium |
| Memorandum of understanding between Consortium partners and MoE&HE | CARE Somalia |
| Other relevant information provided by the project management unit | CARE Somalia (Puntland)/Save the children |

⃰

- MTR REPORT STRUCTURE AND PRESENTATION

The principal output of the mid-term should be a report, detailing the approach, methodology and limitations, findings, conclusions and recommendations, referencing all relevant documents and intermediary work it is based upon. The mid-term evaluation report (max 30 pages, excluding the preliminary pages and annexes), will contain a short executive summary (max 3 pages) and a main body of the report covering the background of the interventions, a description of the assessment methods and limitations, findings, conclusions, lessons learned and recommendations. The mid-term evaluation report will be submitted one week after receipt of the consolidated feedback from CARE International and the consortium partners. The report should be three (3) Hard-cover-bound copies and soft copy in two (4) CD- ROMs in pdf version.

- GUIDING PRINCIPLES AND VALUES

The external evaluator will be required to;

- Adhere to internationally accepted good practices and solid ethical principles and standards;

- Be skilled in implementing diverse evaluation methodologies;

- Ensure the evaluation is an inclusive and participatory learning exercise; and

- Be culturally adaptive and gender-sensitive.

- Fulfil the criteria of professionalism, impartiality and credibility. Maintain total independence and sole responsibility for the final content of the report and recommendations

- Copyright and disclosure: all author rights rest with the contracting entity of the assessment, in this case, the CARE International.

- IMPLEMENTATION WORK PLAN

| # | Tasks | Duration (Man days) |
| --- | --- | --- |
|  | Literature review/Desk Review | 3 |
|  | Preparation of data collection tools, translation into Somali and testing/revision of tools | 2 |
|  | Travel to and from Puntland | 2 |
|  | Field data and information collection | 10 |
|  | Data and information analysis | 6 |
|  | Report writing and presentations | 7 |
|  | Total | 30 |

This assignment will be carried out in a total of 30 days effective from 1st March 2024.

- EXPECTED PROFILE OF THE CONSULTANT

The consultant will have the following expertise:

- Master’s Degree in Education, Social science and/or any other relevant discipline and not less than five years of relevant professional experience in conducting  programme  reviews/evaluations

- In-depth knowledge and understanding of capacity-building techniques for non-profit organizations involved in health programming.

- Demonstrated experience in developing organizational development and strengthening strategies for organizations. Previous consultancy experience of this nature is an added advantage for this assignment.

- A very good understanding of education system structures in Somalia. An understanding of how the government of Puntland operates and implements education services will be necessary for this assignment.

- Proven expertise and experience in developing capacity-building strategies.

- SUBMISSION OF PROPOSAL

All applicants must meet the minimum requirements described above, and those unable to meet these requirements will not be considered.

Each application package should include the following:

- An application letter addressing the selection criteria including how the firm’s/group’s previous experience matches the consultancy objectives as well as the interest for the position. The letter should be no longer than two pages.

- Technical proposal

- Financial proposal clearly providing breakdown of professional fees and field data collection costs.

- A sample of recently written report for a similar assignment.

- Updated CVs for all consultants including relevant work experience and qualifications.

- Contact details of 3 references

- Other required documents related to selection criteria.

| Requirement & Specs | Qty. | Unit of Measurement | Required Delivery Lead Time | Delivery Address | Contract Period |
| --- | --- | --- | --- | --- | --- |
| Mid-term Review of Education is Light IV project’ | N/A | N/A | 30 days | Puntland |  |

| Item # | Other Requirements |  |
| --- | --- | --- |
| 1 | Delivery/Execution Date & Time |  |
| 2 | Delivery Terms (incoterms) if applicable | EXW [Ex-works (Place)] |
|  |  | FCA [Free Carrier (Port)] |
|  |  | FAS [Free Along-Side Ship (Port)] |
|  |  | FOB [Free On-Board (Port)] |
|  |  | CFR [Cost, & Freight (Port)] |
|  |  | CIF [Cost, Insurance & Freight (Port)] |
|  |  | CPT [Carriage Paid-To (Place)] |
|  |  | CIP [Carriage & Insurance Paid-To (Place)] |
|  |  | DAP [Delivered at Place (Place)] |
|  |  | DPU [Delivered at Place Unloaded (Place)] |
|  |  | DDP [Delivered Duty Paid (Place)] |
| 3 | Custom Clearance (Must be linked to Incoterms at origin) | Not Applicable. Shall be done by _______________ |
|  |  | Shouldered by CARE |
|  |  | Supplier/ Bidder |
|  |  | Freight Forwarder |
| 4 | Exact Address(es) of Delivery Location | Puntland |
| 5 | Warranty Period | Standard Manufacturer’s Warranty (if applicable) |
| 6 | Payment Terms | 30 Days upon Receipt of invoice |
| 7 | Quotation Validity |  |

# PROJECT TIMELINE

All bidders are advised to strictly follow the below timeline as noted.

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible | Remarks |
| --- | --- | --- | --- |
| RFP Issued | 15-Feb-2024 | CARE |  |
| Supplier to notify CARE of intention to participate in bidding | N/A | N/A |  |
| Deadline for submission of clarification questions to CARE | 22-Feb-2024 | Supplier | Deadlines must be strictly observed. |
| CARE to answer all clarifications | 24-Feb-2024 | CARE |  |
| Supplier’s Deadline of Submission of Proposal | 25-Feb-2024 | Supplier | Deadlines must be strictly observed. |
| Evaluation of Proposal | 25-29-Feb-2024 | CARE |  |
| Vendor presentation (if required) | N/A | Supplier |  |
| Finalists selected | 5 March 2024 | CARE | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

# PROJECT REQUIREMENTS

- Technical Requirements

a.1 Technical Proposal of the Product

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Overall Proposal Suitability |  |  |
| 1 | Provide bidders’ approach to the end line evaluation |  |
| 2 | Bidders’ workplan with milestones for the implementation lead times. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Previous Works and Awards |  |  |
| 1 | Provide 3 or more client experiences referees or testimonials (References whose environment, size, and scope are most similar to CARE. Include a summary of the work completed for each account. Include reference contact names, with telephone numbers and email addresses.) |  |
| 2 | Provide previous records (experience) of performance and service. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Technical Expertise and Organizational Experience |  |  |
| 1 | Provide 3 Availability of vendor’s representatives to call upon and consult with including the lead consultant. |  |
| 2 | Any proof that the bidder has the Ability to render satisfactory service in this instance. |  |
| 3 | Provide Years of experience in providing the same requirement to other companies. |  |
| 4 | Provide the latest audited Financial Statement |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Others |  |  |
| 1 |  |  |

- VALUE & COST (Financial Requirements)

(Provide below requirements, payment terms, etc., if there’s any)

Financial proposal clearly providing breakdown of professional fees and field data

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery/Implementation Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

# EVALUATION CRITERIA

CARE will evaluate all proposals based on the following criteria.  To ensure consideration for this Request for Proposal, your proposal should be complete and include all of the following criteria:

- Overall Proposal Suitability: proposed solution(s) must meet the scope and needs included herein and be presented in a clear and organized manner

- Previous Work and Awards: Bidders will be evaluated on examples of their work pertaining to the requirement as well as client testimonials and references

- Technical Expertise and Organizational Experience: Bidders must provide descriptions and documentation of staff technical expertise and experience. Bidders also need to provide their experiences as an organization which include but not limited to years of experiences, financial stability, expertise, and edge to other competitors.

- Value and Cost: Bidders will be evaluated on the cost of their solution(s) based on the work to be performed in accordance with the scope of this project Including the detailed breakdown of professional costs, and separate costs for reimbursable expanse – please refer to the budget proposal requirements in ToR.

CARE will review proposed budgets and pricing after the initial review of the criteria above.