Request for Proposal

TERMS OF REFERENCE (TOR) FOR INTEGRATED NUTRITION SMART SURVEY CONSULTANCY

RFP DOCUMENT: 37914

RFP Issue Date: 5 June 2025

Proposal submission Deadline: 12 June 2025

CARE USA

151 Ellis Street NE

Atlanta, GA 30303-2440

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of submitted proposal

- To award another type of contract other than that described herein, or to award no contract;

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions, and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.B. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Consultant/Firm Name: |  |
| --- | --- |
| Title/Designation: |  |
| Contact Person |  |
| Telephone & email |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in the proposals must be all-inclusive to include any outsourced or contracted work.  Any proposals which call for outsourcing or contracting work must include a name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

TOR FOR THE CONSULTANT

Background

CARE is a leading international non-governmental organization operating in Somalia and Somaliland since 1981, dedicated to addressing poverty, social injustice, and humanitarian crises through integrated programs in Climate Justice, Food, Water, and Nutrition; Gender Equality & Education; and Humanitarian Assistance. Aligned with national development plans, CARE focuses on enhancing food security, improving nutritional outcomes, and building resilience among vulnerable populations, including internally displaced persons (IDPs), women-headed households, and communities affected by recurrent climate shocks and conflict. CARE manages a significant humanitarian portfolio in Somalia and has built a strong reputation as a humanitarian actor in Somalia and Somaliland thanks to many years of support to populations affected by conflict, droughts, famine, and epidemic outbreaks.

The humanitarian situation in Somalia is dire, with the total acute malnutrition burden for January to December 2025 estimated to affect 1.8 million children aged 6-59 months, including 479,000 likely to be severely malnourished. This represents an increase of nearly 47,000 children compared to the January 2025 analysis, which estimated 1.7 million affected . A reduction in humanitarian funding is already impacting service delivery across the nutrition, health, and WASH sectors, which is expected to exacerbate levels of acute malnutrition nationwide. Sixteen districts, primarily in rural areas include Qardho, Caynabo, Lascanood, Badhan, and Afmadow districts in Bari, Sool, Sanaag and Lower Juba regions are identified as the most affected. The acute malnutrition situation is projected to deteriorate further between April and June 2025, moving from IPC AMN Phase 3 (Serious) to Phase 4 (Critical) in several areas. Contributing factors include the closure of health facilities, suspension of therapeutic feeding programs, and increased household hunger gaps due to reduced food assistance.

To strengthen nutrition surveillance and provide timely data in light of the current crisis, CARE plans to conduct a SMART survey in the Qardho, Caynabo, Lascanood, Badhan, and Afmadow districts of Bari, Sool, Sanaag, and Lower Juba regions. CARE seeks an external consultant to lead this survey, aiming to generate quality information for humanitarian actors and address regional nutrition information gaps. Given the evolving humanitarian situation, this survey will help ascertain key indicators essential for an effective response.

METHODOLOGY

The survey will be developed using the SMART methodology, utilizing ENA software 2020 to perform all necessary analyses typical of a standard SMART survey. This includes conducting standardization tests, calculating sample sizes, selecting clusters, and determining the final rates of wasting based on both WHZ scores and MUAC measurements. The sampling approach will employ a two-stage probability proportional to size method, where the first stage involves selecting clusters and the second stage focuses on selecting households within those clusters.

The sample size will be calculated at the district level using ENA 2020, with relevant parameters sourced for the survey. The survey will be conducted at the district level, aiming to include all accessible settlements within the sampling frame. Additionally, the analysis of anthropometric findings will be categorized according to WHO standards released 2006, ensuring that the results are aligned with established guidelines for health assessments.

OBJECTIVES

The Consultant will oversee the SMART survey in three districts of Bakool, Southwest State of Somalia, ensuring the production of quality data on anthropometry, common childhood illnesses, acute food insecurity, WASH, and immunization coverage, along with additional household demographic information, while leading data analysis and report writing for the survey.

SPECIFIC OBJECTIVES

- To engage AIMWG for Survey protocol and report validation.

- To work with the MEAL department to support field teams in coding and uploading data on the Kobo platform and exporting it to ENA software using standard questionnaires.

- To extract daily plausibility reports from ENA and provide feedback on the collected data daily.

- To analyze the coverage of Vitamin A supplementation and immunization services, as well as the prevalence of illness among children under five years.

- To estimate the prevalence of acute malnutrition in children aged 6-59 months and assess maternal nutrition status of women of childbearing age (WCBA) and pregnant/lactating women (PLWs) using MUAC measurements.

- To determine the coverage of measles vaccination among children aged 9-59 months and evaluate the two-week period prevalence of morbidity in the same age group.

- To assess food security indicators, including HDD, FCS, CSI, and WASH indicators

- To establish recommendations based on findings and determine the uptake of Outpatient Therapeutic Programs (OTP) and Supplementary Feeding Programs (SFP).

DURATION OF ENGAGEMENT

The consultation will be engaged for a period of 25 working days with the possibility of extension if other assessments arise. The support onsite and routine updates provided to the MEAL unit, Health and Nutrition sector leads, and Technical Specialist.

ROLE & RESPONSIBILITIES

Snr MEAL Manager, supported by the Health and Nutrition Program Managers, and Country Office sector leads will provide all the necessary support to the consultant for conducting the SMART survey. CARE will provide all necessary project documents including a previous SMART survey, technical assistance (e.g. availability of any other documents and information needed etc).

CARE Role

- Coordination and arrangements of the training event include logistics, stationery, venue and lunch and refreshments.

- Hiring Enumerators and engaging supervisors.

- Community engagement and sensitization.

- Laise with respective line ministries for all regions.

Consultant Role

- Develop training plan for the SMART survey and conduct full enumerators training for all survey participants.

- Facilitate, conduct and share the record of Standardization test with the survey manager (NHIMS).

- Develop SMART survey protocol and present to the AIMWG for validation,

- Review of the SMART survey training materials ahead of the training and provide input where necessary.

- The consultant will manage pilot test in specific selected clusters, analyze the data and give feedback before starting data collection.

- The consultant will oversee the process of the collection of all data ensuring quality control measures are in place.

- The consultant will conduct daily data quality checking and share the plausibility report with CARE team on the ground regularly.

- The consultant will lead the data analysis and generate quality report in line with smart Methodology quality standards

- Share full ENA dataset with all sections completed (planning dataset, standardization dataset, under 5 dataset, mortality and morbidity dataset, food security and WASH and other additional indicators dataset).

- Prepare power point slides for AIM working group validation and share one week before presenting to the AIMWG for internal review and input.

- Present the SMART survey assessment result to AIM working group.

- Address any additional comments from AIM working group.

- After validation, share final report with complete dataset and Stata files for reproducibility, and prepare one pager visualization sheet for the key results.

DELIVERABLES

1.	Training and Data Collection Proposal

- Develop and submit a comprehensive proposal for the training and data collection, including a detailed budget.

2.	Training Report

- A detailed report includes training content, composition of participants, key observations and reflections from the training.

3.	Quality Data Set

- The total number of households achieved (100% of the sample expected).

- Quality plausibility check results with an acceptable overall score.

- Acceptable standardization data and corresponding datasets.

- Cluster control forms.

4.	Draft and Final SMART Survey Report

5.	Compile and submit the final SMART survey report.

6.	Scan, zip, and email all relevant documents.

SKILLS AND QUALIFICATIONS

1.	Education: Degree in Nutrition, Public Health, or Statistics.

2.	Experience: Minimum of 4 years in conducting SMART surveys, research, or surveillance, with strong reporting skills.

3.	Skills:

- Ability to coach, supervise, and build capacity in SMART methodologies.

- Proficiency in STATA, EPI/ENA, and Epi Info; attendance at SMART Survey Manager training or equivalent is preferred.

- Fluent in English and Somali, have adult learning and presentation skills, along with high organizational capabilities.

- The ability to contextualize training is a plus.

- Can independently travel to Somaliland, Puntland and Jubaland.

4.	Coordination and Management: Excellent coordination, management, and report writing skills.

5.	Previous Experience: Experience with CARE is an added advantage.

REPORTING

The consultant will report to the Senior Health and Nutrition Advisor and the Senior MEAL Manager throughout the assessment period. Regular updates will be provided to ensure alignment with project goals.

APPLICATION PROCEDURE AND REQUIREMENTS

Interested candidates in the position are expected to provide the following documentation:

1.	A technical proposal with a detailed response to the TOR, with specific focus on the scope of work, detailed work plan.

2.	Initial work plan based on the methodology outlined, and indication of availability physically.

3.	A financial proposal detailing the daily rate expected but not including accommodation, stationery, research assistance(enumerators) and all other costs related to this assignment.

4.	Company profile including the CVs for the consultant

5.	Contract details of three reputable references.

6.	A sample of previously conducted similar studies.

HOW TO APPLY

All applicants must submit their technical proposals along with the other requirements and complete them accordingly. Applicants must meet the minimum requirements described above; those unable to meet these requirements will not be considered.

Please send your complete RFP, technical and financial proposals (professional costs only) to this email address: SOM.Consultant@care.org, clearly marking the subject line “Integrated Nutrition SMART Survey”. Applications must be submitted no later than 12 June 2025, at 11:59 PM EAT. Links will not be accepted.

6.	 SELECTION CRITERIA

  - Technical Requirements

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. | Score |
| --- | --- | --- | --- |
| - Overall Proposal Suitability |  |  | % |
| 1 | Provide bidders’ approach and methodology for assignment including clear workplan with milestones for the implementation. |  | 30 |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. | Score |
| --- | --- | --- | --- |
| - Previous Works and Awards |  |  | % |
| 1 | Provide full information of 3 referees for previous and most recent clients |  | 10 |
| 2 | Provide report sample for similar consultancy services |  | 10 |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. | Score |
| --- | --- | --- | --- |
| - Technical Expertise |  |  | % |
| 1 | Updated CVs for Technical assigned to this activity including relevant work experience and qualifications |  | 20 |

CARE will review proposed budgets and pricing after the initial review of the criteria above is done.

  - Financial Requirements

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. | Score |
| --- | --- | --- | --- |
| - Financial Proposal |  |  | % |
| 1 | The financial proposal must cover all the activities outlined above consultant. |  | 30 |

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery/Implementation Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days) |  |  |  |
| Other Requirements (Please specify) |  |  |  |