Request for Proposal

[Terms of Reference for Endline Assessment for the Global Food Crisis - Somalia - Gender-responsive Nutrition Support Project in Lower Juba and Gedo Region, Somalia, 2022 – 2024, CARE

]

RFP DOCUMENT # [__35680]

RFP Issue Date:  05/02/2024]

Proposal submission Deadline :  [15/02/2024]

CARE USA

151 Ellis Street NE

Atlanta, GA 30303-2440

onfidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of submitted proposal

- To award another type of contract other than that described herein, or to award no contract;

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions, and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.A. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Supplier Name: |  |
| --- | --- |
| Title/Designation: |  |
| Company Name: |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All vendors must provide written notification via email to (Som.consultant@care.org) of their intent to participate, or not to participate in the bidding process by [feb-15th  2024

Proposals will be accepted until feb-15th 2024  if you  may need any clarification on the TOR you can  delivered via email solely to Mahdi.Mohamed@care.org>;  ] , no later than 10/02/2024.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in proposals must be all-inclusive to include any outsourced or contracted work.  Any proposals which call for outsourcing or contracting work must include a name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

CARE is issuing this RFP (Request for Proposal) soliciting qualified bidders to submit proposals intended for the   Endline Assessment for the Global Food Crisis - Somalia - Gender-responsive Nutrition Support Project in Lower Juba and Gedo Region, Somalia, 2022 – 2024, CARE

This RFP is an invitation to bid, not an offer of contract.  Bidders must submit a response that complies with the minimum requirements contained herein.

# PROJECT OVERVIEW

CARE is seeking a provider to submit proposals intended for the provision of services for conducting Endline Assessment for the Global Food Crisis Project as per the below detailed ToR

## Background

Somalia remains entrenched in one of the most intricate and enduring global humanitarian crises. Consecutive occurrences of severe flooding, escalating conflict, the most severe locust infestation in decades, and the onset of the COVID-19 pandemic have collectively given rise to unparalleled humanitarian needs. The crisis's multi-faceted nature surpasses the capacity of local resources to mount effective responses. According to the 2022 Somalia Humanitarian Response Plan (HRP), an estimated 5.9 million people will require humanitarian assistance, representing an increase from 5.2 million in 2021 and 4.2 million in 2019. The ongoing trend of displacement adds to the challenges, imposing an additional burden on the estimated 2.6 million people already living in a prolonged state of displacement.

Specifically, in Somalia, urgent life-saving nutrition support is needed for approximately 45% of children under the age of 5 (1.5 million children) and over 250,000 pregnant and lactating women until the end of 2022. The humanitarian situation in Jubaland state has significantly deteriorated following the failure of the April-June 2022 rainfall, impacting 1.1 million people with Crisis or more severe outcomes, including approximately 361,000 people facing Emergency conditions (IPC Phase 4). In Jubaland State, 178,300 children under the age of five are grappling with acute malnutrition, with nearly 46,000 at risk of severe malnourishment. Stunting among children under 5 in Jubaland state is prevalent at 28.1%. Malnutrition rates among these children are 33.7%, with a 16.3% prevalence of wasting. Poor infant and young child feeding practices are evident, including low dietary diversity (5%), sub-optimal breastfeeding rates (76%), and a limited number of children being breastfed up to 2 years (30%). The World Food Programme (WFP) identifies Gedo and Lower Juba, regions within Jubbaland, as having the highest levels of insufficient food consumption. In Gedo, 50% of the population, and in Lower Juba, 54%, are facing Crisis (IPC 3) and Emergency (IPC 4) food consumption gaps until year-end. Failed cereal harvests and global price shocks due to the Ukraine conflict have pushed staple and imported food prices beyond the means of millions of households already spending 60-80% of their income on food. A CARE needs assessment in February 2022 highlighted that 74% of respondents in Sool, Sanaag, Lower Juba, and Galguduud had no access to nutrition treatment services. Consequently, only 20% of households needing such services reported receiving malnutrition treatment in the past month. Despite intensified humanitarian efforts, national nutrition response rates remain low, with 57.7% coverage for Severe Acute Malnutrition (SAM) and 43.8% coverage for Moderate Acute Malnutrition (MAM) as of July 2022. In Bardhere, only three humanitarian organizations are present, and out of the 24 health facilities, only 16 offer Targeted Supplementary Feeding Program (TSFP) services, served by a single stabilization center (Somalia Nutrition Cluster).

The impact of the multiple humanitarian crises has exacerbated pre-existing vulnerabilities of women and girls and negatively affected health, wash and livelihoods, and coping mechanisms for vulnerable families and internally displaced people (IDPs).

CARE is a humanitarian non-governmental organization committed to working with poor women, men, boys, girls, communities, and institutions to significantly impact the underlying causes of poverty. Through GAC funding projects, CARE aims to save lives, alleviate suffering, and maintain human dignity through gender-responsive nutrition interventions for crisis-affected women, men, boys, and girls in Somalia. Life-saving nutrition services through the CMAM approach are core to the project’s design, the components of CMAM being community outreach and mobilization; management of SAM without medical complications through outpatient therapeutic programs (OTP); inpatient management of SAM with medical complications at stabilization centres (SC); and outpatient targeted supplementary feeding programs (TSFP) to manage MAM. The project teams will work through community-based approaches to raise awareness of good nutrition practices (particularly infant and young child feeding (IYCF)) and early referral to nutrition services, given their importance for the prevention of malnutrition, and reducing risk of associated mortality and adverse developmental outcomes. As critical, basic health and WASH assistance play a vital role in the prevention of acute malnutrition and deterioration of nutritional status, nutrition activities will be complemented by primary health care services with clear nutrition outcomes, and provision of safe water, basic hygiene items, and hygiene promotion campaigns by contribute to economic and social transformation, unleashing the power of the most vulnerable women and girls.

The Global Food Crisis for Gender-responsive Nutrition Support project in Lower Juba and Gedo Region, Somalia, 2022 – 2024 is a 2-year Global Affairs Canada-funded project running from October 2022, through Mar 2024. The project is implemented by CARE, which plays an overall leadership role and implements field activities. The outcome of the project is to save lives, alleviate suffering, and maintain human dignity through gender-responsive nutrition interventions for crisis-affected women, men, boys, and girls in the Lower Juba and Gedo regions of Somalia.

To achieve the project goal, CARE implemented initiatives targeting the immediate needs of internally displaced persons (IDPs), returnees, and host communities. The efforts focused on enhancing health and nutrition conditions, addressing water, sanitation, and hygiene (WaSH) issues, and providing protection-related assistance. The project aimed to benefit a total of 528,074 individuals, including 103,525 men, 179,696 women, 123,210 boys, and 121,643 girls, over a two-year period as displayed in the below table. The project covered five districts: Kismayo, Afmadow, and Badhaade districts in the Lower Juba region, as well as Bardhere and Luuq Districts in the Gedo region.

Intermediate Outcome

Lives saved, suffering alleviated and human dignity maintained through nutrition interventions for crisis-affected women, men, boys, and girls in Somalia.

Immediate outcomes

- Outcome 1 - Increased and more equitable access to gender-responsive nutrition services for children under 5 and PLW/G in Somalia

- Outcome 2 - Increased and more equitable knowledge of community nutrition practices, especially infant and young child feeding (IYCF), among caregivers, community members, and nutrition/health workers in Somalia.

- Outcome 3 - Increased and more equitable access to critical basic health and WASH services in communities targeted with nutrition programming (especially children under 5 and PLW/G) to reduce risk, and support successful treatment, of malnutrition in Somalia.

# Objectives of the Endline Assessment

The primary aim of the endline assessment is to evaluate and establish dependable concluding data regarding the project's performance concerning predefined parameters across its three components: Health and Nutrition (encompassing cash interventions targeting Severe Acute Malnutrition beneficiaries), WASH, and Protection. The evaluation report will pinpoint best practices and essential insights in both technical aspects and the program management approach, facilitating continuous learning and enhancing the effectiveness of humanitarian emergency response. The outcomes of this concluding assessment will be communicated to Global Affairs Canada (GAC) and shared with the humanitarian community operating in Somalia, disseminated through channels such as the Somalia NGO Consortium, the UN Cluster system, the broader CARE International network, and local networks. Specific objectives include:

- To determine whether the implementation strategy has contributed to addressing the issues identified in the baseline assessment that justified the development and implementation of the project (relevance);

- Assess the results achieved and any discrepancies between planned and achieved objectives (effectiveness);

- Compare the results achieved with material, financial, human resources, etc. used (efficiency);

- Assess the strengths and weaknesses of the overall project implementation methodology as well as the opportunities and constraints for its scale-up.

- Assess the quality of the involvement and participation of the various stakeholders (CMP, country office, and project participants) in the implementation of the project.

# Evaluation Questions

- What were the project's achievements in relation to the established targets and bassline values outlined in the Performance Measurement Framework at outcome levels (immediate, intermediate, and ultimate)?

- To what extent does the project comply with OECD-DAC criteria on effectiveness and impact?

- What were the lessons learned in terms of the project's contribution towards gender-responsive nutrition outcomes and nutrition services?

- What was the impact of project intervention on women, IDPs, returnees, and people with disabilities who received direct support through the project?

- What are the key lessons learned and best practices from the program implementation, operating context, and response type as well?

Evaluation Criteria

The evaluation will be done in line with OECD-DAC recommended criteria based on the  three criteria sustainability, and impact. The end-line assessment will contribute to both strengthening the accountability of CARE International in Somalia to its donors and key stakeholders including beneficiaries, and to learn from this experience to inform future programming.

Effectiveness

- To what extent has the project increased the capacity of Health and Nutrition accessibility and enhanced the community needs and priorities? Are the results satisfactory?

- To what extent has the project enhanced and addressed the practices related to feeding infants and young children and personal hygiene practices through the attainment of knowledge, attitude, and practice changes?

- What were the key drivers and barriers that impacted on the delivery of the project outputs?

- To what extent has the project used learning to improve delivery?

- To what extent has the program achieved its intended health and nutrition outcomes?

- Can changes in health and nutrition outcomes be directly attributed to the program?

Sustainability

- What is the level of community ownership, as reflected in the participation of the community in the project-supported Health facility community-based structures?

- Is the project supported by community-based structures adequately and has a long-term vision and strategy for operating, maintaining, and regulating the water supply and sanitation infrastructure/system?

- Do the community have the capacity to maintain the benefits from the project with support from CARE or any other donor? If yes, how? If not, what will be the principal challenges in sustaining the program benefits?

- To what extent has the program achieved its intended health and nutrition outcomes?

- Can changes in health and nutrition outcomes be directly attributed to the program?

Impact

- Has the project contributed to the improvement in the quality of life of the people in affected districts?

- Have there been any other changes (positive and negative) at the household or community level as a result of the project?

- How has the health and nutrition status of the target population changed over the course of the intervention or program?

- What are the observed improvements or deteriorations in key health & nutrition indicators?

- Has the project affected people in ways that were not originally intended? If yes, what has changed?

- What was the role of the program partners in delivering the assistance?

- What is the gender impact of the project in the areas of intervention?

Equity

- Did the project contribute to equitable participation and benefits to various groups (men, women, boys and girls, and differently abled people)?

- Over the past 2 years, were there any undertakings by the project to promote equity? If yes, how? If not, why not?

# Approach and Methodology

The final evaluation serves as a performance assessment, utilizing a non-experimental design to enable a simple pre-post comparison of results. This evaluation employs a combination of quantitative and qualitative methods, involving a beneficiary household survey, document reviews, and interviews with both participants and stakeholders. The reporting of project accomplishments linked to specific indicator values will take a comparative analysis approach.

The technical support team is anticipated to put forth a fitting and comprehensive evaluation methodology that includes the right evaluation approach, sampling techniques, data analysis methods, presentation and reporting strategies, and ethical considerations for the evaluation.

# Scope of the Evaluation

The end-line assessment will cover the Kismayo, Afmadow, and Badhaade districts of Lower Juba, Somalia, Specifically the locations where the project activities have been implemented. The participants of the evaluation survey will include IDPs, returnees, host rural and urban communities in the target area as well as government authorities and partner agencies.

# Responsibilities of CARE

- CARE will provide all logistics support including flights, accommodation, transport, enumerators recruitment, payment of enumerators, etc.

- Commission the consultancy fee for the study

- Introduce the consultant to relevant stakeholders.

- Review and approve the study instruments/tools including the digital quantitative (Kobo, ONA) tool and qualitative guides.

- Support the consultant in field data collection while supervising the entire process.

- Overall data quality control and technical review of the final report and approval of the final report

# Responsibilities of the Consultant

- Develop appropriate methodology and tools for the data collection and analysis process. The tools will be shared and approved by CARE before starting fieldwork.

- Develop a practical work plan for the work

- Undertake a desk-based review and lead field-level data collection

- Train enumerators who will be involved in the data collection.

- Conduct data collection including pretesting of tools in the districts covered by the project,

- Ensure that datasets are clean, complete, and consistent.

- Analyse data and write baseline survey report.

- The consultant shall be liable for ethical procedures including obtaining informed consent from respondents.

- Debrief CARE Somalia/Somaliland after completing the assignment and validate the findings prior to submitting the final report.

- Prepare and submit a final evaluation report to CARE Somalia/Somaliland as per the time frame set in the ToR.

# Key Deliverables

The evaluation deliverables are:

- Inception Report:  For review, the evaluation team should submit to CARE an inception report presenting findings from the desk review and/or examination of data to date. The inception Report should include

  - Detailed evaluation methodology

  - Proposed sample size with specific detail on sampling approach and methodology

  - Evaluation Matrix

  - Procedures for ethical consideration

  - Revised work plan

  - Data collection methodology, including data collection tools for all indicators

  - Proposed data analysis methods and the tools and technologies to be used.

- Draft Evaluation Report: The consultant providing the technical support should share a draft evaluation report that addresses all the questions identified in the ToR and any other issues the team considers to have a bearing on the objectives of the evaluation. Once the initial draft evaluation report is submitted, CARE will have 5 working days in which to review, comment on the initial draft, and submit the consolidated comments to the evaluation team. The evaluation team will then be asked to submit a revised final draft report within 5 working days, and again CARE will review and send comments on this final draft report within 4 working days of its submission.

- Final Evaluation Report:  The consultant will be asked to take no more than 7 working days (or as agreed upon in the work plan) to respond to and incorporate final evaluation report comments from CARE. The technical lead will then submit the final report to the Emergency Director in CARE International in Somalia/Somaliland. A fact sheet (one page) for each thematic area and a succinct presentation should accompany the final report.

CARE suggests the final evaluation report have the following format/structure,

- Executive Summary (one page written succinctly to summarize the methodology, key findings, and lessons learned)

- Recommendations—list of key recommendations and learning from the evaluation, with brief explanations

- Introduction:

- Project Introduction, purpose and objectives

- Methodology, Scope, and Sampling

- Limitations

- Key Findings analyzed on evaluation criteria and in reference to the evaluation question while also providing gender and geographically disaggregated data.

- Conclusions

- Recommendations for future programmingAnnexes: Evaluation Terms of Reference

- - Names of evaluators

- - Logical Framework Matrices (Updated with endline values)

- - Map of the project area, if applicable

- - List of persons/organizations consulted

- - Literature and documentation consulted

- - Other technical appendices (e.g., statistical analyses)

- Submission of Dataset(s) to the Development Data Library: The consultant must submit the report to CARE in a machine-readable, non-proprietary format, any dataset created or obtained in the performance of this award. The dataset should be organized and documented for use by even those not fully familiar with the intervention or valuation. The data sets to be submitted include

- All data collection tools used for the assignment

- Raw and cleaned data sets (Qualitative and Quantitative)

- Generated codebooks and syntaxes preferably in SPSS or STATA formats

- Qualitative codebook, audio types, transcriptions, and translations.

- All Photos documented for evaluation purposes

- GPS Coordinates for all sampled locations

- Presentations

# Duration of the Assignment

The duration of the assignment is 40 working days after the signing of the contract. Days are inclusive of traveling, fieldwork, and reporting. The evaluation is expected to take place from 10th February to 25th March 2024.

|  | Activity | Time Frame |
| --- | --- | --- |
| 1 | Inception Meetings, Literature review, and Finalization of Inception Report (with tools attached) | 3 days |
| 2 | Hiring Enumerators, Translating of tools, pretesting tools, and Training Enumerators | 6 days |
| 3 | Fieldwork –Data Collection –Qualitative and Quantitative | 10 days |
| 4 | Data Entry, Cleaning, Data Analysis, and Production of Tables | 5 days |
| 5 |  |  |
| 6 | Final-End line Study Report Preparation | 5 days |
| 7 | Formal presentation of results to CARE | 1 day To be submitted 12 days after completion of study |

# Qualification of the Consultant

The evaluation is to be conducted externally. The consultant or consulting team should possess extensive experience in conducting evaluations for projects similar to those funded by GAC. Additionally, they should demonstrate substantial expertise in the context of Somalia, particularly – Jubaland State regions to ensure a thorough understanding of the local conditions.

Further qualifications for the consultant or team are outlined below.

- Over 10 years of international humanitarian and development expertise, specifically in the Somalia context.

- Demonstrated experience in conducting humanitarian evaluations.

- Substantial experience and a thorough understanding of nutritional expertise and its interrelations with diverse sectors, notably health, WASH (Water, Sanitation, and Hygiene), food security, and livelihoods.

- Profound understanding of the factors influencing malnutrition and poor health in the Somalia context, coupled with experience in evaluating health and nutrition programs.

- Comprehensive knowledge and experience in the Somalia context, with a preference for teams that include Somali speakers. If not feasible, the methodology should outline how local feedback will be obtained.

- Familiarity with the World Humanitarian Summit’s Grand Bargain and OECD DAC Criteria.

- Robust experience and understanding of applying humanitarian standards such as SPHERE and Core Humanitarian Standards (CHS).

- Well, converse and understanding of the integrated programming approach, with the ability to offer recommendations based on evaluation findings.

- Capability to grasp the broader context and provide practical recommendations for implementation and on-the-ground improvements.

- Proficiency in absorbing, consolidating, analyzing, and communicating extensive amounts of data and information simply and concisely.

- Experience and ability to operate in security-volatile environments.

- Background in collaborating with local partners and the private sector, particularly in the Health and Nutrition sector.

- Excellent interpersonal skills.

- Willingness to travel to Somalia within the security framework established by CARE International.

- Proficient in participatory facilitation and workshop design.

- Excellent English report-writing skills

# How to apply:

All applications MUST be accompanied by a technical and financial proposal including a brief outline of the proposed methodology, 3 references with contacts, and a tentative work plan as well as the candidate’s availability during the months of February and March 2024. The proposals shouldn’t exceed 10 pages. The deadline for submission of technical and financial proposals is 15th February 2024.

Interested consultants or firms are expected to conduct their own security and accessibility of the target project locations before application. Updated CVs of individuals or profiles of applying companies expressing interest in conducting the assessment should be sent som.consultant@care.org not later than 15th February 2024. Please indicate “Global Food Crisis Project – GAC End-line assessment’.

Bids should include the following:

- Technical proposal in word or PDF covering bidders approach to the evaluation; workplan with milestones, how the bidder meets the qualifications, including CVs of all key involved persons etc

- Financial proposal in excel or PDF format covering only for professional fee,

NOTE: please download the RFQ templet from the link and fill where appropriate and share it back with all other requirement documents

| Requirement & Specs | Qty. | Unit of Measurement | Required Delivery Lead Time | Delivery Address | Contract Period |
| --- | --- | --- | --- | --- | --- |

[Provide additional requirements]

| Item # | Other Requirements |  |
| --- | --- | --- |
| 1 | Delivery Date & Time | Bidder shall deliver the goods at least ____ weeks after Contract signature. |
| 2 | Delivery Terms (incoterms) | EXW [Ex-works (Place)] |
|  |  | FCA [Free Carrier (Port)] |
|  |  | FAS [Free Along-Side Ship (Port)] |
|  |  | FOB [Free On-Board (Port)] |
|  |  | CFR [Cost, & Freight (Port)] |
|  |  | CIF [Cost, Insurance & Freight (Port)] |
|  |  | CPT [Carriage Paid-To (Place)] |
|  |  | CIP [Carriage & Insurance Paid-To (Place)] |
|  |  | DAP [Delivered at Place (Place)] |
|  |  | DPU [Delivered at Place Unloaded (Place)] |
|  |  | DDP [Delivered Duty Paid (Place)] |
| 3 | Custom Clearance (Must be linked to Incoterms at origin) | Not Applicable. Shall be done by _______________ |
|  |  | Shouldered by CARE |
|  |  | Supplier/ Bidder |
|  |  | Freight Forwarder |
| 4 | Exact Address(es) of Delivery Location | The evaluation will cover 25 districts across six region/states; Puntland, Galmudug, South West, Hirshabelle, Jubaland and Banaadir as outlined in the ToR. |
| 5 | Warranty Period | Standard Manufacturer’s Warranty (if applicable) |
| 6 | Payment Terms | 30 Days upon Receipt of items |
| 7 | Quotation Validity | The quote needs to be valid for 90 days to cover all the days from bidding up to the award process. However, once the contract has been released, it shall be valid for the same coverage as reflected in the requirement above. |

[Provide additional requirements]

# PROJECT TIMELINE

All bidders are advised to strictly follow the below timeline as noted.

Any technical questions arising during the preparation of your response to this RFP should be submitted in writing via email to Mahdi.Mohamed@care.org no later than [05/02/2024.

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible | Remarks |
| --- | --- | --- | --- |
| RFP Issued | 05/02/2024 | CARE |  |
| Supplier to notify CARE of intention to participate in bidding |  | Supplier | Deadlines must be strictly observed. |
| Deadline for submission of clarification questions to CARE | 05/02/2024 | Supplier | Deadlines must be strictly observed. |
| CARE to answer all clarifications | 7/02/2024 | CARE |  |
| Supplier’s Deadline of Submission of Proposal | 10-02/2024 | Supplier | Deadlines must be strictly observed. |
| Evaluation of Proposal |  | CARE |  |
| Vendor presentation (if required) |  | Supplier |  |
| Finalists selected |  | CARE | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

# PROJECT REQUIREMENTS

- Technical Requirements

a.1 Technical Proposal of the Product

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Overall Proposal Suitability |  |  |
| 1 | Please see the Scope of Work and any other required specifications for this project. |  |
| 2 | Provide Delivery Lead Time |  |
| 3 | Provide after-sales service (if applicable) |  |
| 4 | Ability to provide sample (if applicable) |  |
| 5 | Provide Warranty Period |  |
|  | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Previous Works and Awards |  |  |
| 1 | Provide 3 or more client experiences or testimonials (References whose environment, size, and scope are most similar to CARE. Include a summary of the work completed for each account. Include reference contact names, with telephone numbers and email addresses.) |  |
| 2 | Provide previous records of performance and service. |  |
| 3 | Provide citations and awards. This encompasses reviewing the citations and awards a vendor has received from other customers and award-giving bodies. |  |
| 4 | Provide any testimonials, survey response/s from previous buyers and/or partners. |  |
| 5 | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Technical Expertise and Organizational Experience |  |  |
| 1 | Provide 5 Availability of vendor’s representatives to call upon and consult with. |  |
| 2 | Any proof that the vendor has the Ability to render satisfactory service in this instance. |  |
| 3 | Provide Years of experience in providing the same requirement to other companies. |  |
| 4 | Provide the latest audited Financial Statement |  |
| 5 | (Any additional requirement that is deemed necessary for “Technical Expertise and Organizational Experience. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Others |  |  |
| 1 | Provide any relative requirements which were not mentioned above. (delete if not applicable) |  |

- VALUE & COST (Financial Requirements)

(Provide below requirements, payment terms, etc., if there’s any)

See attached template (in Excel File) to be used for your financial bid.

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

# EVALUATION CRITERIA

CARE will evaluate all proposals based on the following criteria.  To ensure consideration for this Request for Proposal, your proposal should be complete and include all of the following criteria:

- Overall Proposal Suitability: proposed solution(s) must meet the scope and needs included herein and be presented in a clear and organized manner

- Previous Work and Awards: Bidders will be evaluated on examples of their work pertaining to the requirement as well as client testimonials and references

- Technical Expertise and Organizational Experience: Bidders must provide descriptions and documentation of staff technical expertise and experience. Bidders also need to provide their experiences as an organization which include but not limited to years of experiences, financial stability, expertise, and edge to other competitors.

- Value and Cost: Bidders will be evaluated on the cost of their solution(s) based on the work to be performed in accordance with the scope of this project.

Note for Country Offices (CO): The specific criteria must closely represent the objective and scope given the nature of the procurement required. Evaluation criteria reflected above can be added and or adjusted depending on the requirement and the type of purchase. The final evaluation criteria must be reflected above prior to releasing of this RFP.

CARE will review proposed budgets and pricing after the initial review of the criteria above.*