Request for Proposal

[Consultancy Work]

RFP DOCUMENT # [JL/ 35582]

RFP Issue Date:  22/02/2024]

Proposal submission DEADLINE: [01/03/2024]

CARE SOMALIA/SOMALILAND

ISKUFILAN FAANOOLE

Kismayo, Somalia

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP.

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder.

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of the submitted proposal.

- To award another type of contract other than that described herein, or to award no contract.

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal.

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.A. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Supplier Name: |  |
| --- | --- |
| Title/Designation: |  |
| Company Name: |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All vendors must provide written notification via email to (som.consultant@care.org) of their intent to participate, or not to participate in the bidding process by March 1st, 2024.

Proposals will be accepted until March 1st, 2024. in case you may need any clarification on the TOR you can delivered via email solely to Kenneth Marimira Kenneth.marimira@care,org.] no later than 28/02/2024.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in the proposals must be all-inclusive to include any outsourced or contracted work. Any proposals which call for outsourcing or contracting work must include the name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

CARE is issuing this RFP (Request for Proposal) soliciting qualified bidders to submit proposals intended for A CONFLICT-SENSITIVE GENDER AND SOCIAL INCLUSION ANALYSIS

GASHAAN PROJECT.

This RFP is an invitation to bid, not an offer of contract.  Bidders must submit a response that complies with the minimum requirements contained herein.

# PROJECT OVERVIEW

CARE is seeking a provider to submit proposals intended for the [provide requirement description.

TERMS OF A REFERENCE FOR A CONFLICT-SENSITIVE GENDER AND SOCIAL INCLUSION ANALYSIS GASHAAN PROJECT

Context

Somalia is a country that has gone through decades of conflict, recurrent climate shocks, disease outbreaks that has resulted in widespread displacement, rapid urbanization, food insecurity, and increased poverty. A total of 2.9 million IDPs have been displaced by conflict, insecurity, drought and/or floods.  The conflict and climate related shocks have exacerbated the humanitarian situation of both IDP and host communities, with increased numbers of children married earlier as a coping strategy. Somalia is characterized by structural gender inequalities.  Women continue to experience social discrimination and exclusion due to the strong patriarchal nature, low levels of literacy, limited access to employment opportunities. Women and the youth are generally excluded from leadership positions because of the traditional clan system operational in Somalia. The successive humanitarian crises continue to make Somali women and girls vulnerable to heightened levels of conflict related sexual violence and FGM practices. Sexual and Gender Based Violence (SGBV) is prevalent in many regions, but cases go unreported due to fears of rejection and stigmatization. Many women and girls who have been sexually assaulted may not seek help medical or psychosocial services due to the lack of availability of services and due to the stigma attached to sexual assault.

Background

The GAASHAN Programme (Somali word for shield or protect) aims to provide sustainable and comprehensive humanitarian response and prevention to protection and GBV risks for marginalized and hard to reach communities in humanitarian hotspot areas in South Central Somalia. The project will reach 43,756 direct beneficiaries (10,528 men, 21,533 women, 2,850 boys and 8,845 girls of whom 5% people with disabilities) in 18 districts across 9 regions in South Central Somalia. We will also reach an estimated 117,200 indirect beneficiaries (46,452 men, 59,748 women, 5,000 boys, and 6,000 girls). The target districts have been prioritized as they experience consistently high levels of humanitarian needs and face the compounding effects of conflict and climate-related shocks and stressors, making populations vulnerable to gender based violence (GBV) and abuse. These districts are among the priority locations in the 2023 Somalia Humanitarian Response Plan (HRP) due to the magnitude and severity of needs following the five-season drought. In addition, El Nino is projected during the October to December Deyr rainfall season, resulting in excess rainfall and flooding. There are increased risks of flooding along the main rivers of Juba and Shabelle, leading to displacement, loss of lives, livelihoods and infrastructure, and heightening the risk of disease outbreaks. This threatens to worsen the humanitarian situation in these hotspot areas.

The project will also target locations in newly liberated areas which lack/have low humanitarian service provision, especially for protection and GBV services. The Programme will build on the consortium’s programming experience in delivery of prevention and response services in humanitarian contexts. We will continue targeting the most vulnerable communities who have been impacted by displacement due to conflict and climate-induced shocks, especially in hard to reach or newly accessible areas.

GASHAAN project is a 5-year initiative that seeks to address the needs of women, men girls, and boys for better protection systems against GBV, and child abuse including family separation and child recruitment and receive high-quality response where needed. GASHAAN  works with communities  in Banadir, Hirshabelle, South West, Jubaland and Galmudug to implement an integrated and innovative package of interventions that intend to; 1) Strengthen the capacity of GBV and child protection actors to ensure improved access to and availability of GBV and CP services 2) Empower communities and enhance community-based protection structures effectively to prevent, mitigate, and respond to GBV and child abuse (especially family separation and child recruitment) 3) Strengthen protection monitoring to trigger an effective GBV and child protection response to ensure better protection outcomes. 4) Enhance capacity and collective action amongst women and girls' groups, civil society actors and platforms to advocate for social change and policy reforms that promote gender equality and protection of civilians. GASHAAN target locations consistently experience high levels of humanitarian needs and face the compounding effects of conflict and climate-related shocks and stressors, making populations vulnerable to GBV, abuse and conflict. The consortium works together to carry out community-oriented initiatives to ensure community support and promote the project's long-term viability. The project’s local partners assist communities in reducing and resolving conflict through community-based measures such as dispute resolution, community dialogue sessions, and protection/GBV community awareness programs as they have experience operating in the complex Somali context for many decades and a fundamental component have been the use of conflict sensitive techniques in their operations.

Objective

Somali society is a patriarchal society whose culture is shaped by a fusion of nomadic traditional practices and norms with Islamic teachings. In Somali culture, the clan system defines the identity and affinity of both men and women and serves as the collective memory. According to the 2022 CARE Drought Rapid Gender Assessment 60% of all respondents of the RGA felt that there is no equality among males and females in their communities. Within Somali family systems, men are regarded as central figures of the household responsible for providing for and making decisions for the household therefore men are largely responsible for earning an income through different livelihood initiatives. Meanwhile, based on cultural and social norms, women and girls are primarily responsible for the private sphere within the household that includes caregiving responsibilities. Protection concerns in Somalia stem from acts of violence, exploitation, abuse, oppression, and deprivation, especially in situations of conflict, displacement, and through violations of International Human Rights and International Humanitarian Law. There is a high prevalence of GBV in Somalia and is present in all forms including rape, domestic violence, sexual assault and harassment, trafficking of women, girls and boys and harmful traditional practices including female genital mutilation/cutting, early marriage, bride inheritance and others. GBV primarily – but not exclusively – affects women and girls. Inevitable features of the conflict in Somalia exacerbated by climate induced shocks such as droughts and floods include targeted and indiscriminate physical attacks on civilian and on property, widespread sexual and gender-based violence, child recruitment, arbitrary arrest, forced displacement, evictions, and clan conflicts. However, due to the deeply ingrained conflicts, GBV and social exclusion inclinations in Somalia, that have ever been potential sources of polarization within society or between groups because of the fragility and conflict-affected states and stakeholders. Due to the rigid cultural and traditional roles, Somali societies experience deeply ingrained male dominance culture and social pressures impending women's development and indirectly supporting violence against women among many social groupings. The GASHAAN project will address these challenges by providing sustainable and comprehensive humanitarian response and prevention to protection and GBV risks for marginalized and hard to reach communities in humanitarian hotspot areas in South Central Somalia. The project will draw on the experience and lessons of the CHANGES project phases I and II which used a multi-level approach to transform harmful norms and tackle child, early and forced marriage, GBV and FGM. Previous phases used the ecological model to target adolescent girls and boys, their families, and the wider community, as well as religious leaders, service providers and the wider policy environment, and used targeted conversations and curriculum, economic empowerment, promotion of champions, media, and advocacy to achieve both prevention and response outcomes. Phase III of the project will adapt these approaches to make them appropriate for the humanitarian setting and focus on the most impactful interventions. The project will be inclusive of men, women, girls, and boys (with and without disability) who are at risk of GBV and/or survivors.

The project seeks to engage a consultant for a conflict sensitive gender and social inclusion analysis to inform the project development and implementation and  gather gender-related information especially gender roles, responsibilities, barriers, misconceptions, social norms, policies, stressors and shocks that heighten risks of GBV and support systems available for survivor of gender based violence while taking account prolonged conflict, displacement, violence and social exclusion of women, minorities and other vulnerable groups such as people with disabilities.

Specific Objectives

•	Conduct a detailed conflict-sensitive Gender and Social Inclusion Analysis in conflict and climate-affected target areas.

•	Analyze the gender and social inclusion aspects of conflict-related violence, encompassing the prevalence and various forms of sexual and gender-based violence (SGBV), and their impacts on individuals and communities.

•	Present a comprehensive analysis of areas that should be addressed in delivering services related to protection initiatives that are based on conflict and climate change analysis best practices.

•	Explore the different needs, capacities, levels of participation (both in the private sphere and the public), and coping strategies of specific minority or marginalized groups, including clans or tribes, as well as barriers and opportunities around access to services during and after conflict and climate shocks.

•	Explore the roles and experiences of women, girls and men and WROs in peacebuilding and conflict resolution efforts in Somalia.

•	Identify key protective / AA measures and strategies in place or needed to ensure the safety and well-being of women and children in conflict-affected regions of Somalia and how effective these measures are in practice.

•	Explore cultural and economic factors that influence the differential impacts of climate change on men, women, and marginalized groups in Somalia.

•	Provide concrete and actionable recommendations that inform both the design and implementation process of protection activities and programming based on evidence and established best practices in conflict or environmental shocks affected regions.

Scope of Work:

The scope of the conflict-sensitive Gender and Social Inclusion Analysis will include but not necessarily be limited to the following:

•	Review literature on gender, social inclusion, and conflict in Somalia at large and in the project target regions in particular Banadir ( Hawlwadaag/ Dayniile) Jowhar, Beletweyne, Baidoa, Kismayo, Dollow, Afmadow and South Galkacayo)  including observed and projected impacts of conflict on exuberating gender inequalities; the  extent  of  integration and implementation  of  gender and social inclusion  into  various  key  development  policies,  National/local government  capacity on gender equality and clan conflicts; recognition  of  socio-cultural  dimensions  of  vulnerability,  in  particular  the  power imbalance/dynamics of vulnerability between men and women;

•	Developing and adapting the conflict Inclusive sensitive GESI analysis to analyze the interconnection between gender, social inclusion, and conflict.

•	Develop an inception report that describes the methodology, timeline and includes data collection instruments and tools for feedback and approval.

•	Train/Orient and guide the assessment team to conduct field assessments that are both qualitative and quantitative.

•	Facilitate a reflection workshop to outline recommendations for the design and implementation of project interventions and opportunities to help communities adopt gender-equitable and safe environments for women, girls and socially excluded groups.

•	Finalize GESI analysis report detailing findings, recommendations and share for review and feedback.

•	Presentation and submission of the final validated GESI analysis report to CARE.

Deliverables:

In reference to the scope of work, the consultant team is expected to submit the following:

1.	An inception report including:

•	Methodology

•	Sampling

•	Draft data collection tools

2.	Detailed work plan outlining all tasks to be completed by each of the members of the consultant team.

3.	Data collection protocols

4.	Enumerators’ training plans

5.	Complete clean datasets in Excel

6.	An independent report that provides an analysis of the data

CARE will review all deliverables and provide feedback to the consultant within three business days of receiving the deliverable.

Expected duration of the assignment

The consultancy shall be executed within a maximum of 30 days commencing after signing the contract. The proposal should include a detailed schedule.

Milestone	Deadline dates

Literature/document review / review of project’s theory of change, impact logic 	2

Draft Inception Report submission and finalization 	3

Data Cleaning and Analysis	4

Data collection enumerator training 	4

conflict-sensitive gender and social inclusion analysis Study Data collection	11

Draft report Briefs submitted for review	2

Consultant addresses comments, revises and share final the report 	4

Total	30

Budget

The budget prepared by the consultant should cover all the activities outlined above, including design, data collection, cleaning, analysis, and reporting. This budget is inclusive of all costs covering team member costs, travel, Enumerator training research costs and any other costs associated with the completion of the work including where required costs for reasonable adjustment. The selected consultant is required to organize and fund their own duty of care arrangements as required.

The consultant/s is required to provide a costed proposal in the form of a price schedule that as a minimum should include:

•	Sub-total of fees for the delivery of any task or deliverable.

•	Expenses and overheads broken down by deliverables.

•	Reasonable adjustment costs; and

•	Total costs before and after any taxes that are applicable.

The selected consultant is required to provide a payment schedule based on milestone payments for the successful delivery of each deliverable.

Proposals should include the following:

•	Technical proposal –approach to the study; work plan with milestones; how meet qualifications.

•	Financial proposal

•	CVs of all involved persons

1.	Professional Skills and Qualifications

Qualifications: The selected consultant/s is required to clearly identify and provide CVs for all those proposed in the team, clearly stating their roles and responsibilities for the study.

The proposed person or team should include the technical expertise and practical experience required to deliver the scope of work and outputs, in particular, concerning.

•	Design: the team should include skills and expertise required to design, plan and conduct electronic data collection in fragile contexts, including developing qualitative and quantitative tools.

•	Experience and expertise with studies and research on gender, GBV social inclusion, and conflict in Somalia

•	Relevant subject matter knowledge and experience: at least 5 years of experience required on conducting research with women and girls in conflict areas, gender and social inclusion, socio-cultural practices and beliefs, to ensure that the design and methods are as relevant and meaningful as possible given the aims and objectives of the project and the context in which it is being delivered.

•	Data collection management: manage a data collection process from end-to-end.

•	Country experience: it is particularly important that the team has the appropriate country knowledge /experience and ability to interpret findings from a contextual perspective, as required to conduct the research.

•	Data management and data cleaning.  Ability to supervise the collection, entry (if required), cleaning and management of large data sets.

•	Safety and ethical considerations: Ensuring the whole process adheres to best practice for research with children including the implementation of child protection policy and procedures to ensure safety of participants.

•	Our selection process reflects our commitment to the protection of children from abuse. CARE is a Zero Tolerant organization for child abuse and sexual exploitation and abuses.

Application Procedure

The interested candidates are requested to submit:

•	Technical proposal showing how the consultant intends to carry out the consultancy.

•	Financial proposal

•	Qualifications

•	Relevant experience related to the assignment including samples and references of most recent similar work done.

Submission Information

The deadline for submission is 17:00 time on 1st of March 2024.

Submissions should be emailed to:  SOM.Consultant@care.org

And questions about TOR should be emailed TO Kenneth.marimira@care,org.

| Requirement & Specs | Qty. | Unit of Measurement | Required Delivery Lead Time | Delivery Address | Contract Period |
| --- | --- | --- | --- | --- | --- |

[Provide additional requirements]

| Item # | Other Requirements |  |
| --- | --- | --- |
| 1 | Delivery Date & Time | Bidder shall deliver the goods at least ____ weeks after Contract signature. |
| 2 | Delivery Terms (incoterms) | EXW [Ex-works (Place)] |
|  |  | FCA [Free Carrier (Port)] |
|  |  | FAS [Free Along-Side Ship (Port)] |
|  |  | FOB [Free On-Board (Port)] |
|  |  | CFR [Cost, & Freight (Port)] |
|  |  | CIF [Cost, Insurance & Freight (Port)] |
|  |  | CPT [Carriage Paid-To (Place)] |
|  |  | CIP [Carriage & Insurance Paid-To (Place)] |
|  |  | DAP [Delivered at Place (Place)] |
|  |  | DPU [Delivered at Place Unloaded (Place)] |
|  |  | DDP [Delivered Duty Paid (Place)] |
| 3 | Custom Clearance (Must be linked to Incoterms at origin) | Not Applicable. Shall be done by _______________ |
|  |  | Shouldered by CARE |
|  |  | Supplier/ Bidder |
|  |  | Freight Forwarder |
| 4 | Exact Address(es) of Delivery Location | Please provide addresses |
| 5 | Warranty Period | Standard Manufacturer’s Warranty (if applicable) |
| 6 | Payment Terms | 30 Days upon Receipt of items |
| 7 | Quotation Validity | The quote needs to be valid for 90 days to cover all the days from bidding up to the award process. However, once the contract has been released, it shall be valid for the same coverage as reflected in the requirement above. |

[Provide additional requirements]

# PROJECT TIMELINE

All bidders are advised to strictly follow the below timeline as noted.

Any technical questions arising during the preparation of your response to this RFP should be submitted in writing via email to [Kenneth.marimira@care,org) no later than 21/02/2024.

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible | Remarks |
| --- | --- | --- | --- |
| RFP Issued | 22/02/2024 | CARE |  |
| Supplier to notify CARE of intention to participate in bidding |  | Supplier | Deadlines must be strictly observed. |
| Deadline for submission of clarification questions to CARE | 28/02/2024 | Supplier | Deadlines must be strictly observed. |
| CARE to answer all clarifications | 29/02/2024 | CARE | Deadlines must be strictly observed. |
| Supplier’s Deadline of Submission of Proposal | 01/03/2024 | Supplier | Deadlines must be strictly observed. |
| Evaluation of Proposal |  | CARE |  |
| Vendor presentation (if required) |  | Supplier |  |
| Finalists selected |  | CARE | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

# PROJECT REQUIREMENTS

- Technical Requirements

a.1 Technical Proposal of the Product

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Overall Proposal Suitability |  |  |
| 1 | Please see the Scope of Work and any other required specifications for this project. |  |
| 2 | Provide Delivery Lead Time |  |
| 3 | Provide after-sales service (if applicable) |  |
| 4 | Ability to provide sample (if applicable) |  |
| 5 | Provide Warranty Period |  |
|  | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Previous Works and Awards |  |  |
| 1 | Provide 3 or more client experiences or testimonials (References whose environment, size, and scope are most similar to CARE. Include a summary of the work completed for each account. Include reference contact names, with telephone numbers and email addresses.) |  |
| 2 | Provide previous records of performance and service. |  |
| 3 | Provide citations and awards. This encompasses reviewing the citations and awards a vendor has received from other customers and award-giving bodies. |  |
| 4 | Provide any testimonials, survey response/s from previous buyers and/or partners. |  |
| 5 | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Technical Expertise and Organizational Experience |  |  |
| 1 | Provide 5 Availability of vendor’s representatives to call upon and consult with. |  |
| 2 | Any proof that the vendor has the Ability to render satisfactory service in this instance. |  |
| 3 | Provide Years of experience in providing the same requirement to other companies. |  |
| 4 | Provide the latest audited Financial Statement |  |
| 5 | (Any additional requirement that is deemed necessary for “Technical Expertise and Organizational Experience. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Others |  |  |
| 1 | Provide any relative requirements which were not mentioned above. (delete if not applicable) |  |

- VALUE & COST (Financial Requirements)

(Provide below requirements, payment terms, etc., if there’s any)

See attached template (in Excel File) to be used for your financial bid.

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

# EVALUATION CRITERIA

CARE will evaluate all proposals based on the following criteria.  To ensure consideration for this Request for Proposal, your proposal should be complete and include all of the following criteria:

- Overall Proposal Suitability: proposed solution(s) must meet the scope and needs included herein and be presented in a clear and organized manner

- Previous Work and Awards: Bidders will be evaluated on examples of their work pertaining to the requirement as well as client testimonials and references.

- Technical Expertise and Organizational Experience: Bidders must provide descriptions and documentation of staff technical expertise and experience. Bidders also need to provide their experiences as an organization which include but not limited to years of experiences, financial stability, expertise, and edge to other competitors.

- Value and Cost: Bidders will be evaluated on the cost of their solution(s) based on the work to be performed in accordance with the scope of this project.

Note for Country Offices (CO): The specific criteria must closely represent the objective and scope given the nature of the procurement required. Evaluation criteria reflected above can be added and or adjusted depending on the requirement and the type of purchase. The final evaluation criteria must be reflected above prior to releasing of this RFP.

CARE will review proposed budgets and pricing after the initial review of the criteria above. *