Request for Proposal

[Third Party Monitoring Services for CARE Somalia’s ADOLESCENT GIRLS’ EDUCATION IN SOMALIA (AGES) PROJECT ]

RFP DOCUMENT # [35787]

RFP Issue Date:  04/03/2024]

Proposal submission Deadline :  [15/03/2024]

CARE USA

151 Ellis Street NE

Atlanta, GA 30303-2440

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of submitted proposal

- To award another type of contract other than that described herein, or to award no contract;

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions, and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.A. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Supplier Name: |  |
| --- | --- |
| Title/Designation: |  |
| Company Name: |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All vendors must provide written notification via email to (Som.consultant@care.org) of their intent to participate, or not to participate in the bidding process by [March-15th  2024

.

Proposals will be accepted until March-15th  2024  if you  may need any clarification on the TOR you can  delivered via email solely to Paul Odhiambo <Paul.Odhiambo@care.org> ] , no later than 07/03/2024.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in proposals must be all-inclusive to include any outsourced or contracted work.  Any proposals which call for outsourcing or contracting work must include a name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

# CARE is issuing this RFP (Request for Proposal) soliciting qualified bidders to submit proposals intended for the [Third Party Monitoring Services for CARE Somalia’s ADOLESCENT GIRLS’ EDUCATION IN SOMALIA (AGES) PROJECT

].

This RFP is an invitation to bid, not an offer of contract.  Bidders must submit a response that complies with the minimum requirements contained herein.

# PROJECT OVERVIEW

CARE is seeking a provider to submit proposals intended for the [provide requirement description]

# Terms of Reference

# Third Party Monitoring Services for CARE Somalia’s ADOLESCENT GIRLS’ EDUCATION IN SOMALIA (AGES) PROJECT

# 1. SUMMARY

CARE Somalia is seeking to procure the services of a consultant or team of consultants to conduct third party monitoring of the Adolescent Girls’ Education in Somalia (AGES) project. AGES is jointly funded by United Kingdom’s (UK) Foreign Commonwealth and Development Office (FCDO) and United States Agency for International Development (USAID) through the FCDO’s Girls’ Education Challenge (GEC) initiative.

The consultant/s will be contracted to be responsible for the design and execution of third party monitoring including the preparation and refinement of tools as required and manage data collection.

2. BACKGROUND TO THE AGES PROJECT

Operating in Somalia since 1981, CARE currently works through three main programs: the first, CARE’s rural vulnerable women’s program supports poor rural women and girls in addressing long term underlying causes of poverty and vulnerability, addressing social, economic, cultural and political obstacles to positive change. We help women and girls improve their economic status, access education and support them to play a greater role in local leadership and conflict resolution. Our second program area, the youth program, focuses on job creation and livelihood opportunities for poor youth through e.g. secondary education, vocational training, small business development, and microfinance. Thirdly, our emergency program provides direct humanitarian relief to victims of drought and conflict in Puntland, Mogadishu, and Lower Juba. CARE has its main offices in Hargeisa, Garowe, Mogadishu and Erigavo, and satellite offices in Burao, El Afweyn, Kismayo and Bossaso. We work with a large number of local partners and maintain excellent relations with local governments.

Adolescent Girls’ Education in Somalia (AGES) project is a long-term project funded by both FCDO and USAID which aims to improve learning outcomes and positive transitions for ultra-marginalized adolescent girls in the Banaadir Regional Administration, Hirshebele, Jubaland, and South West States of Somalia. The project is targeting over 80,475 ultra-marginalised and out‐of‐school girls to enrol in formal education, accelerated education, or non‐formal education classes. The FCDO component targets 42,000 girls across the 3 pathways; Formal Education (FE), None Formal Education (NFE) and Accelerated Basic Education (ABE) while the USAID component targets 38475 girls with Non Formal Education. The project also indirectly benefits 14,000 boys enrolled in targeted formal schools. The project works with teachers, participatory governance mechanisms (Community Education Committees (CECs)), parents/caregivers, and education officials to address barriers to girls’ attendance, retention, and learning. AGES is also supporting schools and learning centres to implement activities to develop student leadership skills and financial literacy and to improve girl’s knowledge of reproductive health and menstrual health management.

Furthermore, the project’s objectives include but are not limited to the expansion of critical life skills around finances to prompt girls to stay in school, re-enrol in school, enrol in alternative education, or move into meaningful and dignified employment opportunities. Given the context and the barriers girls in the targeted areas face, the project takes a multidimensional approach while addressing these key barriers affecting most marginalized girls. At the individual and household levels, the project is sponsoring Village Savings and Loans (VSL) groups; providing bursaries to 959 girls with disability; providing girls with essential life skills related to resilience building and socioemotional learning through Girls’ Empowerment Forums (GEFs); mentoring boys through parallel Boys’ Empowerment Forums, and sensitizing mothers to pro-education norms, especially for girls and learners with disabilities. At the community level, religious leaders have been mobilized to advocate for inclusive education and trained on Islamic principles that emphasize gender equality and girls’ education, delivering pro-education messaging through radio and social media.

3. THIRD PARTY MONITORING PURPOSE AND DESIGN

Monitoring Objective

Conduct a monitoring exercise in hard-to-reach locations to identify potential gaps in activity implementation. Monitoring findings will be used to verify program implementation and quality in hard to reach project locations.

Data collection locations and sampling

The Third Party Monitoring will only target the USAID component in the hard to reach project locations

The distribution of learning centers, facilitators and enrolled girls in the targeted hard-to-reach NFE centers across the three zones and districts is given in the table below.

| District / zone | Learning centers | Facilitators | Enrolled girls |
| --- | --- | --- | --- |
| South West | 19 | 60 | 2700 |
| Afgoye | 8 | 30 | 1375 |
| Walanwayn | 8 | 21 | 936 |
| Diinsor | 3 | 9 | 389 |
| Hirshabelle | 15 | 45 | 2095 |
| Balcad | 5 | 15 | 675 |
| Jowhar | 8 | 24 | 1149 |
| Mahaday | 2 | 6 | 271 |
| TOTAL | 34 | 104 | 4795 |

For the purposes of this third party monitoring, the following sample size is expected:

- All learning centers (34) to be surveyed

- One facilitator randomly selected from each learning center surveyed (34 total, 33% of full sample)

- 10 girls randomly selected from each learning center surveyed (340 total, 7.0% of full sample)

Data Collection Methods

The primary data collection method will be through school visits and interviews will be conducted with respondents in all the target locations to assess;

- Attendance vis-à-vis learners’ enrollment

- Whether the facilitator is the correct facilitator and they are receiving stipends

- Practices with 10 girls randomly selected at each of the 34 locations.

- Existence and functionality of Village Savings and Loans Associations (VSLA) groups

- Existence and functionality of Girls Empowerment Forums (GEFs)

Data to be collected

Data will be collected with NFE learners (girls) and facilitators.

- With learners:

- Enrolment data vs presence in class (e.g. potential for presence of non-registered learners; number of dropouts)

- Attendance data

- Participation in GEF meetings and VSLAs

- Experience / witnessing of any form of verbal and physical abuse

- Knowledge of FCRM mechanisms

- Impact of the floods

- Facilitators’ attendance

- With NFE facilitators

- Records of formative assessment – only for in

- Attendance register/tracking – only for in

- Verifying the facilitator surveyed is the actual facilitator

- Verifying whether facilitators are receiving stipends

- Verifying the existence of VSLA groups (number of groups for cohort 6, number of members for each group, names of the groups, the group officials)

- Verifying the existence of GEF groups (number of groups for cohort 6, number of members for each group, names of the groups, the group officials)

Ethical protocols

The monitoring must consider the safety of participants and especially children at all stages of the data collection. The selected consultant/s will need to demonstrate how they have considered the protection of children through the different data collection stages, including recruitment and training of enumerators, data collection and data entry/storage.

The selected consultant/s is required to set out their approach to ensuring complete compliance with international good practice with regards to research ethics and protocols particularly with regards to safeguarding children, vulnerable groups (including people with disabilities) and those in fragile and conflict affected states. Consideration should be given to:

- administrative, technical and physical safeguards to protect the confidentiality of those participating;

- physical safeguards for those conducting research;

- data protection and secure maintenance procedures for personal information;

- parental consent concerning data collection from children or collation of data about children;

- age- and ability-appropriate assent processes based on reasonable assumptions about comprehension for the ages of children and the disabilities they intend to involve in the research; and

- Age-appropriate participation of children, including in the development of data collection tools.

Risk and risk management

Risk management plan: It is important that the successful bidder has taken all reasonable measures to mitigate any potential risk to the delivery of the required outputs for this monitoring. Therefore, the selected company / consultant once contracted will be required to submit a risk management plan covering:

- the assumptions underpinning the successful completion of the proposals submitted and the anticipated challenges that might be faced;

- estimates of the level of risk for each risk identified;

- proposed contingency plans that the bidder will put in place to mitigate against any occurrence of each of the identified risk;

- specific child protection risks and mitigating strategies, including reference to the child protection policy and procedures that will be in place; and

- Health and safety issues that may require significant duty of care precautions.

Professional Skills and Qualifications

Qualifications: the selected consultant/s is required to clearly identify and provide CVs for all those proposed in the team, clearly stating their roles and responsibilities for this monitoring.

The proposed person or team should include the technical expertise and practical experience required to deliver the scope of work and outputs, in particular, with regards to:

- Design: the team should include skills and expertise required to design, plan and conduct electronic data collection in fragile contexts;

- Experience with the implementation of phone surveys in Somalia;

- Relevant subject matter knowledge and experience: knowledge and experience required on conducting research with children and adolescents, the education sector, disability and gender to ensure that the design and methods are as relevant and meaningful as possible given the aims and objectives of the project and the context in which it is being delivered;

- Data collection management: manage a data collection process from end-to-end;

- Country experience: it is particularly important that the team has the appropriate country knowledge /experience and ability to interpret findings from a contextual perspective, as required to conduct the research;

- Data management and data cleaning. Ability to supervise the collection, entry (if required), cleaning and management of large data sets.

- Safety and ethical considerations: Ensuring the whole process adheres to best practice for research with children including the implementation of child protection policy and procedures to ensure safety of participants.

Day–to–day project management of the monitoring will be the responsibility of the M&E and Knowledge Manager, AGES project/ CARE Somalia.

Expected duration of the assignment

- The successful bidder is expected to conduct two rounds of third party monitoring with the first round in March/April and the second round in May/June 2024

- The expected duration of each round of third party monitoring is one and a half months.

- Each round of the third party monitoring will be treated as a separate assignment and the costing of the bid should therefore be for one round

Deliverables and Schedule

- Expected Tasks

- Review the project’s MEL framework and monitoring reports;

- Submit an inception report (draft and final), that outlines the monitoring methodology, including data collection tools and detailed work plan outlining all tasks to be completed by each of the members of the team;

- Finalization of tools, including back-translation where required;

- Enumerator training on data collection tools and their application;

- Collect data according to work plan

- Validate all datasets and collate data as necessary for analysis;

- Submit a final report analyzing the results of the data.

Deliverables

In reference to the scope of work above, the consultant team led by a quantitative research expert is expected to accomplish and submit the following:

- An inception report including:

- Monitoring methodology including the sampling methodology

- Draft data collection tools,

- Detailed work plan outlining all tasks to be completed by each of the members of the consultant team for the duration of the baseline.

- Data collection protocols;

- Enumerators training plans;

- Complete clean datasets in Excel;

- An independent report that provides an analysis of the data

The consultant/s will be expected to identify a Project Director for communication and reporting purposes. At the Inception meeting the Evaluation Team Project Manager will be expected to submit a full contact list of all those involved in the data collection.

Budget

The budget prepared by the consultant/s should cover all the activities outlined above, including design, data collection, cleaning, analysis and reporting. This budget is inclusive of all costs covering team member costs, travel, research costs and any other costs associated with the completion of the work including where required costs for reasonable adjustment. The selected consultant is required to organize and fund their own duty of care arrangements as required.

The consultant/s is required to provide a fully costed proposal in the form of a price schedule that as a minimum should include:

- Sub-total of fees for the delivery of any task or deliverable;

- Sub-total for number of days per partner organization (as applicable);

- Expenses and overheads broken down by the project cost categories;

- Reasonable adjustment costs; and

- Total costs before and after any taxes that are applicable.

The selected consultant/s are required to provide a payment schedule on the basis of milestone payments for the successful delivery of each deliverable.

Proposals should include the following:

- Technical proposal –approach to the monitoring; work plan with milestones; how meet qualifications.

- Financial proposal

- CVs of all involved persons

Submission Information

- The deadline for submission is 15/03/2024

- The submission should be emailed to:  Som.consultant@care.org

- Questions about TOR should be sent to  Paul.Odhiambo@care.org

- Please note that only questions about ToR should be sent to Paul.Odhiambo@care.org not the bid submission. All bid documents should be submitted through Som.consultant@care.org

| Requirement & Specs | Qty. | Unit of Measurement | Required Delivery Lead Time | Delivery Address | Contract Period |
| --- | --- | --- | --- | --- | --- |

[Provide additional requirements]

| Item # | Other Requirements |  |
| --- | --- | --- |
| 1 | Delivery Date & Time | Bidder shall deliver the goods at least ____ weeks after Contract signature. |
| 2 | Delivery Terms (incoterms) | EXW [Ex-works (Place)] |
|  |  | FCA [Free Carrier (Port)] |
|  |  | FAS [Free Along-Side Ship (Port)] |
|  |  | FOB [Free On-Board (Port)] |
|  |  | CFR [Cost, & Freight (Port)] |
|  |  | CIF [Cost, Insurance & Freight (Port)] |
|  |  | CPT [Carriage Paid-To (Place)] |
|  |  | CIP [Carriage & Insurance Paid-To (Place)] |
|  |  | DAP [Delivered at Place (Place)] |
|  |  | DPU [Delivered at Place Unloaded (Place)] |
|  |  | DDP [Delivered Duty Paid (Place)] |
| 3 | Custom Clearance (Must be linked to Incoterms at origin) | Not Applicable. Shall be done by _______________ |
|  |  | Shouldered by CARE |
|  |  | Supplier/ Bidder |
|  |  | Freight Forwarder |
| 4 | Exact Address(es) of Delivery Location | Please provide addresses |
| 5 | Warranty Period | Standard Manufacturer’s Warranty (if applicable) |
| 6 | Payment Terms | 30 Days upon Receipt of items |
| 7 | Quotation Validity | The quote needs to be valid for 90 days to cover all the days from bidding up to the award process. However, once the contract has been released, it shall be valid for the same coverage as reflected in the requirement above. |

[Provide additional requirements]

# PROJECT TIMELINE

All bidders are advised to strictly follow the below timeline as noted.

Any technical questions arising during the preparation of your response to this RFP should be submitted in writing via email to [Paul.Odhiambo@care.org) no later than [04/02/2024.

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible | Remarks |
| --- | --- | --- | --- |
| RFP Issued | 04/03/2024 | CARE |  |
| Supplier to notify CARE of intention to participate in bidding |  | Supplier | Deadlines must be strictly observed. |
| Deadline for submission of clarification questions to CARE | 07/03/2024 | Supplier | Deadlines must be strictly observed. |
| CARE to answer all clarifications | 10/03/2024 | CARE |  |
| Supplier’s Deadline of Submission of Proposal | 15-03/2024 | Supplier | Deadlines must be strictly observed. |
| Evaluation of Proposal |  | CARE |  |
| Vendor presentation (if required) |  | Supplier |  |
| Finalists selected |  | CARE | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

# PROJECT REQUIREMENTS

- Technical Requirements

a.1 Technical Proposal of the Product

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Overall Proposal Suitability |  |  |
| 1 | Please see the Scope of Work and any other required specifications for this project. |  |
| 2 | Provide Delivery Lead Time |  |
| 3 | Provide after-sales service (if applicable) |  |
| 4 | Ability to provide sample (if applicable) |  |
| 5 | Provide Warranty Period |  |
|  | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Previous Works and Awards |  |  |
| 1 | Provide 3 or more client experiences or testimonials (References whose environment, size, and scope are most similar to CARE. Include a summary of the work completed for each account. Include reference contact names, with telephone numbers and email addresses.) |  |
| 2 | Provide previous records of performance and service. |  |
| 3 | Provide citations and awards. This encompasses reviewing the citations and awards a vendor has received from other customers and award-giving bodies. |  |
| 4 | Provide any testimonials, survey response/s from previous buyers and/or partners. |  |
| 5 | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Technical Expertise and Organizational Experience |  |  |
| 1 | Provide 5 Availability of vendor’s representatives to call upon and consult with. |  |
| 2 | Any proof that the vendor has the Ability to render satisfactory service in this instance. |  |
| 3 | Provide Years of experience in providing the same requirement to other companies. |  |
| 4 | Provide the latest audited Financial Statement |  |
| 5 | (Any additional requirement that is deemed necessary for “Technical Expertise and Organizational Experience. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Others |  |  |
| 1 | Provide any relative requirements which were not mentioned above. (delete if not applicable) |  |

- VALUE & COST (Financial Requirements)

(Provide below requirements, payment terms, etc., if there’s any)

See attached template (in Excel File) to be used for your financial bid.

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

# EVALUATION CRITERIA

CARE will evaluate all proposals based on the following criteria.  To ensure consideration for this Request for Proposal, your proposal should be complete and include all of the following criteria:

- Overall Proposal Suitability: proposed solution(s) must meet the scope and needs included herein and be presented in a clear and organized manner

- Previous Work and Awards: Bidders will be evaluated on examples of their work pertaining to the requirement as well as client testimonials and references

- Technical Expertise and Organizational Experience: Bidders must provide descriptions and documentation of staff technical expertise and experience. Bidders also need to provide their experiences as an organization which include but not limited to years of experiences, financial stability, expertise, and edge to other competitors.

- Value and Cost: Bidders will be evaluated on the cost of their solution(s) based on the work to be performed in accordance with the scope of this project.

Note for Country Offices (CO): The specific criteria must closely represent the objective and scope given the nature of the procurement required. Evaluation criteria reflected above can be added and or adjusted depending on the requirement and the type of purchase. The final evaluation criteria must be reflected above prior to releasing of this RFP.

CARE will review proposed budgets and pricing after the initial review of the criteria above.*