Request for Proposal

Terms of Reference for Mapping and capacity assessment support to Local NGO Partners

RFP DOCUMENT # [0000036851]

RFP Issue Date: [ 11TH September     2024]

Proposal submission DEADLINE: [ 25th  September -2024]

CARE USA

151 Ellis Street NE

Atlanta, GA 30303-2440

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP.

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder.

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of the submitted proposal.

- To award another type of contract other than that described herein, or to award no contract.

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal.

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest, or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.A. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Supplier Name: |  |
| --- | --- |
| Title/Designation: |  |
| Company Name: |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All vendors must provide written notification via email to som.consultant@care.org  of their intent to participate, or not to participate in the bidding process on 25th September 2024.

Proposals will be accepted until 11:59 PM EST on 25th  September   2024.

delivered via email solely to som.consultant@care.org, no later than the above specified date.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in the proposals must be all-inclusive to include any outsourced or contracted work.  Any proposals which call for outsourcing or contracting work must include the name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

CARE is issuing this RFP (Request for Proposal) soliciting qualified bidders to submit proposals intended Terms of Reference for Mapping and capacity assessment support to Local NGO Partners

1. Introduction

The Somali NGO Consortium (SNC) is a membership organization of national and international NGOs (with 120 member NGOs by end of 2023) that work together to create an enabling environment for the efficient and effective delivery of humanitarian and development assistance to Somali communities. The operating environment in Somalia is highly challenging and complex, due to recurrent climate related shocks, continuing conflict, weak governance, and restricted humanitarian access to populations in need. Some of our members continue to have challenges putting in place robust institutional structures for administrative and operational compliance on programming, targeting, finance & grants management, networking / coordination and reporting. This has limited their chances of accessing funding as well as  meaningful engagement in mainstream (IASC) coordination and decision making processes. Particularly,  Minority Rights Organizations (MROs) and Women Led national NGOs.

The Somali NGO Consortium (SNC) continues to facilitate inclusive dialogues and engagements between international and national member NGOs on critical pragmatic and operational issues across Somalia and Somaliland. SNC has offices in Somalia (Mogadishu, Garowe, Kismayo, Baidoa and Dhusamareeb) and in Somaliland we have an office in Hargeisa. The Consortium currently has over 120 members working across Somalia and Somaliland.

The number of organizations in Somalia continue to grow with 405 operating partners (national and international NGOs) reported in 18 regions in 73 districts. For effective continued support and advocating for national NGOs (including women-led NGOs and MROs), there is need to get updated mapping of national NGOs (especially MROs and Women-led national NGOs) across Somalia and Somaliland.

Submit a response that complies with the minimum requirements contained herein.

| Item # | Other Requirements |  |
| --- | --- | --- |
| 1 | Delivery Date & Time | Bidder shall deliver the service at least _30 days after Contract signature. |
| 2 | Delivery Terms (incoterms) | EXW [Ex-works (Place)] |
|  |  | FCA [Free Carrier (Port)] |
|  |  | FAS [Free Along-Side Ship (Port)] |
|  |  | FOB [Free On-Board (Port)] |
|  |  | CFR [Cost, & Freight (Port)] |
|  |  | CIF [Cost, Insurance & Freight (Port)] |
|  |  | CPT [Carriage Paid-To (Place)] |
|  |  | CIP [Carriage & Insurance Paid-To (Place)] |
|  |  | DAP [Delivered at Place (Place)] |
|  |  | DPU [Delivered at Place Unloaded (Place)] |
|  |  | DDP [Delivered Duty Paid (Place)] |
| 3 | Custom Clearance (Must be linked to Incoterms at origin) | Not Applicable. Shall be done by _______________ |
|  |  | Shouldered by CARE |
|  |  | Supplier/ Bidder |
|  |  | Freight Forwarder |
| 4 | Exact Address(es) of Delivery Location | Please provide addresses |
| 5 | Warranty Period | Standard Manufacturer’s Warranty (if applicable) |
| 6 | Payment Terms | 30 Days upon Receipt of items |
| 7 | Quotation Validity | The quote needs to be valid for 90 days to cover all the days from bidding up to the award process. However, once the contract has been released, it shall be valid for the same coverage as reflected in the requirement above. |

# PROJECT TIMELINE

All bidders are advised to strictly follow the below timeline as noted.

Any technical questions arising during the preparation of your response to this RFP should be submitted in writing via email(program.specialist@somalingoconsortium.org) to no later than 18th September 2024

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible | Remarks |
| --- | --- | --- | --- |
| RFP Issued | September 10 2024 | CARE |  |
| Terms of Reference for Mapping and Capacity Assessment Support to Local NGO Partners | 25th September 2024, | Supplier | Deadlines must be strictly observed. |
| Deadline for submission of clarification questions to CARE | 18th September 2024 | Supplier | Deadlines must be strictly observed. |
| CARE to answer all clarifications | 19th September 2024 | CARE |  |
| Supplier’s Deadline of Submission of Proposal | 25th September 2023 | Supplier | Deadlines must be strictly observed. |
| Finalists selected | n/a | CARE | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

# PROJECT REQUIREMENTS

- Technical Requirements

a.1 Technical Proposal of the Product

See below TOR

Terms of Reference for Mapping and capacity assessment support to Local NGO Partners

1. Introduction

The Somali NGO Consortium (SNC) is a membership organization of national and international NGOs (with 120 member NGOs by end of 2023) that work together to create an enabling environment for the efficient and effective delivery of humanitarian and development assistance to Somali communities. The operating environment in Somalia is highly challenging and complex, due to recurrent climate related shocks, continuing conflict, weak governance, and restricted humanitarian access to populations in need. Some of our members continue to have challenges putting in place robust institutional structures for administrative and operational compliance on programming, targeting, finance & grants management, networking / coordination and reporting. This has limited their chances of accessing funding as well as  meaningful engagement in mainstream (IASC) coordination and decision making processes. Particularly,  Minority Rights Organizations (MROs) and Women Led national NGOs.

The Somali NGO Consortium (SNC) continues to facilitate inclusive dialogues and engagements between international and national member NGOs on critical pragmatic and operational issues across Somalia and Somaliland. SNC has offices in Somalia (Mogadishu, Garowe, Kismayo, Baidoa and Dhusamareeb) and in Somaliland we have an office in Hargeisa. The Consortium currently has over 120 members working across Somalia and Somaliland.

The number of organizations in Somalia continue to grow with 405 operating partners (national and international NGOs) reported in 18 regions in 73 districts. For effective continued support and advocating for national NGOs (including women-led NGOs and MROs), there is need to get updated mapping of national NGOs (especially MROs and Women-led national NGOs) across Somalia and Somaliland.

2. Objectives

The SNC has received funding from the World Food Program (WFP) Somalia in a project titled “Partner Coordination and Capacity Strengthening” which has the following outcome areas:

- To strengthen the capacity of Somali NGO Consortium in achieving its objectives as a national platform for NGOs – as part of the localization agenda by investing on an existing national platform.

- To improve presence, leadership and influence of national NGOs (including women-led and minority rights organizations) in humanitarian leadership, coordination and advocacy.

- To improve support and institutional capacity strengthening for national NGOs (including women-led and minority rights organizations) for efficient and effective humanitarian response.

- To enhance collaboration and efficiency among partner organizations by developing and implementing strategies for effective coordination, and by strengthening their capacities through targeted training and resource support,

- Through this project, the SNC intends to conduct a mapping exercise of national NGOs (particularly WFP partners, MROs and women-led national NGOs) across Somalia and Somaliland. This exercise will be conducted in two phases:

- Mapping of national NGOs (WFP partners, MROs and women-led national NGOs) across Somalia and Somaliland.

- Broad capacity analysis / assessment of MROs and women-led national NGOs using SPAT tool.

Phase 1

The primary objective of this mapping exercise is to:

- Identify which local NGOs are members of the Somali NGO Consortium and determine which of these members are also partners of the World Food Program (WFP), identify NGOs that are not members of the SNC but are partners of the WFP.

- Establish how many of these are women-led and Minority Rights Organizations.

- Map the geographical and thematic distribution of these NGOs.

- Establish how many of these are actively partnered with other UN agencies.

- To identify and assess the strengths, weaknesses, and gaps within the current partner network and their capabilities, in order to develop a strategic plan for optimizing coordination and enhancing their overall effectiveness and impact in achieving project goals."

Phase two

The second phase of this activity will be to support women-led and Minority Rights Organizations to carry out an organizational capacity assessment using the SNC Harmonized Standardized Partnership capacity Assessment tool, generate results, establish an analysis of the capacity gaps and capacity improvement plan for each women-led and Minority Rights Organizations and lastly support these organizations to enroll and utilize the UN Partner Portal,

3. Scope of Work- Phase One

The consultant will be responsible for the following tasks:

3.1 Data Collection and Analysis

- Identify Membership: Compile a comprehensive list of local NGOs that are members of the Somali NGO Consortium.

- WFP Partnerships: Determine which of these members are also partners of the World Food Program (WFP).

- Non-Member Partners: Identify local NGOs that are partners of the WFP but are not members of the SNC.

- Women-Led and Minority Rights Organizations: Identify and categorize NGOs that are led by women and those focused on minority rights.

- Geographical and thematic Disposition: Map the geographical distribution of these NGOs across Somalia, noting areas of operation and regional presence.

- UN Agency Partnerships: Identify any additional partnerships these NGOs have with other UN agencies and international organizations.

3.2 Data Verification

- Cross-check data with existing records from the SNC, WFP, government’s NGO registration documents / records and other relevant databases.

- Conduct interviews or surveys with NGO representatives to verify and gather additional information.

3.3 Scope of Work Phase Two

- Have an understanding of the utility of the SNC harmonized standardized Capacity Assessment tool (SPAT)

- Support the mapped-out women-led and minority rights organizations to perform an organizational assessment using the SPAT, generate an objective score and capacity gap analysis

- Support the organizations to enroll on the UN Partner Portal.

3.3 Reporting

- Compile the collected data into a comprehensive report.

- Provide visual representations such as maps, charts, and graphs to illustrate findings.

- Highlight key insights, trends, and potential areas for further collaboration.

- Deliver a well-organized report summarizing the findings, including visual aids such as charts or maps to illustrate key points.

4. Deliverables

The consultant will deliver the following:

- Inception Report: Outline the methodology, work plan, and timeline for the mapping exercise.

- Draft Report: A preliminary report containing initial findings and data analysis.

- Final Report: A comprehensive report detailing the mapping results, including visual aids and recommendations. The report should outline the current state of partner coordination and capacity, and suggest strategies for enhancing these areas.

- Presentation: A PowerPoint presentation summarizing the key findings and recommendations, to be presented to the SNC and stakeholders.

5. Timeline

The entire mapping exercise is expected to be completed within [6 weeks] from the date of commencement. Key milestones include:

- Week 1 & 2: Inception phase, including meetings with SNC representatives and review of existing data.

- Week 3 & 5: Data collection and verification & deployment of SPAT

- Week 4 - 5: Real time data analysis and draft report preparation.

- Week 6: Review and feedback on the draft report- Final report and presentation.

6. Qualifications and Experience

The consultant or consultancy firm should possess the following qualifications:

- At least a bachelor’s degree in development studies, business related course, international relations or related field.

- Proven experience in conducting mapping, capacity assessment and analysis of actors and stakeholders within a humanitarian context. Include in the application at-least 2 samples of similar work done within the last five years.

- Demonstrated strong understanding of the humanitarian and development landscape in Somalia, including coordination platforms.

- Demonstrated expertise in data collection, analysis, and reporting.

- Excellent communication and interpersonal skills for engaging with various stakeholders.

- Ability to deliver high-quality reports and presentations within the stipulated time-frame.

- Analytical and problem solving skills.

- Understanding of contextual dynamics in terms of diversity, inclusion and cultural sensitivity.

- Proficiency in GIS and mapping applications.

How to Apply

Candidates interested in the position should send their applications online to  som.consultant@care.org to be received no later than 25th September 2024. The application should be titled “Terms of Reference for Mapping and Capacity Assessment Support to Local NGO Partners."

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days after service delivery) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

CARE will review proposed budgets and pricing after the initial review of the criteria above.*