Request for Proposal

Undertake study to determine the impact of school feeding programs currently active in 25 primary schools within Somaliland's Tog-dheer, Marodi-Jeex, and Sanaag regions, focusing on their influence on pupil enrollment, retention, and scholastic performance.

prf number [som01-0000037796]

rfp issue date: [april30th, 2025]

proposal submission deadline: [may 6TH, 2025]

CARE USA

151 Ellis Street NE

Atlanta, GA 30303-2440

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome, and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP.

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder.

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of the submitted proposal.

- To award another type of contract other than that described herein, or to award no contract.

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal.

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by the vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be a reason for disqualification.  CARE, at their discretion, reserves the right to request a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those people directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such a time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest, or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.A. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance of the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Supplier Name: |  |
| --- | --- |
| Title/Designation: |  |
| Company Name: |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All vendors must provide written notification via email to som.consultant@care.org  of their intent to participate, or not to participate in the bidding process on May 6th, 2025

Proposals will be accepted until May 6th, 2025, and deliver to som.consultant@care.org, no later than the above specified date.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in the proposals must be all-inclusive to include any outsourced or contracted work.  Any proposals which call for outsourcing or contracting work must include the name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning candidate for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

CARE is issuing this RFP (Request for Proposal) soliciting qualified bidders to submit proposals intended

| Item # | Other Requirements |  |
| --- | --- | --- |
| 1 | Delivery Date & Time | Bidder shall deliver the service at least ___________________ after Contract signature. |
| 2 | Delivery Terms (incoterms) | EXW [Ex-works (Place)] |
|  |  | FCA [Free Carrier (Port)] |
|  |  | FAS [Free Along-Side Ship (Port)] |
|  |  | FOB [Free On-Board (Port)] |
|  |  | CFR [Cost, & Freight (Port)] |
|  |  | CIF [Cost, Insurance & Freight (Port)] |
|  |  | CPT [Carriage Paid-To (Place)] |
|  |  | CIP [Carriage & Insurance Paid-To (Place)] |
|  |  | DAP [Delivered at Place (Place)] |
|  |  | DPU [Delivered at Place Unloaded (Place)] |
|  |  | DDP [Delivered Duty Paid (Place)] |
| 3 | Custom Clearance (Must be linked to Incoterms at origin) | Not Applicable. Shall be done by _______________ |
|  |  | Shouldered by CARE |
|  |  | Supplier/ Bidder |
|  |  | Freight Forwarder |
| 4 | Exact Address(es) of Delivery Location | Please provide addresses which are outlined in the above TOR |
| 5 | Warranty Period | Standard Manufacturer’s Warranty (if applicable) |
| 6 | Payment Terms | 30 Days upon Receipt of items |
| 7 | Quotation Validity | The quote needs to be valid for 90 days to cover all the days from bidding up to the award process. However, once the contract has been signed, it shall be valid for the same coverage as reflected in the requirement above. |

# PROJECT TIMELINE

All bidders are advised to strictly follow the timeline below as noted.

Any technical questions arising during the preparation of your response to this RFP should be submitted in writing via email (nimohajji.ali@care.org) to no later than May 6th, 2025

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible |  | Remarks |
| --- | --- | --- | --- | --- |
| RFP Issued | April 30th, 2025 | CARE |  |  |
| Terms of Reference |  | Supplier |  | Deadlines must be strictly observed. |
| Deadline for submission of clarification questions to CARE | May 4th, 2025 | Supplier |  | Deadlines must be strictly observed. |
| CARE to answer all clarifications | May 5th, 2025, | CARE |  |  |
| Supplier’s Deadline for Submission of Proposal | May 6th, 2025 | Supplier |  | Deadlines must be strictly observed. |
| Finalists selected | May 12th, 2025 | CARE |  | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

# PROJECT REQUIREMENTS:

- Technical Requirements

- Technical Proposal of the Product

See below TOR

TERMS OF REFERENCE for Undertake Study to Determine the of Impact of School Feeding Programs Currently Active In 25 Primary Schools Within Somaliland's Tog-Dheer, Marodi-Jeex, And Sanaag Regions, Focusing on Their Influence on Pupil Enrollment, Retention, And Scholastic Performance.

Summary

CARE is currently implementing the Home-Grown School Feeding Initiative (HGSF) in Somaliland. CARE is seeking to procure the services of an external consultant to undertake study of the impact on school feeding on pupil enrolment, retention and performance in Somaliland.

CARE is a humanitarian non-governmental organization committed to working with poor women, men, boys, girls, communities, and institutions to have a significant impact on the underlying causes of poverty. CARE seeks to contribute to economic and social transformation, unleashing the power of the most vulnerable women and girls.  CARE has been providing emergency relief and lifesaving assistance to the Somali people since 1981. CARE is implementing three mutually supportive programs and are designed along the humanitarian-development nexus: Education and Gender Equality: Builds the capacity of government institutions to provide gender responsive education services while building adolescents and young people’s life skills. It strengthens the capacity of feminist organizations and Savings Groups Networks and supports their collective advocacy. Climate Justice and Food, Water, and Nutrition: Contributes to increased food security and an improved nutritional status of vulnerable populations through promoting gender-responsive, climate-smart and sustainable crop and livestock production, diversifying livelihoods, linking pastoralists and smallholder farmers with financial services and markets, promoting WASH and nutrition, and strengthening early warning systems and family and community contingency planning. Humanitarian Assistance: Provide a wide range of humanitarian services covering food security and economic recovery as well as education, health, nutrition, WASH, and protection in emergencies, ensuring investments into recovery. We will continue to contribute to humanitarian coordination and promote gender-responsive emergency assistance with the help of Rapid Gender Assessments and the promotion of women’s leadership in response.

- Project overview

CARE implements the HGSF program in Somaliland supported by Ministry of foreign affairs, CARE has extended its impact through the implementation of HGSF Program. This initiative:

- Provides nutritious, locally sourced meals for schoolchildren, enhancing their health and learning outcomes

- Supports local farmers and traders, contributing to economic growth

- Strengthens the connection between schools and communities, fostering sustainability through capacity building and ownership

The Home-Grown School Feeding (HGSF) program aims to enhance educational outcomes and community resilience by providing safe, nutritious, and locally sourced meals to schoolchildren. This initiative is currently operational in 25 primary schools across Somaliland's Tog-dheer, Marodi-Jeex, and Sanaag regions.

- Developing capacities of MOE at national and regional levels for effective HGSF operation and raising awareness.

- Providing training on HGSF quality standards for small-holder farmers and CECs. With improved capacities the MOE and CECs are expected to support schools to implement HGSF according to quality standards

- Ensuring primary school children in target schools receive more nutritious meals through locally produced food

- Promoting gender-sensitive advocacy for improved application of HGSF by local CSOs. This will be achieved through encouraging women-led CSOs to actively engage in advocacy for HGSF within communities and strengthening coordination and information sharing among national and sub-national stakeholders to enhance support for HGSF promotion.

HGSF Project Impact, Outcomes & Outputs

Impact: Contribute to reducing the risk of children attending school hunger through vitalizing local climate-smart agricultural production systems and capacitating stakeholders to disseminate a gender-sensitive HGSF concept

- Outcome 1: Targeted schools are supported by government structures to benefit from HGSF implemented according to national quality standards

- Outcome 2: primary school children in target primary schools receive more nutritious school meals (dietary diversity) as a result

- Outcome 3: Local CSOs do gender-sensitive advocacy for improved application of HGSF

The project is currently in its third year of implementation and has achieved the following milestones:

- Strengthened government support & quality standards

- Effective government engagement: 6 MOE Wellbeing Units actively supporting HGSF at all levels

- Monitoring results confirmed more than 75% of targeted schools adhering to national HGSF implementation standards

- Enhanced Capacity: through technical support and capacity building for school administrators and CECs

- Improved nutrition & local food sourcing

- Nutritious meals provided: 5,537 primary school children receiving regular meals

- Local Sourcing Success: 90 tonnes of cereals procured from smallholder farmers

- Local Trader Engagement: 866 tonnes of food items sourced from local traders

- Supported local farmers with technical support and training

- Empowered local advocacy & collaboration

- Advanced policy development: Significant progress towards evidence-based HGSF policy

- Community Partnerships: Strong collaboration with farmers' cooperatives, women's groups, and VSLAs

- Strengthened networks: Improved coordination between schools, businesses, and traders

- CSO’s are playing an instrumental role in fostering connections between schools, businesses and traders

- Study objectives

The main objective of the study is to assess the impact of the school feeding program on pupils’ enrollment, retention and performance

Specific objectives:

- To determine how the school feeding program contributed to student’s enrollment and what changes occurred when compared over the last 2 years in targeted schools

- And what factors that have contributed to improvements in enrollment and retention (what has worked or not worked)

- To assess the impact of the HGSF on learners’ retention by analyzing enrollment, dropouts, transfers and transitions in targeted schools

- To assess the impact of HGSF on pupils’ performance through head teachers, teachers, CECs assessments and pupils’ assessment as well as their participation in school activities

- To document challenges faced by the school feeding program related to enrollment, retention and performance and suggest effective recommendations for enhancing the HGSF to promote these aspects

- Methodology

The study design should entail a holistic approach, comprising both the qualitative and quantitative method designed to provide a comprehensive understanding of HGSF project impact on pupils’ enrollment, retention and performance. In addition, the study will have to use gender sensitive methods, ensuring that women, girls, men and boys from different groups of stakeholders participate, and that their different responses and perceptions are incorporated into the study process.

The study should focus on understanding the impact of the HGSF program within the targeted schools. Data on pupil enrolment, retention, and performance will have to be collected as the HGSF program has been ongoing in the last 2 years and compare with the baseline report. To understand how the program is perceived and influenced these areas, the study will have to gather detailed opinions and experiences from head teachers, teachers, CECs, REOs, DEOs, parents, and learners through quantitative and qualitative methods.

- Scope of work

- Develop inception report

Describe methodology, timeline, and include data collection instruments and tools

- Prepare detailed work plan and methodology

Outline steps to implement and achieve task objectives with high quality

- Review of existing project documents

Assess annual reports, monitoring assessments, baseline report, and other relevant materials from the project.

- Conduct interviews

Engage with a diverse range of stakeholders, including:

- Head teachers

- Teachers

- Community Education Committees (CECs)

- Parents

- Learners (girls, boys)

- Gender focal persons

- Regional Education Officers (REOs), District Education Officers (DEOs), Ministries of education officials

- Develop and share draft study report

Share initial version of the report

- Finalize impact study report

Incorporate reviews and feedback received and finalize the study report

- Deliverables

In reference to the scope of work above, the consultant team is expected to accomplish and submit the following:

- An inception report including:

- Research methodology including the sampling methodology and the analysis framework,

- Draft data collection tools,

- Detailed work plan outlining all tasks

- Data collection protocols

- In depth quantitative and qualitative analysis of data.

- Complete clean datasets in SPSS/STATA

- Complete qualitative datasets in Excel or open-source software.

- SPSS/STATA syntax and output files reflecting the analysis conducted.

- Report (in MS Word), following the format provided

- Presentations of preliminary findings and recommendations validation and feedback with CARE and other stakeholders.

- Final report with corresponding finalized annexes in English.

# Outline of Baseline study report

- Cover page, Table of contents, List of acronyms

- Executive summary – should be a clear and concise stand-alone document that states the most salient findings, conclusions and recommendations of the study and gives readers the essential contents of the study report in the three to five pages.

- Methodology and study design – should describe the methodology ad design of the quantitative and qualitative components, constraints and limitations to the study, and issues in carrying out the study.

- Findings – should present results from the quantitative survey and qualitative study. Results from the quantitative survey should be analyzed and discussed, using findings from the qualitative study for triangulation, interpretation and validation of results. Any bivariate and multivariate analysis undertaken should also be included.

- Conclusions and recommendations – should provide high-level conclusions from the impact study and recommendations for the design and implementation of the future studies. Recommendations must be relevant to the project and context and include concrete and realistic steps for implementation.

- Annexes – all special documentation identified as necessary or useful (e.g. quantitative survey/qualitative study instruments, sampling plan for the quantitative survey, syntax files etc.).

Timeline

| Documentation of learning products | Days |
| --- | --- |
| Inception report + tools (drafting and finalized) | 2 days |
| Field work data collection (inclusive training, piloting) | 6 days |
| Draft report submitted | 4 days |
| Consultant addresses comments and revises study report | 2 days |
| Final report submitted | 2 days |
| Total days | 16 days |

- Consultant qualifications

The selected firm/consultant(s) shall possess the following qualifications:

- Advanced university degree in Education, Social Sciences or any other related field with a minimum of 5 years of experience in conducting similar work. Previous experience in undertaking studies for similar projects

- Demonstrated experience and expertise in designing, organizing and conducting qualitative research, data collection and analysis

- Demonstrated experience in school feeding programs in Somalia/Somaliland

- Experience in conducting project evaluations of similar programmes using participatory methods.

- Thorough knowledge of education programming; including school feeding program

- Appropriate country knowledge /experience and ability to interpret findings from a contextual perspective

- Ability to deliver high-quality written products

- BUDGET

The budget prepared by the bidder should cover all the activities outlined above, including study training, data collection, data cleaning, transcription and translation. This budget is inclusive of all costs covering team member costs, travel, research costs and any other costs associated with the completion of the work including where required costs for reasonable adjustment.

Bidders are required to organise and fund their own duty of care arrangements as required.

Bidders are required to provide a fully costed proposal in the form of a price schedule that as a minimum should include:

- Sub-total of fees for the delivery of any task or deliverable.

- Sub-total for number of days per partner organisation (as applicable),

- Expenses and overheads broken down by the project cost categories.

- Reasonable adjustment costs; and

- Total costs before and after any taxes that are applicable.

Proposals should include the following:

Technical proposal – bidders’ approach to the study

Financial proposal

Qualifications – how does the bidder meet the qualifications, including CVs of all key involved persons

References

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days after service delivery) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

Note: Additional required documents:

- Submit copy of valid Business license

- Submit copy of valid tax clearance

- Experience client contracts