Request for Proposal

[Conflict Mapping and Context Analysis in Hiraan Region, Hirshabelle State of Somalia

]

RFP DOCUMENT # [__38824)

RFP Issue Date:  01/04/2026]

Proposal submission Deadline :  [07/04/2026]

CARE USA

151 Ellis Street NE

Atlanta, GA 30303-2440

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of submitted proposal

- To award another type of contract other than that described herein, or to award no contract;

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions, and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.A. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Supplier Name: |  |
| --- | --- |
| Title/Designation: |  |
| Company Name: |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All vendors must provide written notification via email to (som.consultant@care.org) of their intent to participate, or not to participate in the bidding process by [07/04/2026

.

Proposals will be accepted until 07/04/2026 delivered via email solely to [Procurement Staff’s Name] (procurement staff’s active email address), no later than the above specified date.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in proposals must be all-inclusive to include any outsourced or contracted work.  Any proposals which call for outsourcing or contracting work must include a name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

CARE is issuing this RFP (Request for Proposal) soliciting qualified bidders to submit proposals intended for the [ToR Conflict Mapping and Context Analysis in Hiraan Region, Hirshabelle State of Somalia

This RFP is an invitation to bid, not an offer of contract.  Bidders must submit a response that complies with the minimum requirements contained herein.

# PROJECT OVERVIEW

CARE is seeking a provider to submit proposals intended for the [provide requirement description]

# Terms of reference for Conflict Mapping and Context Analysis in Hiraan Region, Hirshabelle State of Somalia

- Background and Context

## Somalia has experienced prolonged political instability and violent conflict since the collapse of the central government in 1991. The breakdown of state institutions resulted in the fragmentation of political authority, the emergence of armed factions, and the proliferation of clan-based militias competing for territorial control, economic resources, and political influence. Over the past three decades, Somalia’s conflict landscape has evolved into a complex system characterized by overlapping dynamics including clan competition, violent extremist insurgency, contested governance arrangements, and disputes over natural resources.

Following the establishment of the Federal Government of Somalia (FGS) in 2012, significant efforts have been made to rebuild state institutions and advance the federalization process through the creation of Federal Member States (FMS). The federal governance framework aims to decentralize authority, promote inclusive political representation, and strengthen governance structures at regional and district levels. However, the federalization process has also introduced new political dynamics, including tensions between federal and state authorities, disputes over power-sharing arrangements, and debates concerning the distribution of political authority and resources among different regions and communities. At the same time, Somalia’s conflict dynamics continue to be influenced by entrenched clan identities, competition over land and natural resources, weak institutional capacity, economic marginalization, and the persistent threat posed by the armed extremist group Al-Shabaab, particularly in rural areas where state presence remains limited.

Hirshabelle State was formally established in 2016 as part of Somalia’s federalization process through the merger of the Hiran and Middle Shabelle regions. While the formation of Hirshabelle represented an important step toward strengthening regional governance, it also generated political contestation among local stakeholders regarding issues of representation, power-sharing, and the distribution of administrative authority between the two regions. As a result, the governance landscape in Hirshabelle continues to be characterized by evolving institutional arrangements, limited administrative capacity, and ongoing negotiations among political actors, clan leaders, and community representatives. District administrations often face significant challenges in delivering public services, maintaining security, and effectively managing disputes due to resource constraints and institutional limitations.

Within this context, the Hiran Region occupies a strategically significant position in Hirshabelle State. The regional capital, Beledweyne, serves as an important economic and transportation hub linking central Somalia with cross-border trade routes connecting Ethiopia and other parts of the country. The region also benefits from the presence of the Shabelle River, which supports agricultural production and agro-pastoral livelihoods. Despite these advantages, Hiran faces substantial development challenges, including limited infrastructure, high unemployment, and chronic livelihood insecurity among communities. Environmental pressures such as recurrent flooding along the Shabelle River and periodic droughts further exacerbate these challenges by disrupting agricultural production, displacing rural populations, and intensifying competition over grazing land and water resources.

Hiran has also experienced persistent insecurity linked to both localized inter-clan conflicts and the broader insurgency involving Al-Shabaab. The region has historically served as an important operational corridor for the group due to its strategic location and mobility routes. In recent years, however, community-led resistance movements have emerged in response to the group’s presence. Local militia mobilizations commonly referred to as Ma’awisley have supported government-led counter-insurgency operations and contributed to altering the security landscape in several districts. While these efforts have weakened insurgent control in certain areas, they have also introduced new governance and security challenges related to militia coordination, command structures, and the management of local security arrangements.

At the same time, unresolved clan disputes, political rivalries, and competition over administrative authority continue to generate localized tensions within the region. Environmental shocks such as drought and flooding further interact with these social and political dynamics, intensifying competition over scarce resources and increasing the potential for conflict. The interaction between insurgency dynamics, community mobilization, governance challenges, and resource competition creates a complex and evolving conflict environment in Hiran Region. Given these interlinked political, social, security, and environmental dynamics, there is a need for a comprehensive conflict mapping and context analysis to better understand the drivers, actors, and patterns of conflict in the region.

This analysis will be carried out under the CARE led Puntland and Galmudug Peace Initiative project. Whilst the project is not operational in Hirshabelle state, the region has been chosen as a climate-conflict hotspot with a view to providing an evidence-based foundation to inform future conflict-sensitive programming, strengthen peacebuilding efforts, and support governance and development initiatives aimed at promoting stability and resilience in Hiran Region and across Hirshabelle State.

- Rationale for Conducting the Conflict Mapping

Given the multidimensional nature of conflict dynamics in Hiran Region, there is a need for a comprehensive and systematic analysis that examines these dynamics in an integrated and evidence-based manner. Understanding the underlying drivers of conflict, the relationships between key actors, and the structural conditions that contribute to instability is essential for designing effective peacebuilding and development interventions. Conflict mapping and context analysis provide critical analytical tools for identifying patterns of conflict, assessing risks, and informing conflict-sensitive programming. Such analysis can help stakeholders better understand the interactions between governance, security, social dynamics, and environmental pressures that shape conflict trajectories.

To support this objective, CARE International Somalia seeks to engage a qualified external consultancy firm to undertake a comprehensive Conflict Mapping and Context Analysis in Hiran Region, Hirshabelle State Somalia.

- Purpose of the Consultancy

The purpose of this consultancy is to undertake a comprehensive conflict mapping and context analysis of Hiran Region to generate a detailed understanding of the political, social, economic, and environmental dynamics shaping conflict in the region.

The consultancy will identify the key drivers of conflict, map relevant actors and relationships, assess current and emerging risks, and analyse the institutional and social mechanisms that influence conflict prevention and resolution. The findings will provide an analytical foundation for designing conflict-sensitive interventions and strengthening peacebuilding, governance, and development programming in Hirshabelle State.

- Objectives of the Consultancy

  - Overall Objective

## The overall objective of the consultancy is to conduct a comprehensive conflict mapping and context analysis in Hiran Region that identifies key conflict drivers, actors, relationships, and emerging risks to inform evidence-based peacebuilding, governance, and development interventions.

  - Specific Objectives

The specific objectives of the consultancy include:

- Conducting a brief overview of the historical evolution of conflict dynamics in Hiran Region.

- Identifying and analysing structural and proximate drivers of conflict affecting communities in the region.

- Identify consequences and impacts of conflict – on social, economic and political structures and relationships, with an explicit gender and age lens.

- Mapping key conflict actors, their interests, influence, and relationships. This should be at both general and context specific level, focusing on drivers and push factors, including tipping points and displacement as well as connectors and dividers.

- State/formal and traditional/informal governance systems, conflict prevention and dispute resolution mechanisms – including examining their strengths and weaknesses

- Analysing the impact of environmental pressures and climate variability on resource competition.

- Examining gender and youth dimensions of conflict and peacebuilding – including barriers and opportunities for their participation in relevant decision-making spaces.

- Assessing potential future conflict scenarios and associated risks for different groups, including marginalised groups, women/girls.

- Providing practical recommendations to strengthen conflict prevention and peacebuilding efforts. The recommendations are expected to cover political processes (including power sharing), security and justice issues, as well as economic and environmental dimensions of peace at both district and regional levels.

- Scope of Work

The consultancy firm will undertake a comprehensive conflict mapping and context analysis of the Hiran Region, examining the multidimensional factors that shape conflict dynamics and social relations across the region. The scope of work will encompass an in-depth assessment of political, social, security, economic, and environmental dimensions that influence patterns of instability, cooperation, and peacebuilding opportunities. The analysis will explore how formal governance institutions at federal, state, and district levels interact with informal systems of authority, including clan structures, customary institutions, and religious leadership, in shaping local decision-making and conflict management processes. Attention will be given to understanding the historical and contemporary drivers of conflict, including disputes over land and natural resources, political representation, access to services, and control over economic opportunities.

The consultancy is also expected to examine the evolving security landscape, including the presence and activities of armed actors, community defence groups, and security forces, and assess how these actors affect local governance and civilian protection. In addition, the study will analyse socioeconomic pressures such as unemployment, livelihood insecurity, and market access, as well as environmental stressors including recurrent droughts, flooding along the Shabelle River, and competition over grazing and agricultural land. Through this multidimensional assessment, the consultancy will generate a detailed conflict map that identifies key actors, relationships, drivers of conflict, and potential entry points for conflict prevention, peacebuilding, and conflict-sensitive development interventions in Hiran Region.

  - Political and Governance Dynamics

The consultancy will examine governance structures at the federal, state, and district levels to understand how political authority and administrative responsibilities are organized and exercised within Hiran Region. The analysis will assess the effectiveness and legitimacy of governance institutions in delivering public services, managing disputes, and responding to community needs. Attention will be given to the relationships between the Federal Government of Somalia, the Hirshabelle State administration, and district authorities, and how these relationships influence political representation, accountability, and decision-making processes at the local level.

In addition, the study will explore the interaction between formal governance institutions and informal authority systems, including clan elders, religious leaders, and customary dispute resolution mechanisms. These traditional structures often play a critical role in maintaining social order and mediating conflicts within communities. The consultancy will analyse how these systems complement or compete with formal state institutions and assess their contribution to local governance, conflict and natural resource management, and community legitimacy.

  - Clan Relations and Social Dynamics

The consultancy will analyse the role of clan and sub-clan structures in shaping social relations, political alliances, and conflict dynamics within Hiran Region. Clan identity remains a key factor influencing access to resources, representation in governance institutions, and the management of disputes between communities. The study will examine historical inter-clan relationships, territorial claims, and existing grievances that may contribute to tensions or conflict between different groups. The analysis will also assess the role of customary institutions and traditional leadership structures in maintaining social cohesion and resolving disputes. Elders and religious leaders often play a central role in mediating conflicts through customary mechanisms that are widely recognized by local communities. The consultancy will examine the effectiveness of these mechanisms in addressing contemporary conflicts and explore how changing social dynamics, including displacement and urbanization, may be influencing traditional systems of social organization.

  - Security and Armed Actors

The consultancy will assess the security landscape in Hiran Region by identifying the various security actors operating within the region and examining their roles, influence, and interactions with local communities. The analysis will consider the presence and activities of federal and state security forces, community-based militias, and armed non-state actors, including insurgent groups that may operate in or influence the region. Understanding the relationships between these actors is critical for identifying the sources of insecurity and the dynamics that shape local stability. The study will also examine how security operations and armed actors affect civilian populations and governance structures. Attention will be given to issues such as protection of civilians, freedom of movement, displacement, and community perceptions of safety and trust in security institutions. The consultancy will analyse how security dynamics influence everyday life in communities and how they intersect with political and social tensions.

  - Resource-Based Conflicts

## The consultancy will examine patterns of competition over natural resources in Hiran Region, particularly disputes related to land ownership, water access, and grazing areas. These resources are central to the livelihoods of agricultural and pastoral communities, and competition over their use can contribute to tensions between different groups. The analysis will explore how land tenure arrangements, irrigation systems, and seasonal grazing routes influence relationships between communities. The study will also assess how demographic pressures, displacement, and changes in land use patterns may intensify resource-based conflicts. Attention will be given to understanding how traditional mechanisms for resource sharing and dispute resolution operate and whether they remain effective in managing contemporary challenges related to resource access and the roles and effectiveness of natural resource committees.

  - Socioeconomic Drivers

The consultancy will analyse the socioeconomic conditions that shape conflict dynamics in Hiran Region, including levels of poverty, unemployment, and access to livelihood opportunities. Economic hardship and limited access to resources can contribute to frustration and social tension, particularly among youth who may face significant barriers to employment and economic participation. The study will also examine how disparities in access to services, infrastructure, and development opportunities influence perceptions of inequality and marginalization among communities.

  - Environmental Pressures and climate shocks

The consultancy will examine how environmental factors and climate shocks influence conflict dynamics in Hiran Region, particularly the impacts of recurrent droughts and flooding along the Shabelle River. These climate shocks can disrupt agricultural production, reduce access to grazing land, and force communities to migrate in search of water and pasture, thereby increasing competition over scarce resources. The study will also assess how climate variability interacts with social and political factors to shape patterns of displacement and livelihood vulnerability, paying particular attention to the disproportionate impact on women and girls. By analysing the relationship between environmental pressures, climate shocks and local conflicts, the consultancy will identify areas where climate-related risks may contribute to instability and where early warning systems supporting preparedness and early actions along with longer term resilience-building measures may help reduce tensions.

  - Gender and Social Inclusion

The consultancy will analyse the differential impacts of conflict on women, youth, and marginalized groups within Hiran Region. Conflict and insecurity often affect social groups in distinct ways, influencing access to resources, participation in decision-making processes, and exposure to violence or displacement. The study will examine how these impacts are experienced across different segments of society. In addition, the analysis will explore the roles played by women and youth in peacebuilding and conflict resolution processes. Women often play important roles in community mediation and social support networks, while youth represent both a vulnerable group and a potential driver of positive change. The consultancy will assess opportunities to strengthen inclusive participation in governance and peacebuilding initiatives.

- Methodology

The consultancy will adopt a mixed-method research approach that combines both qualitative and analytical methods to generate a comprehensive understanding of conflict dynamics in Hiran Region. The study will begin with an extensive desk review of existing literature, reports, policy documents, and previous conflict assessments related to governance, security, social dynamics, and environmental pressures in the region. This review will help establish a contextual foundation for the study and guide the design of field research activities.

Primary data collection will be conducted through key informant interviews and focus group discussions with a wide range of stakeholders, including community leaders, government officials, civil society organizations, women groups, peace committees, natural resource committees, youth representatives, and other relevant actors. In addition, the consultancy will apply analytical tools such as stakeholder mapping, conflict tree analysis, power-interest analysis, and conflict timeline mapping based on the CARE CCCVA model to identify relationships between actors, drivers of conflict, and potential entry points for peacebuilding. The findings will be validated through consultations with key stakeholders to ensure the accuracy, credibility, and relevance of the analysis.

- Expected Deliverables

The consultancy firm will be responsible for producing the following deliverables during the assignment. Each output is intended to document the progress of the study and ensure that the findings of the conflict mapping and context analysis are clearly presented and accessible to stakeholders.

  - Inception Report

The consultancy firm will prepare an inception report at the beginning of the assignment outlining the proposed methodology, research design, data collection tools, and detailed workplan. The report will also clarify the scope of the study, sampling approach, and stakeholder engagement strategy to guide the implementation of the analysis.

  - Draft Conflict Mapping and Context Analysis Report

Upon completion of the field research and preliminary analysis, the consultancy will submit a draft report presenting the initial findings of the conflict mapping. The draft report will include an overview of conflict dynamics, key drivers of conflict, stakeholder mapping, and preliminary recommendations.

  - Final Conflict Mapping and Context Analysis Report

Following feedback from the CARE International and relevant stakeholders, the consultancy firm will submit a final report incorporating revisions and additional analysis where necessary that will present a comprehensive assessment of conflict dynamics in Hiran Region, supported by evidence and detailed recommendations on peacebuilding and conflict-sensitive programming for development and government actors.

  - Conflict Actor Mapping and Analytical Framework

The consultancy will develop a conflict actor map and analytical framework illustrating the relationships between key stakeholders, sources of conflict, and potential entry points for conflict mitigation.

  - Policy Brief

The consultancy will produce a concise policy brief summarizing the key findings of the study and highlighting the most important recommendations that will be designed to provide decision-makers with clear and accessible insights for policy and program development.

  - Presentation of Findings

The consultancy firm will present the findings of the study to relevant stakeholders through a dissemination or validation workshop that will provide an opportunity to discuss the results, gather feedback, and promote the use of the study’s recommendations in future interventions.

- Duration of the Assignment

The consultancy assignment is expected to be completed within a period of 4 weeks from the date of contract signing. During this period, the consultancy firm will undertake all activities required to complete the conflict mapping and context analysis, including the inception phase, desk review, field data collection, analysis, and preparation of the final report and other deliverables.

The detailed workplan and timeline for implementing the assignment will be presented in the inception report and agreed upon with CARE International at the start of the consultancy. The consultancy firm will ensure that all deliverables are completed within the agreed timeframe while maintaining the quality and integrity of the research process.

| ## Phase | ## Key Activities | ## Duration |
| --- | --- | --- |
| ## Phase 1: Inception and Planning | ## Contract signing, introductory meetings with CARE, development of research design, preparation of data collection tools, and submission of the inception report | ## 5 days |
| ## Phase 2: Desk Review and Context Analysis | ## Review of relevant literature, policy documents, previous conflict assessments, and secondary data related to Hiran Region | ## 5 days |
| ## Phase 3: Field Data Collection | ## Conduct key informant interviews and focus group discussions with community leaders, government officials, civil society organizations, women groups, youth representatives, and other stakeholders | ## 7 days |
| ## Phase 4: Data Analysis and Conflict Mapping | ## Analysis of collected data, development of conflict actor mapping, conflict tree analysis, and identification of key drivers of conflict | ## 5 days |
| ## Phase 5: Draft Report Preparation | ## Preparation and submission of the draft conflict mapping and context analysis report to CARE for review and feedback | ## 4 days |
| ## Phase 6: Validation and Finalization | ## Stakeholder validation workshop, incorporation of feedback, and submission of the final report and policy brief | ## 4 days |

- Qualifications of the Consultancy Firm

The consultancy firm should demonstrate strong institutional capacity and relevant technical expertise to conduct a comprehensive conflict mapping and context analysis in fragile and conflict-affected environments. Given the complexity of conflict dynamics in Hiran Region, the firm must possess proven experience in conflict analysis, peacebuilding research, governance assessments, and stakeholder engagement. The consultancy team should also demonstrate a strong understanding of Somalia’s political, social, and security context, particularly within Hirshabelle State, and the ability to conduct field-based research in sensitive environments while adhering to ethical and conflict-sensitive research principles.

The consultancy firm should meet the following minimum qualifications:

- Proven institutional experience of at least 7–10 years in conducting conflict and climate analysis, peacebuilding research, governance assessments, or political economy analysis in fragile and conflict-affected contexts.

- Demonstrated experience implementing similar assignments such as conflict mapping, social cohesion studies, or context analyses for international NGOs, UN agencies, government institutions, or development partners.

- Strong technical expertise in conflict analysis methodologies, including stakeholder mapping, conflict tree analysis, political economy analysis, and risk assessment.

- Demonstrated experience conducting qualitative research, including key informant interviews, focus group discussions, and participatory community consultations.

- Proven knowledge of Somalia’s political, governance, and security landscape, particularly the dynamics within Hirshabelle State and central Somalia.

- Demonstrated capacity to manage field research operations, coordinate data collection teams, and ensure quality assurance of analytical outputs.

- Ability to engage diverse stakeholders, including government institutions, community leaders, civil society organizations, women groups, and youth representatives.

- Strong analytical and report writing capacity, with a track record of producing high-quality analytical reports and policy-oriented publications.

- Demonstrated commitment to ethical research practices, including conflict-sensitive approaches, informed consent, and the application of Do No Harm principles.

  - Team Composition

The consultancy team may include qualified experts with the following expertise:

- Senior Conflict Analyst with extensive experience in conflict analysis, peacebuilding programming, and leading complex research assignments and expertise in governance systems, political structures, and institutional analysis. Contextual knowledge of Somalia, fluency in Somali language, and experience engaging communities in Hiran Region.

- Gender and Social Inclusion Specialist with experience analysing gender dynamics and the inclusion of marginalized groups in conflict and peacebuilding contexts. Contextual knowledge of Somalia, fluency in Somali language, and experience engaging communities in Hiran Region.

- Evaluation Criteria

Proposals submitted by interested consultancy firms will be evaluated based on their technical quality, institutional experience, expertise of the proposed team, understanding of the assignment, and overall value for money. The evaluation process will ensure that the selected consultancy firm demonstrates both strong technical capacity and contextual understanding necessary to conduct a comprehensive conflict mapping and context analysis in Hiran Region.

The evaluation will be based on the following criteria:

- Technical Approach and Methodology – The clarity, relevance, and feasibility of the proposed methodology, including the research design, data collection methods, analytical tools, and stakeholder engagement approach for conducting the conflict mapping and context analysis.

- Experience of the Consultancy Firm – Demonstrated institutional experience in conducting conflict analysis, peacebuilding research, governance assessments, or similar analytical studies in fragile and conflict-affected settings.

- Qualifications and Expertise of the Proposed Team – The professional qualifications, technical expertise, and relevant experience of the proposed team members, particularly in areas such as conflict analysis, governance, gender and social inclusion, and qualitative research.

- Contextual Understanding – The degree to which the proposal demonstrates an understanding of Somalia’s political, social, and security dynamics, particularly the context of Hirshabelle State and Hiran Region.

- Financial Proposal – The overall cost of the consultancy and the extent to which the proposed budget represents value for money while ensuring the quality and feasibility of the assignment.

- Proposal Submission Requirements

## Interested consultancy firms are invited to submit a comprehensive proposal outlining their capacity and approach to undertake the assignment. The proposal should demonstrate the firm’s technical expertise, understanding of the assignment, and ability to deliver high-quality analytical outputs within the specified timeframe.

## The submission should include the following documents:

- Technical Proposal: A detailed technical proposal (maximum 15 pages) describing the firm’s understanding of the assignment, the proposed approach, and the methodology to be used for conducting the conflict mapping and context analysis. The proposal should clearly outline how the consultancy intends to achieve the objectives of the assignment

- Detailed Methodology: A clear description of the proposed research methodology, including data collection methods, analytical tools, stakeholder engagement strategies, and approaches to ensure ethical and conflict-sensitive research practices

- Workplan and Timeline: A proposed workplan outlining the key phases of the assignment, expected activities, and timeline for completing each deliverable within the agreed consultancy period.

- Company Profile: A brief profile of the consultancy firm highlighting its institutional experience, core areas of expertise, and relevant experience in conducting similar assignments in fragile or conflict-affected contexts

- Curriculum Vitae of Key Team Members: Updated CVs of all key personnel proposed for the assignment, clearly outlining their qualifications, relevant experience, and roles within the consultancy team

- Financial Proposal: A detailed financial proposal indicating the total cost of the consultancy, including professional fees, operational costs, and any other expenses associated with the assignment.

- References from Previous Assignment: Contact details of at least two to three references from previous clients or organizations for whom the consultancy firm has conducted similar assignments. These references should demonstrate the firm’s experience and performance in delivering comparable work.

- Ethical Considerations

The consultancy firm will be required to adhere to the highest ethical standards throughout the implementation of the assignment, recognizing that conflict mapping and context analysis involve engagement with communities and stakeholders in potentially sensitive environments. The research process must be conducted in a manner that respects the dignity, safety, and rights of all participants while ensuring that the study does not exacerbate existing tensions or create unintended harm. All data collection activities must follow ethical research practices, including obtaining informed consent from participants prior to interviews or discussions, ensuring confidentiality and anonymity of respondents where necessary, and safeguarding any sensitive information collected during the study. The consultancy team must also demonstrate cultural sensitivity and respect for local customs and social norms when engaging with communities and local stakeholders.

In addition, the consultancy firm must apply a conflict-sensitive approach and the Do No Harm principle throughout the research process. This includes carefully selecting participants, facilitating discussions in a neutral and inclusive manner, and ensuring that the research does not reinforce existing divisions or grievances between communities. The consultancy team must also ensure that the perspectives of diverse groups, including women, youth, and marginalized populations, are captured in a respectful and inclusive way while maintaining the safety and confidentiality of all participants involved in the study.

.

- HOW TO APPLY

The deadline for submission of bids is 07/04/2026. Interested bidders if you are any clarification or questions send to Mohamed.Abdirizak@care.org,  the bidders should send their applicants to Som.Consultant@care.org with  the Subject line Independent Baseline Evaluation & GESI analysis services for Joint Peace Initiative Project

| Requirement & Specs | Qty. | Unit of Measurement | Required Delivery Lead Time | Delivery Address | Contract Period |
| --- | --- | --- | --- | --- | --- |

[Provide additional requirements]

| Item # | Other Requirements |  |
| --- | --- | --- |
| 1 | Delivery Date & Time | Bidder shall deliver the goods at least ____ weeks after Contract signature. |
| 2 | Delivery Terms (incoterms) | EXW [Ex-works (Place)] |
|  |  | FCA [Free Carrier (Port)] |
|  |  | FAS [Free Along-Side Ship (Port)] |
|  |  | FOB [Free On-Board (Port)] |
|  |  | CFR [Cost, & Freight (Port)] |
|  |  | CIF [Cost, Insurance & Freight (Port)] |
|  |  | CPT [Carriage Paid-To (Place)] |
|  |  | CIP [Carriage & Insurance Paid-To (Place)] |
|  |  | DAP [Delivered at Place (Place)] |
|  |  | DPU [Delivered at Place Unloaded (Place)] |
|  |  | DDP [Delivered Duty Paid (Place)] |
| 3 | Custom Clearance (Must be linked to Incoterms at origin) | Not Applicable. Shall be done by _______________ |
|  |  | Shouldered by CARE |
|  |  | Supplier/ Bidder |
|  |  | Freight Forwarder |
| 4 | Exact Address(es) of Delivery Location |  |
| 5 | Warranty Period | Standard Manufacturer’s Warranty (if applicable) |
| 6 | Payment Terms | 30 Days upon Receipt of items |
| 7 | Quotation Validity | The quote needs to be valid for 90 days to cover all the days from bidding up to the award process. However, once the contract has been released, it shall be valid for the same coverage as reflected in the requirement above. |

[Provide additional requirements]

# PROJECT TIMELINE

All bidders are advised to strictly follow the below timeline as noted.

Any technical questions arising during the preparation of your response to this RFP should be submitted in writing via email Abdirashid Ahmed <Abdirashid.Ahmed@care.org>  no later than [05/04/2026].

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible | Remarks |
| --- | --- | --- | --- |
| RFP Issued | 07/04/2026 | CARE |  |
| Supplier to notify CARE of intention to participate in bidding |  | Supplier | Deadlines must be strictly observed. |
| Deadline for submission of clarification questions to CARE | 07/04/2026 | Supplier | Deadlines must be strictly observed. |
| CARE to answer all clarifications | 0504/2026 | CARE |  |
| Supplier’s Deadline of Submission of Proposal | 07/04/2026 | Supplier | Deadlines must be strictly observed. |
| Evaluation of Proposal |  | CARE |  |
| Vendor presentation (if required) |  | Supplier |  |
| Finalists selected |  | CARE | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

# PROJECT REQUIREMENTS

- Technical Requirements

a.1 Technical Proposal of the Product

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Overall Proposal Suitability |  |  |
| 1 | Please see the Scope of Work and any other required specifications for this project. |  |
| 2 | Provide Delivery Lead Time |  |
| 3 | Provide after-sales service (if applicable) |  |
| 4 | Ability to provide sample (if applicable) |  |
| 5 | Provide Warranty Period(if applicable) |  |
|  | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Previous Works and Awards |  |  |
| 1 | Provide 3 or more client experiences or testimonials (References whose environment, size, and scope are most similar to CARE. Include a summary of the work completed for each account. Include reference contact names, with telephone numbers and email addresses.) |  |
| 2 | Provide previous records of performance and service. |  |
| 3 | Provide citations and awards. This encompasses reviewing the citations and awards a vendor has received from other customers and award-giving bodies. |  |
| 4 | Provide any testimonials, survey response/s from previous buyers and/or partners. |  |
| 5 | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Technical Expertise and Organizational Experience |  |  |
| 1 | Provide 5 Availability of vendor’s representatives to call upon and consult with. |  |
| 2 | Any proof that the vendor has the Ability to render satisfactory service in this instance. |  |
| 3 | Provide Years of experience in providing the same requirement to other companies. |  |
| 4 | Provide the latest audited Financial Statement |  |
| 5 | (Any additional requirement that is deemed necessary for “Technical Expertise and Organizational Experience. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Others |  |  |
| 1 | Provide any relative requirements which were not mentioned above. (delete if not applicable) |  |

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

# EVALUATION CRITERIA

CARE will evaluate all proposals based on the following criteria.  To ensure consideration for this Request for Proposal, your proposal should be complete and include all of the following criteria:

- Overall Proposal Suitability: proposed solution(s) must meet the scope and needs included herein and be presented in a clear and organized manner

- Previous Work and Awards: Bidders will be evaluated on examples of their work pertaining to the requirement as well as client testimonials and references

- Technical Expertise and Organizational Experience: Bidders must provide descriptions and documentation of staff technical expertise and experience. Bidders also need to provide their experiences as an organization which include but not limited to years of experiences, financial stability, expertise, and edge to other competitors.

- Value and Cost: Bidders will be evaluated on the cost of their solution(s) based on the work to be performed in accordance with the scope of this project.

Note for Country Offices (CO): The specific criteria must closely represent the objective and scope given the nature of the procurement required. Evaluation criteria reflected above can be added and or adjusted depending on the requirement and the type of purchase. The final evaluation criteria must be reflected above prior to releasing of this RFP.

CARE will review proposed budgets and pricing after the initial review of the criteria above.*