Request for Proposal

[Independent Baseline Evaluation & GESI analysis services for Joint Peace Initiative Project

]

RFP DOCUMENT # [__38815____]____]

RFP Issue Date:  31/03/2026]

Proposal submission Deadline :  [07/04/2026]

CARE USA

151 Ellis Street NE

Atlanta, GA 30303-2440

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of submitted proposal

- To award another type of contract other than that described herein, or to award no contract;

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions, and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.A. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Supplier Name: |  |
| --- | --- |
| Title/Designation: |  |
| Company Name: |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All vendors must provide written notification via email to (som.consultant@care.org) of their intent to participate, or not to participate in the bidding process by [07/04/2026

.

Proposals will be accepted until 07/04/2026 delivered via email solely to [Procurement Staff’s Name] (procurement staff’s active email address), no later than the above specified date.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in proposals must be all-inclusive to include any outsourced or contracted work.  Any proposals which call for outsourcing or contracting work must include a name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

CARE is issuing this RFP (Request for Proposal) soliciting qualified bidders to submit proposals intended for the [ToR Independent Baseline Evaluation & GESI analysis services for Joint Peace Initiative Project

This RFP is an invitation to bid, not an offer of contract.  Bidders must submit a response that complies with the minimum requirements contained herein.

# PROJECT OVERVIEW

CARE is seeking a provider to submit proposals intended for the [provide requirement description]

Independent Baseline Evaluation & GESI analysis services for Joint Peace Initiative Project

Terms of Reference

Independent Baseline Evaluation & GESI analysis services for Joint Peace Initiative Project

- Background and context

CARE, in partnership with Centre for Peace and Democracy (CPD) and Puntland Youth and Social Development Association (PSA), is implementing the SSF III Joint Puntland and Galmudug Peace Initiative Project in the Mudug region of Somalia. The project builds on previous phases that contributed to ceasefire agreements and strengthened community-based peace mechanisms, and seeks to consolidate and expand these gains through inclusive peacebuilding, strengthened governance, and enhanced community resilience.

Mudug represents a complex and fragile context, situated along the administrative boundary between Puntland and Galmudug, where interdependence over shared resources such as water, rangeland, and markets coexists with recurrent tensions and localized conflict. Conflict dynamics are shaped by a combination of factors including clan relations, competition over natural resources, weak and fragmented governance systems, population movements, and the proliferation of small arms. While local peace agreements and dialogue platforms have reduced large-scale violence, the situation remains fragile, with persistent risks linked to unresolved grievances, misinformation, and limited institutional capacity to manage disputes.

Climate variability further compounds these challenges, as recurrent droughts, water scarcity, and environmental stress intensify competition over resources and place additional pressure on already strained community relations and governance systems. The interaction between climate risks and conflict drivers presents a critical dimension that requires integrated analysis to inform sustainable peacebuilding interventions.

At the same time, deeply rooted gender inequalities continue to shape access to resources, participation in decision-making, and exposure to risks. Women and youth remain largely excluded from formal and informal governance and peacebuilding structures due to entrenched patriarchal norms and clan-based systems. Their limited participation reduces the inclusiveness and effectiveness of peace processes and local governance mechanisms. Additionally, women and girls face heightened protection risks, including sexual and gender-based violence (SGBV) and harmful practices, which are often underreported due to stigma, lack of services, and social barriers.

Despite these challenges, there are important opportunities to build on existing peace structures, community dialogue platforms, and the active role of women and youth groups in promoting reconciliation and social cohesion. Strengthening these systems while addressing underlying gender inequalities and climate–conflict dynamics is essential for achieving sustainable peace.

In this context, CARE seeks to commission an integrated baseline evaluation combined with a climate–conflict sensitive gender analysis to generate robust evidence that will inform project implementation, strengthen inclusive programming, and provide a foundation for measuring progress and impact over time.

- Project overview

The SSF III Joint Peace Initiative Project is a peacebuilding program implemented across Puntland and Galmudug, building on results from earlier pilot phases that strengthened peace structures and facilitated reconciliation processes. The project focuses on consolidating and scaling peace gains by supporting existing peace agreements, strengthening joint peace and security mechanisms, and enhancing collaboration between communities and government authorities. Through structured engagement with stakeholders, including traditional elders, government institutions, and community groups, the project promotes inclusive peace processes, social cohesion, and coordinated responses to conflict. Phase Two emphasizes sustainability by reinforcing community–government trust, expanding interventions into new conflict-affected locations, and integrating climate and conflict approaches to address underlying drivers of instability.

Project Objectives

The project aims to achieve the following:

- Strengthen peace agreements and conflict response mechanisms in identified conflict hotspots, enhance joint peace structures with inclusive participation, and deepen community engagement to sustain peace.

- Strengthen social cohesion among communities through conciliation processes, trauma healing initiatives, and inclusive community-based activities that promote trust and interaction.

- Promote coordinated community-led approaches that integrate conflict management with climate adaptation and mitigation for sustainable peace.

- Increase awareness and ownership of peace agreements in peripheral areas and strengthen government–community engagement to build trust and accountability.

The project is being implemented in several regions including Mudug, Galgaduud and Bari regions, covering both existing (pilot/continuation) and new expansion areas. In the existing locations include Goldogob, Banderadley, Dhabad, Galinsoor and Caabduwaaq, Galkacyo. The project builds on established peace agreements, functional peace structures, and ongoing implementation processes, with continued support focused on consolidation, including final peace conferences and strengthened monitoring mechanisms. In the new expansion areas include Afbarwaqo, Balibusle, Tawfiiq, Afbarwaaq and Cadaado. the aim for new locations is to initiate and strengthen peacebuilding interventions. Implementation across all locations is carried out in close coordination with state, district, and local government authorities, as well as traditional leaders and joint peace committees to ensure inclusive and locally grounded processes.

- Purpose and Objectives of the Evaluation

Purpose

The purpose of this assignment is to establish credible baseline values for all indicators in the project results framework while generating an in-depth, integrated understanding of conflict dynamics, governance systems, climate–conflict interactions, and gendered power relations in the target areas. The findings will inform evidence-based, inclusive, and conflict-sensitive program implementation and provide a robust reference point for measuring progress, outcomes, and impact over the project lifecycle.

Objectives

The baseline evaluation and integrated analysis will pursue the following objectives:

- Establish baseline values for all indicators in the project results framework, with appropriate disaggregation to enable future measurement of change.

- Analyze the current conflict context, including key drivers, triggers, actors, and existing peace mechanisms, as well as levels of social cohesion and community resilience.

- Examine the climate–conflict nexus by assessing how climate variability, resource scarcity, and environmental stress interact with conflict dynamics, and how communities and institutions currently anticipate, respond to, and manage these risks.

- Assess the functionality, inclusiveness, and effectiveness of governance and decision-making structures (formal and informal), including peace committees, dialogue platforms, early warning systems, and natural resource management mechanisms.

- Analyze gender and social inclusion dynamics, including power relations, participation, leadership, and barriers affecting women, youth, and marginalized groups in peacebuilding, governance, and climate-related decision-making processes.

- Key Evaluation Questions

The baseline will address the following key thematic areas and corresponding questions:

Conflict dynamics and peacebuilding

- What are the key drivers, triggers, and patterns of conflict across the target locations?

- What formal and informal mechanisms currently exist for conflict prevention, management, and resolution?

- How effective and inclusive are existing peace agreements, dialogue platforms, and reconciliation processes?

- What factors contribute to sustaining peace or increasing the risk of conflict relapse?

Governance and institutional systems

- What governance and decision-making structures (formal and informal) exist at community, district, and inter-state levels?

- How do these structures function in practice in relation to peacebuilding, dispute resolution, and service delivery?

- Who holds decision-making power within these systems, and how are decisions made and enforced?

- What are the strengths, gaps, and coordination challenges across governance and peace structures?

Climate–conflict nexus

- How do climate-related risks (e.g., drought, water scarcity, environmental stress) influence conflict dynamics and cooperation among communities?

- What systems exist for early warning, early action, and resource management, and how effectively do they respond to climate-related risks?

- How do communities currently cope with and adapt to climate-induced shocks, and how does this affect conflict and peace dynamics?

Gender, power, and social inclusion

- What are the prevailing gender roles, relations, and power dynamics within communities, and how do these influence women’s participation, leadership, and decision-making in governance, peacebuilding, and natural resource management systems?

- What formal and informal governance and decision-making structures exist (state, traditional, and community-based), and how inclusive are they in terms of participation and leadership of women, youth, and marginalized groups?

- What are the key barriers (social, cultural, economic, mobility, time, security) limiting the participation of women and marginalized groups, and what opportunities or entry points exist to strengthen their meaningful engagement and leadership?

- How do climate-related risks and conflict dynamics affect women and marginalized groups, and what coping mechanisms, capacities, and roles do they currently have in conflict prevention, response, and recovery?

- How do climate-related risks and conflict dynamics affect women and marginalized groups, and what coping mechanisms, capacities, and roles do they currently have in conflict prevention, response, and recovery?

Participation, social cohesion, and community capacities

- What is the current level of trust, cooperation, and social cohesion within and between communities?

- How do different groups (men, women, youth, IDPs, marginalized groups) perceive peace processes and governance systems?

- What capacities exist within communities to engage in peacebuilding, conflict resolution, and climate adaptation efforts?

- What factors enable or hinder inclusive participation and collective action?

- Methodology

The assignment will adopt a mixed-methods approach, combining quantitative and qualitative techniques to generate robust baseline data while providing in-depth analysis of conflict dynamics, governance systems, climate–conflict interactions, and gender and social inclusion. The approach will ensure triangulation of data from multiple sources to enhance validity, reliability, and contextual understanding.

Overall Approach

The baseline will integrate:

- Quantitative methods to establish baseline values for all indicators in the results framework

- Qualitative methods to explain underlying drivers, perceptions, and contextual dynamics

- Participatory and gender-sensitive approaches to capture diverse perspectives, particularly of women, youth, and marginalized groups

- Institutional and governance mapping to analyze formal and informal systems, power dynamics, and decision-making processes

Sampling Approach

The study will apply a structured sampling strategy to ensure adequate representation across project locations in Puntland and Galmudug. The sample will capture key population groups relevant to the project, including variation by sex, age, and other contextually relevant characteristics. The sampling design should be sufficiently robust to generate credible baseline values for indicators and enable disaggregation as required in the results framework.

For qualitative data collection, purposive sampling will be used to engage a diverse range of stakeholders, including community members, peace committees, traditional and religious leaders, women and youth groups, local authorities, civil society actors, and other relevant stakeholders involved in governance, peacebuilding, and natural resource management.

Data collection methods

The baseline will draw on multiple sources of evidence, including:

- Household and/or individual surveys to generate quantitative baseline data for logframe indicators

- Key Informant Interviews (KIIs) with government representatives, peace actors, and institutional stakeholders

- Focus Group Discussions (FGDs) with community members, including women, men, and youth, to capture perceptions and lived experiences

- Participatory approaches to explore power dynamics, gender relations, and community perspectives

- Institutional and governance mapping to identify and analyze formal and informal structures, roles, and relationships

- Desk review of relevant project documents, prior assessments, conflict and gender analyses, and available monitoring data

All tools and approaches must be context-sensitive and designed to ensure inclusion of diverse voices, particularly those of women, youth, IDPs, and marginalized groups.

Ethical and safeguarding considerations

The study will adhere to strict ethical and safeguarding standards appropriate to a fragile and conflict-affected context. This includes:

- Obtaining informed consent from all participants

- Ensuring confidentiality and secure data management

- Applying conflict-sensitive and do-no-harm approaches

- Minimizing risks to participants, particularly when discussing sensitive topics

- Establishing clear referral pathways for safeguarding and protection concerns, including SGBV disclosures

All data collection processes must be conducted in a culturally appropriate and gender-sensitive manner.

Data analysis and reporting

Quantitative data will be analyzed to generate baseline values for all indicators, including required disaggregation. Qualitative data will be analyzed thematically to explain patterns, perceptions, power dynamics, and contextual factors influencing project outcomes.

The analysis will integrate findings across thematic areas, including conflict dynamics, governance systems, climate–conflict interactions, and gender and social inclusion, to produce coherent, actionable insights. The methodology will also acknowledge limitations and propose mitigation measures where necessary.

- Scope of Work

The consultant/team will undertake the following tasks:

- Develop an inception report

Prepare a concise inception report outlining the proposed approach aligned to the ToR, including the overall methodology, sampling strategy, analysis framework, ethical safeguards, risk management, data quality assurance (DQA) approach, and a draft workplan. Draft data collection tools should be included in annex.

- Prepare detailed methodology and workplan

Translate the proposed approach into a detailed and sequenced plan of activities, including roles, timelines, coordination mechanisms. The methodology should include a clear data analysis matrix demonstrating how qualitative and quantitative data will be used to address each evaluation question and generate indicator-level findings. All data must be collected, stored, and managed in line with data protection standards, and disaggregated.

- Conduct desk review

Review all relevant project and contextual documentation to inform the study design and analysis. This includes project proposals, results frameworks, workplans, MEAL documents, previous assessments, conflict and gender analyses, and any relevant secondary data sources.

- Design data collection tools

Develop quantitative and qualitative data collection instruments aligned with the evaluation objectives and research questions. Conduct pilot testing to ensure clarity, cultural appropriateness, and reliability, and revise tools accordingly prior to full implementation.

- Conduct field data collection

Undertake quantitative and qualitative data collection using appropriate methods (e.g., surveys, KIIs, FGDs, participatory approaches), ensuring representation across target locations and stakeholder groups. Engage a diverse range of actors including community members, peace committees, traditional and religious leaders, women and youth groups, local authorities, civil society, and other relevant stakeholders. Ensure inclusive, gender-sensitive, and conflict-sensitive data collection processes.

- Conduct governance, power, and gender analysis

Undertake a structured analysis of formal and informal governance and decision-making systems, including peacebuilding, early warning, and natural resource management structures. This should include mapping of institutions and stakeholders, analysis of power dynamics, and assessment of the extent and quality of participation and leadership of women, youth, and marginalized groups. Identify key barriers, protection risks, and entry points for strengthening inclusive and gender-responsive programming.

- Train and supervise data collection teams

Provide comprehensive training to enumerators and qualitative facilitators on data collection tools, ethical standards, safeguarding protocols, and data quality requirements. Ensure appropriate field supervision, spot-checking, and quality control throughout the data collection process.

- Data management and analysis

Clean, validate, and analyze quantitative and qualitative data in line with the agreed analysis plan. Generate baseline values for all indicators with required disaggregation, and synthesize qualitative findings to explain trends, patterns, and contextual dynamics, including conflict, climate–conflict interactions, governance, and gender dimensions.

- Reporting and validation

Prepare draft reports and facilitate a validation workshop with key stakeholders to present findings, gather feedback, and refine interpretations. Finalize all reports incorporating feedback and submit a complete data and knowledge handover package.

- Deliverables

The consultant/team will be expected to produce the following deliverables:

- Inception report

A comprehensive inception report detailing the overall approach to the assignment, including refined methodology, sampling strategy, data collection plan, analysis framework, ethical and safeguarding considerations, risk mitigation measures, and a detailed workplan. The report should include draft data collection tools and a data analysis matrix in annex.

- Final data collection tools and training materials

A complete set of finalized and field-tested data collection instruments and supporting materials, including: quantitative survey tools, qualitative interview and discussion guides, enumerator training materials.

- Cleaned and structured dataset

A complete and well-organized dataset, including: cleaned quantitative data with labels and codebook, qualitative data (transcripts, notes, or summaries), data files in accessible formats (Stata).

- Draft baseline evaluation report

A draft report presenting baseline values for all indicators (with disaggregation), analysis of conflict dynamics and social cohesion, climate–conflict analysis, overview of governance systems, summary of key GESI findings, key gaps, barriers, and emerging insights and a presentation (slide deck) summarizing findings should accompany the report.

- Draft GESI analysis report

A comprehensive and in-depth Gender Equality and Social Inclusion analysis report presenting gender roles, norms, and power dynamics, governance and institutional mapping (GESI lens), participation and leadership analysis, barriers to inclusion and gender-specific risks (including GBV) and opportunities and entry points for gender-responsive and inclusive programming.

- Validation workshop / presentation

Facilitation of a validation session to present findings from both the baseline and GESI analysis, gather feedback, and validate conclusions with key stakeholders.

Final Evaluation Package - Final reports (baseline evaluation report and GESI analysis report) (English) with finalized annexes (tools, sampling note, ethics & safeguarding summary, DQA summary, updated project MEAL framework and the finalized Data & Analysis Package.

- Timelines

The assignment is expected to be completed within 20 working days from the date of contract signing. The indicative timeline is outlined below:

| Milestone | Number of Days |
| --- | --- |
| Inception report development (including methodology, tools drafting and finalization) | 3 days |
| Enumerator training, tool piloting, and revisions | 2 days |
| Field data collection (quantitative and qualitative) | 7 days |
| Data cleaning, analysis, and synthesis (including gender analysis) | 3 days |
| Draft reports preparation and submission | 3 days |
| Stakeholder review and feedback | 1 day |
| Final reports revision and submission | 1 day |
| Total | 20 days |

- Consultant Qualifications and Experience

The consultant/firm should demonstrate the following qualifications and competencies:

- The proposed team must include, at minimum:
(1) a Peacebuilding/Conflict Analysis Expert with demonstrated expertise in conflict dynamics, governance systems, and social cohesion programming; and
(2) a Gender Equality and Social Inclusion (GESI) Expert with demonstrated expertise in gender analysis, power dynamics, and inclusive programming. Both experts must have clearly defined roles in the assignment.

- Advanced university degree in Peace and Conflict Studies, Gender Studies, Social Sciences, Development Studies, or a related field.

- Minimum of 10 years of relevant professional experience in conducting baseline evaluations, research, or assessments in fragile and conflict-affected contexts.

- Proven experience in Somalia (preferably Mudug or similar contexts), with strong understanding of conflict dynamics, governance systems, and socio-cultural context.

- Demonstrated experience in designing and implementing mixed-methods research, including quantitative and qualitative data collection, sampling, analysis, and triangulation.

- Strong expertise in peacebuilding, conflict analysis, and social cohesion programming, including assessment of peace mechanisms and governance structures.

- Proven experience in gender and social inclusion (GESI) analysis, including power analysis, participation, and barriers to inclusion in governance and peacebuilding processes.

- Experience analyzing the climate–conflict nexus, natural resource management, and/or resilience programming is highly desirable.

- Strong data management and analytical skills, including use of statistical and qualitative analysis software, and ability to generate high-quality, evidence-based insights.

- Demonstrated ability to produce clear, structured, and actionable reports and to effectively engage diverse stakeholders in fragile and conflict-affected contexts.

- Budget

The budget prepared by the bidder should cover all the activities outlined above, including endline evaluation design, data cleaning, analysis and reporting. This budget is inclusive of all costs covering team member costs, travel, vehicle transport within the country, research costs (enumerators) and any other costs associated the completion of the work including where required costs for reasonable adjustment. Bidders are required to organize and fund their own duty of care arrangements as required.

Bidders are required to provide a fully costed proposal in the form of a price schedule that as a minimum should include:

- Sub-total of fees for the delivery of any task or deliverable.

- Sub-total for number of days per partner organization (as applicable);

- Expenses and overheads broken down by the project cost categories.

- Reasonable adjustment costs; and

- Total costs before and after any taxes that are applicable.

- Application and Selection Criteria

Submission requirements

Interested consultants should submit:

- Technical Proposal – including approach, methodology, workplan, and demonstration of understanding of the assignment, including conflict sensitivity and GESI integration.

- Financial Proposal – detailed and itemized budget covering all costs.

- CV(s) of Proposed Team Members – clearly outlining roles and responsibilities, including designated Peacebuilding/Conflict Expert and GESI Expert.

- Relevant Experience – at least three sample reports of similar baseline evaluations, research, or studies conducted in Somalia or similar fragile/conflict-affected contexts.

Evaluation Criteria

The following criteria are mandatory. Failure to meet any will result in automatic disqualification:

- Demonstrated relevant experience - The consultant/firm must provide evidence of having led a minimum of three comparable evaluation or research assignments in Mudug region or similar fragile/conflict-affected regions in Somalia. Failure to submit three sample reports with client references (minimum two) with contact details will result in disqualification.

- Comprehensive and coherent methodological approach - The proposal must present a clear, coherent, and context-appropriate methodology covering the full evaluation process, including design, sampling, data collection (quantitative and qualitative), and analysis. Generic or incomplete methodologies will score zero.

- Qualified team with relevant technical expertise - The proposed team must include key personnel with demonstrated verifiable expertise in peacebuilding, conflict analysis, GESI analysis, and mixed-methods research, with clear roles and relevant qualifications as outlined in the ToR. Failure to meet minimum team qualification requirements will result in zero score.

- HOW TO APPLY

The deadline for submission of bids is 07/04/2026. Interested bidders if you are any clarification or questions send to Mohamed.Abdirizak@care.org,  the bidders should send their applicants to Som.Consultant@care.org with  the Subject line Independent Baseline Evaluation & GESI analysis services for Joint Peace Initiative Project

| Requirement & Specs | Qty. | Unit of Measurement | Required Delivery Lead Time | Delivery Address | Contract Period |
| --- | --- | --- | --- | --- | --- |

[Provide additional requirements]

| Item # | Other Requirements |  |
| --- | --- | --- |
| 1 | Delivery Date & Time | Bidder shall deliver the goods at least ____ weeks after Contract signature. |
| 2 | Delivery Terms (incoterms) | EXW [Ex-works (Place)] |
|  |  | FCA [Free Carrier (Port)] |
|  |  | FAS [Free Along-Side Ship (Port)] |
|  |  | FOB [Free On-Board (Port)] |
|  |  | CFR [Cost, & Freight (Port)] |
|  |  | CIF [Cost, Insurance & Freight (Port)] |
|  |  | CPT [Carriage Paid-To (Place)] |
|  |  | CIP [Carriage & Insurance Paid-To (Place)] |
|  |  | DAP [Delivered at Place (Place)] |
|  |  | DPU [Delivered at Place Unloaded (Place)] |
|  |  | DDP [Delivered Duty Paid (Place)] |
| 3 | Custom Clearance (Must be linked to Incoterms at origin) | Not Applicable. Shall be done by _______________ |
|  |  | Shouldered by CARE |
|  |  | Supplier/ Bidder |
|  |  | Freight Forwarder |
| 4 | Exact Address(es) of Delivery Location |  |
| 5 | Warranty Period | Standard Manufacturer’s Warranty (if applicable) |
| 6 | Payment Terms | 30 Days upon Receipt of items |
| 7 | Quotation Validity | The quote needs to be valid for 90 days to cover all the days from bidding up to the award process. However, once the contract has been released, it shall be valid for the same coverage as reflected in the requirement above. |

[Provide additional requirements]

# PROJECT TIMELINE

All bidders are advised to strictly follow the below timeline as noted.

Any technical questions arising during the preparation of your response to this RFP should be submitted in writing via email to Mohamed.Abdirizak@care.org,  no later than [05/04/2026].

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible | Remarks |
| --- | --- | --- | --- |
| RFP Issued | 07/04/2026 | CARE |  |
| Supplier to notify CARE of intention to participate in bidding |  | Supplier | Deadlines must be strictly observed. |
| Deadline for submission of clarification questions to CARE | 07/04/2026 | Supplier | Deadlines must be strictly observed. |
| CARE to answer all clarifications | 0504/2026 | CARE |  |
| Supplier’s Deadline of Submission of Proposal | 07/04/2026 | Supplier | Deadlines must be strictly observed. |
| Evaluation of Proposal |  | CARE |  |
| Vendor presentation (if required) |  | Supplier |  |
| Finalists selected |  | CARE | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

# PROJECT REQUIREMENTS

- Technical Requirements

a.1 Technical Proposal of the Product

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Overall Proposal Suitability |  |  |
| 1 | Please see the Scope of Work and any other required specifications for this project. |  |
| 2 | Provide Delivery Lead Time |  |
| 3 | Provide after-sales service (if applicable) |  |
| 4 | Ability to provide sample (if applicable) |  |
| 5 | Provide Warranty Period(if applicable) |  |
|  | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Previous Works and Awards |  |  |
| 1 | Provide 3 or more client experiences or testimonials (References whose environment, size, and scope are most similar to CARE. Include a summary of the work completed for each account. Include reference contact names, with telephone numbers and email addresses.) |  |
| 2 | Provide previous records of performance and service. |  |
| 3 | Provide citations and awards. This encompasses reviewing the citations and awards a vendor has received from other customers and award-giving bodies. |  |
| 4 | Provide any testimonials, survey response/s from previous buyers and/or partners. |  |
| 5 | (Any additional requirement that is deemed necessary for “Previous Works & Awards” Category. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Technical Expertise and Organizational Experience |  |  |
| 1 | Provide 5 Availability of vendor’s representatives to call upon and consult with. |  |
| 2 | Any proof that the vendor has the Ability to render satisfactory service in this instance. |  |
| 3 | Provide Years of experience in providing the same requirement to other companies. |  |
| 4 | Provide the latest audited Financial Statement |  |
| 5 | (Any additional requirement that is deemed necessary for “Technical Expertise and Organizational Experience. |  |

| REQUIREMENTS |  | Provide the necessary details. Attach document or provide separate sheet if needed. |
| --- | --- | --- |
| - Others |  |  |
| 1 | Provide any relative requirements which were not mentioned above. (delete if not applicable) |  |

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

# EVALUATION CRITERIA

CARE will evaluate all proposals based on the following criteria.  To ensure consideration for this Request for Proposal, your proposal should be complete and include all of the following criteria:

- Overall Proposal Suitability: proposed solution(s) must meet the scope and needs included herein and be presented in a clear and organized manner

- Previous Work and Awards: Bidders will be evaluated on examples of their work pertaining to the requirement as well as client testimonials and references

- Technical Expertise and Organizational Experience: Bidders must provide descriptions and documentation of staff technical expertise and experience. Bidders also need to provide their experiences as an organization which include but not limited to years of experiences, financial stability, expertise, and edge to other competitors.

- Value and Cost: Bidders will be evaluated on the cost of their solution(s) based on the work to be performed in accordance with the scope of this project.

Note for Country Offices (CO): The specific criteria must closely represent the objective and scope given the nature of the procurement required. Evaluation criteria reflected above can be added and or adjusted depending on the requirement and the type of purchase. The final evaluation criteria must be reflected above prior to releasing of this RFP.

CARE will review proposed budgets and pricing after the initial review of the criteria above.*