Request for Proposal

TOR FOR CONSULTANCY CONDUCT SERVICE MAPPING EXERCISES OF SERVICE PROVIDERS AND REFERRAL PATHWAYS, INCLUDING SERVICES FOR CHILDREN OUTSIDE FAMILY.

GAASHAAN PROJECT – Sustainable Humanitarian Response and Prevention to Protection and GBV risks in Somalia.

RFP DOCUMENT # [__35625____]

RFP Issue Date:  jan 22th 2024]

Proposal submission Deadline :  [Jan  31-2024]

CARE USA

151 Ellis Street NE

Atlanta, GA 30303-2440

Confidential Document

Prepared by

CARE ®

Table of Contents

1.	ABOUT CARE	2

2.	GENERAL CONDITIONS and CLAUSES	2

2.1.    	CARE’s GENERAL CONDITIONS	2

2.2.	CONFIDENTIALITY/ NON-DISCLOSURE	3

2.3.	PUBLICITY	3

2.4.	LIABILITY	3

2.5.	FORCE MAJEURE	3

2.6.	ERRORS AND OMISSIONS	4

2.7.	OWNERSHIP OF WORK	4

2.8.	CONFLICT OF INTEREST	4

3.	COMPANY PROFILE & BIDDER’S DECLARATION	5

3.1.	COMPANY PROFILE	5

3.2.	BIDDER’S DECLARATION	6

4.	CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL	7

4.1.	PROPOSOSAL GUIDELINES	7

4.2.	PROJECT PURPOSE AND DESCRIPTION	7

4.3.	PROJECT OVERVIEW	8

4.4.	PROJECT REQUIREMENTS	9

4.5.	PROJECT TIMELINE	11

4.6.	EVALUATION CRITERIA	11

# ABOUT CARE

At CARE, we seek a world of hope, inclusion, and social justice, where poverty has been overcome and people live with dignity and security.

This has been our vision since 1945, when we were founded to send lifesaving CARE Packages® to survivors of World War II. Today, CARE is a leader in the global movement to end poverty. We put women and girls in the center because we know we cannot overcome poverty until all people have equal rights and opportunities. In 2019, CARE worked in 100 countries and reached 70 million people with an incredible range of life-saving programs.

To know more about CARE, visit: https://www.care.org/our-work/

# GENERAL CONDITIONS and CLAUSES

# CARE’s GENERAL CONDITIONS

The enclosed document is not an offer to contract, but a solicitation of a vendor’s proposed intent.  Acceptance of a proposal in no way commits CARE to award a contract for any or all products and services to any vendor.

CARE reserves the right to make the following decisions and actions based on its business interests and for reasons known only to CARE:

- To determine whether the information provided does or does not substantially comply with the requirements of the RFP.

- To contact any bidder after proposal submittal for clarification of any information provided.

- To waive any or all formalities of bidding

- To accept or reject a proposal in whole or part without justification to the bidder.

- To not accept the lowest bid

- To negotiate with one or more bidders in respect to any aspect of the submitted proposal.

- To award another type of contract other than that described herein, or to award no contract.

- To enter into a contract or agreement for purchase with parties not responding to this RFP

- To request, at its sole discretion, selected Vendors to provide a more detailed presentation of the proposal.

- To not share the results of the bids with other bidders and to award contracts based on whatever is in the best interest of CARE.

Any material statements made orally or in writing in response to this RFP or in response to requests for additional information will be considered offers to contract and should be included by vendor in any final contract.

# CONFIDENTIALITY/ NON-DISCLOSURE

All information gained by any vendor concerning CARE work practices is not to be disclosed to anyone outside those responsible for the preparation of this proposal.  Any discussion by the vendor of CARE’s business practices could be reason for disqualification.  CARE, at their discretion, reserves the right to require a non-disclosure agreement.

Reciprocally, CARE commits that information received in response to this RFP will be held in strict confidence and not disclosed to any party, other than those persons directly responsible for the evaluation of the responses, without the express consent of the responding vendor.

Finally, the information contained within this RFP is confidential and is not to be disclosed or used for any other purpose by the vendor.

# PUBLICITY

Any publicity referring to this project, whether in the form of press releases, brochures, or photographic coverage will not be permitted without prior written approval from CARE.

# LIABILITY

The selected vendor(s) will be required to show proof of adequate insurance at such time as CARE is prepared to procure the services.  The participating vendor will also be required to indemnify and hold harmless CARE for, among other things, any third-party claims arising from the selected vendor’s acts or omissions, and will be liable for any damage caused by its employees, agents or subcontractors.

# FORCE MAJEURE

- Neither Party shall be responsible for a performance that is delayed, hindered, or is rendered inadvisable, commercially impracticable, illegal, or impossible by a “Force Majeure Event.” A Force Majeure event includes, without limitation, an act of nature, a pandemic, emergency, civil unrest, or disorder, actual or threatened terrorism, war, fire, governmental action or interference of any kind, power or utility failures, strikes or other labor disturbances, a health warning issued by the Center for Disease Control (or similar agency), any other civil or governmental emergency and/or any other similar event beyond a Party’s reasonable control.

- The Party that seeks to invoke this Force Majeure provision (the “Affected Party”) shall provide the other Party (the “Unaffected Party”) with a written notice within ten (10) days of the date the Affected Party determines a Force Majeure Event has occurred.

# ERRORS AND OMISSIONS

CARE expects the vendor will provide all labor, coordination, support, and resources required based on the vendor’s proposal and corresponding final SOW.  No additional compensation will be available to the vendor for any error or omission from the proposal made to CARE.  The only exclusions are add-ons, deletions, and/or optional services for which the vendor has received written authorization from CARE.

# OWNERSHIP OF WORK

All work created during this evaluation must be original work, and no third party should hold any rights in or to the work.  All rights, title and interest in the work shall be vested in CARE.

# CONFLICT OF INTEREST

CARE encourages every prospective Supplier to avoid and prevent conflicts of interest, by disclosing to CARE if you, or any of your affiliates or personnel, were involved in the preparation of the requirements, design, specifications, cost estimates, and other information used in this RFP.

# COMPANY PROFILE & BIDDER’S DECLARATION

Bidders are requested to complete this form, including the Company Profile and Bidder’s Declaration, sign it and return it as part of your proposal. No alterations to its format shall be permitted and no substitutions shall be accepted.

# COMPANY PROFILE

Table 4.1.A Previous Work with CARE

| Have you already had previous transactions with CARE? | Yes | No |
| --- | --- | --- |
| If marked “Yes”, please provide the year of the latest transaction with CARE and the requirement that was delivered. (This is to inform everyone that this information is for system checking only. This will not be part of any evaluation process.) |  |  |
| If you marked, “No” on the table above, please answer the Table 4.1.A. below: |  |  |

Table 4.1.B Other Information

| Item Description | Detail(s) |
| --- | --- |
| Legal name of bidder |  |
| Legal Address, City, Country |  |
| Website |  |
| Year of Registration |  |
| Company Expertise |  |
| Bank Information (Please answer below) |  |
| Bank Name: |  |
| Bank Address: |  |
| IBAN: |  |
| SWIFT/BIC: |  |
| Account Currency: |  |
| Bank Account Number: |  |

| Previous relevant experience: 3 contracts |  |  |  |  |
| --- | --- | --- | --- | --- |
| Name of previous contracts | Client & Reference Contact Details | Contract Value | Period of activity | Types of activities undertaken |

# BIDDER’S DECLARATION

| Yes | No |  |
| --- | --- | --- |
|  |  | Ethics: By submitting this Proposal/Quote, I/we guarantee that the bidder has not engaged in any improper, illegal, collusive, or anti-competitive arrangements with any competitors; has not directly or indirectly contacted any buyer representative (aside from the point of contact) or gather information regarding the RFP; and has not attempted to influence or offer any type of personal inducement, reward, or benefit to any buyer representative. |
|  |  | I/We affirm that we will not engage in prohibited behavior or any other unethical behavior with CARE or any other party. We also affirm that we have read the general clause and conditions included in this RFP and that we will conduct business in a way that avoids any financial, operational, reputational, or other undue risk to CARE. |
|  |  | Conflict of interest: I/We warrant that the bidder has no actual, potential or perceived Conflict of Interest in submitting this Proposal/Quote; or entering into a Contract to deliver the Requirements. CARE Procurement's Point of Contact will be notified right away by the bidder if a conflict of interest occurs during the RFP process. |
|  |  | Bankruptcy: l/We have not declared bankruptcy, are not involved in bankruptcy or receivership proceedings, and there is no judgment or pending legal issues that could hinder the ability to conduct business. |
|  |  | Offer Validity Period: I/We confirm that this Proposal/Quote, including the price, remains open for acceptance for the Offer Validity. |
|  |  | I/We understand and recognize that you are not bound to accept any proposal you receive, and we certify that the goods offered in our Quotation are new and unused. |
|  |  | By signing this declaration, the signatory below represents, warrants and agrees that he/she has been authorized by the Organization/s to make this declaration on its/their behalf |

| Supplier Name: |  |
| --- | --- |
| Title/Designation: |  |
| Company Name: |  |
| Date: |  |
| Signature |  |

# CONDITIONS AND GUIDELINES FOR SUBMISSION OF PROPOSAL

# PROPOSOSAL GUIDELINES

This Request for Proposal represents the requirements for an open and competitive process.

All vendors must provide written notification via email to som.consultant@care.org  of their intent to participate, or not to participate in the bidding process by jan 31th  2024

Proposals will be accepted until jan 31th 2024

delivered via email solely to som.consultant@care.org, no later than the above specified date.

Any proposals received after this date and time will not be accepted.  All proposals must be signed by an official agent or representative of the company submitting the proposal.

If the organization submitting a proposal must outsource or contract any work to meet the requirements contained herein, this must be clearly stated in the proposal.  Additionally, all costs included in the proposals must be all-inclusive to include any outsourced or contracted work.  Any proposals which call for outsourcing or contracting work must include the name and description of the organizations being contracted.

All costs must be itemized to include an explanation of all fees and costs.

Contract terms and conditions will be negotiated upon selection of the winning bidder for this RFP.  All contractual terms and conditions will be subject to review by the CARE legal department, and will include scope, budget, schedule, and other necessary items pertaining to the project.

You must respond to every subsection including statement, question, and/or instruction without exception.

Any verbal information obtained from, or statements made by representatives of CARE shall not be construed as in any way amending this RFP.  Only such corrections or addenda as are issued in writing by CARE to all RFP participants shall be official.  CARE will not be responsible for verbal instructions.

# PROJECT PURPOSE AND DESCRIPTION

CARE is issuing this RFP (Request for Proposal) soliciting qualified bidders to submit proposals intended for the  CONSULTANCY CONDUCT SERVICE MAPPING EXERCISES OF SERVICE PROVIDERS AND REFERRAL PATHWAYS, INCLUDING SERVICES FOR CHILDREN OUTSIDE FAMILY.

GAASHAAN PROJECT – Sustainable Humanitarian Response and Prevention to Protection and GBV risks in Somalia.

This RFP is an invitation to bid, not an offer of contract.  Bidders must submit a response that complies with the minimum requirements contained herein

.

  - BACKGROUND TO THE PROJECT

The GAASHAN Programme (Somali word for shield or protect) aims to provide sustainable and comprehensive humanitarian response and prevention to protection and GBV risks for marginalized and hard to reach communities in humanitarian hotspot areas in South Central Somalia.

The project will reach 43,756 direct beneficiaries (10,528 men, 21,533 women, 2,850 boys and 8,845 girls of whom 5% people with disabilities) in 18 districts across 9 regions in South Central Somalia. We will also reach an estimated 117,200 indirect beneficiaries (46,452 men, 59,748 women, 5,000 boys, and 6,000 girls).

The target districts have been prioritized as they experience consistently high levels of humanitarian needs and face the compounding effects of conflict and climate-related shocks and stressors, making populations vulnerable to gender based violence (GBV) and abuse. These districts are among the priority locations in the 2023 Somalia Humanitarian Response Plan (HRP) due to the magnitude and severity of needs following the five-season drought. In addition, El Nino is projected during the October to December Deyr rainfall season, resulting in excess rainfall and flooding. There are increased risks of flooding along the main rivers of Juba and Shabelle, leading to displacement, loss of lives, livelihoods and infrastructure, and heightening the risk of disease outbreaks. This threatens to worsen the humanitarian situation in these hotspot areas.

The project will also target locations in newly liberated areas which lack/have low humanitarian service provision, especially for protection and GBV services. The Programme will build on the consortium’s programming experience in delivery of prevention and response services in humanitarian contexts. We will continue targeting the most vulnerable communities who have been impacted by displacement due to conflict and climate-induced shocks, especially in hard to reach or newly accessible areas.

The GAASHAAN Programme will embed learnings from Phases I and II of the CHANGES project and adapt the approaches for a humanitarian response. The consortium will make use of several key approaches that have been proven efficient and effective in the Somali context:

- Centrality of Protection (CoP) will ensure the individual and collective responsibility to focus on protecting the vulnerable from harm caused by human rights violations on children as a central purpose of humanitarian action.

- Accountability to Affected People (AAP) will consider the needs of the targeted communities, with a focus on minorities and marginalized groups. This will be done by ensuring community-based feedback/complaint mechanisms which are inclusive, gender- and age-friendly.

- Adaptive management approach considering the diverse needs and complexity of the context to be agile and adapt to the ever-changing context and situation in Somalia

| Requirement & Specs | Qty. | Unit of Measurement | Required Delivery Lead Time | Delivery Address | Contract Period |
| --- | --- | --- | --- | --- | --- |
| TOR FOR CONSULTANCY CONDUCT SERVICE MAPPING EXERCISES OF SERVICE PROVIDERS AND REFERRAL PATHWAYS, INCLUDING SERVICES FOR CHILDREN OUTSIDE FAMILY. GAASHAAN PROJECT – Sustainable Humanitarian Response and Prevention to Protection and GBV risks in Somalia. | 1 |  |  | this service mapping will be focus on Gedo (Belet Hawo and Dolow districts) and Lower Juba (Kismayo, Afmadhow and Dhobley districts) | 17 days |

| Item # | Other Requirements |  |
| --- | --- | --- |
| 1 | Delivery Date & Time | Bidder shall deliver the service at least ____ weeks after Contract signature. |
| 2 | Delivery Terms (incoterms) | EXW [Ex-works (Place)] |
|  |  | FCA [Free Carrier (Port)] |
|  |  | FAS [Free Along-Side Ship (Port)] |
|  |  | FOB [Free On-Board (Port)] |
|  |  | CFR [Cost, & Freight (Port)] |
|  |  | CIF [Cost, Insurance & Freight (Port)] |
|  |  | CPT [Carriage Paid-To (Place)] |
|  |  | CIP [Carriage & Insurance Paid-To (Place)] |
|  |  | DAP [Delivered at Place (Place)] |
|  |  | DPU [Delivered at Place Unloaded (Place)] |
|  |  | DDP [Delivered Duty Paid (Place)] |
| 3 | Custom Clearance (Must be linked to Incoterms at origin) | Not Applicable. Shall be done by _______________ |
|  |  | Shouldered by CARE |
|  |  | Supplier/ Bidder |
|  |  | Freight Forwarder |
| 4 | Exact Address(es) of Delivery Location | Please provide addresses |
| 5 | Warranty Period | Standard Manufacturer’s Warranty (if applicable) |
| 6 | Payment Terms | 30 Days upon Receipt of items |
| 7 | Quotation Validity | The quote needs to be valid for 90 days to cover all the days from bidding up to the award process. However, once the contract has been released, it shall be valid for the same coverage as reflected in the requirement above. |

# PROJECT TIMELINE

All bidders are advised to strictly follow the below timeline as noted.

Any technical questions arising during the preparation of your response to this RFP should be submitted in writing via email to Kenneth.Marimira@care.org  no later than Jan 25th, 2024

| Schedule of Activities/ To-do | Date of the Activity/ Deadline of Submission | Responsible | Remarks |
| --- | --- | --- | --- |
| RFP Issued | Jan 22th 2023 | CARE |  |
| TOR FOR CONSULTANCY CONDUCT SERVICE MAPPING EXERCISES OF SERVICE PROVIDERS AND REFERRAL PATHWAYS, INCLUDING SERVICES FOR CHILDREN OUTSIDE FAMILY. GAASHAAN PROJECT – Sustainable Humanitarian Response and Prevention to Protection and GBV risks in Somalia. | jan 31th, 2023, | Supplier | Deadlines must be strictly observed. |
| Deadline for submission of clarification questions to CARE | Jan 21 th 2024 | Supplier | Deadlines must be strictly observed. |
| CARE to answer all clarifications | Until 25 janth 2024 | CARE |  |
| Supplier’s Deadline of Submission of Proposal | 31-jan 2023 | Supplier | Deadlines must be strictly observed. |
| Finalists selected | n/a | CARE | Upon notification, the contract negotiation with the winning bidder will begin immediately. |

# PROJECT REQUIREMENTS

- Technical Requirements

a.1 Technical Proposal of the Product

See below TOR

TOR FOR CONSULTANCY CONDUCT SERVICE MAPPING EXERCISES OF SERVICE PROVIDERS AND REFERRAL PATHWAYS, INCLUDING SERVICES FOR CHILDREN OUTSIDE FAMILY.

GAASHAAN PROJECT – Sustainable Humanitarian Response and Prevention to Protection and GBV risks in Somalia.

Background.

The GAASHAN Programme (Somali word for shield or protect) aims to provide sustainable and comprehensive humanitarian response and prevention to protection and GBV risks for marginalized and hard to reach communities in humanitarian hotspot areas in South Central Somalia.

The project will reach 43,756 direct beneficiaries (10,528 men, 21,533 women, 2,850 boys and 8,845 girls of whom 5% people with disabilities) in 18 districts across 9 regions in South Central Somalia. We will also reach an estimated 117,200 indirect beneficiaries (46,452 men, 59,748 women, 5,000 boys, and 6,000 girls).

The target districts have been prioritized as they experience consistently high levels of humanitarian needs and face the compounding effects of conflict and climate-related shocks and stressors, making populations vulnerable to gender based violence (GBV) and abuse. These districts are among the priority locations in the 2023 Somalia Humanitarian Response Plan (HRP) due to the magnitude and severity of needs following the five-season drought. In addition, El Nino is projected during the October to December Deyr rainfall season, resulting in excess rainfall and flooding. There are increased risks of flooding along the main rivers of Juba and Shabelle, leading to displacement, loss of lives, livelihoods and infrastructure, and heightening the risk of disease outbreaks. This threatens to worsen the humanitarian situation in these hotspot areas.

The project will also target locations in newly liberated areas which lack/have low humanitarian service provision, especially for protection and GBV services. The Programme will build on the consortium’s programming experience in delivery of prevention and response services in humanitarian contexts. We will continue targeting the most vulnerable communities who have been impacted by displacement due to conflict and climate-induced shocks, especially in hard to reach or newly accessible areas.

The GAASHAAN Programme will embed learnings from Phases I and II of the CHANGES project and adapt the approaches for a humanitarian response. The consortium will make use of several key approaches that have been proven efficient and effective in the Somali context:

- Centrality of Protection (CoP) will ensure the individual and collective responsibility to focus on protecting the vulnerable from harm caused by human rights violations on children as a central purpose of humanitarian action.

- Accountability to Affected People (AAP) will consider the needs of the targeted communities, with a focus on minorities and marginalized groups. This will be done by ensuring community-based feedback/complaint mechanisms which are inclusive, gender- and age-friendly.

- Adaptive management approach considering the diverse needs and complexity of the context to be agile and adapt to the ever-changing context and situation in Somalia

Project Locations

The multi-year programme is targeting 18 districts across nine regions in Somalia, this service mapping will be focus on Gedo (Belet Hawo and Dolow districts) and Lower Juba (Kismayo, Afmadhow and Dhobley districts)

Objectives of the Consultancy

- Conduct comprehensive service mapping exercises to identify and document service providers and referral pathways, with a specific focus on services for children outside family care.

- Analyze the availability, accessibility, and quality of services provided by different stakeholders in the target areas.

- Identify gaps and challenges in service provision and referral systems.

Methodology:

- Define the scope of the mapping exercise by specifying the geographic area, types of services for children, and any specific criteria or age groups to be included.

- Identify key stakeholders such as service providers, government agencies, NGOs, community organizations, and parents or guardians of children.

- Conduct a literature review to gather existing information and data on services for children outside family use, including relevant reports, studies, and official documents related to child welfare and social services.

- Create data collection tools, such as surveys, interview guides, or questionnaires, to gather information from stakeholders. Include questions about service types, availability, accessibility, quality, and coordination.

- Engage with stakeholders and collect primary data through surveys, interviews, focus groups, or workshops, ensuring representation from a diverse range of service providers and individuals involved in referral pathways.

- Analyze the collected data using qualitative and quantitative analysis techniques to identify key service providers, referral pathways, gaps or bottlenecks, and areas for improvement.

- Develop visual representations of the service providers and referral pathways using mapping tools to visualize relationships and identify any gaps or overlaps in service provision.

- Validate the findings with stakeholders, incorporating their feedback and suggestions for improvement, to ensure the accuracy and completeness of the service maps.

- Based on the analysis and stakeholder input, identify recommendations for improving service coordination, addressing gaps, and enhancing overall service quality for children outside family use.

- Prepare a comprehensive report summarizing the findings, service maps, and recommendations, and share it with relevant stakeholders, policymakers, and organizations involved in child welfare or social service provision.

- Regularly monitor and evaluate the implementation of the recommendations to measure their impact and make necessary adjustments, aiming for continuous improvement in service provision for children.

Scope

The consultancy will focus on the following areas:

- Service Providers Mapping:

- Identify and map all relevant service providers within the target area or community.

- Include government agencies, non-governmental organizations (NGOs), community-based organizations, and private service providers in the mapping exercise.

- Document the services offered by each provider, their target beneficiaries, and geographical coverage.

- Referral Pathways Mapping:

- Understand and document the existing referral pathways for children outside family use.

- Map the process of referral from one service provider to another, including any criteria, procedures, and decision-making mechanisms involved.

- Identify any bottlenecks or challenges in the referral process.

- Services for Children Mapping:

- Identify and document the range of services available for children outside family use.

- Include general services such as education, healthcare, and social support, as well as specialized services for specific needs (e.g., child protection, mental health, disability support).

- Assess the availability, accessibility, and quality of these services.

Tasks and Responsibilities

The consultancy will involve the following tasks and responsibilities:

- Desk Review:

- Conduct a comprehensive desk review of existing reports, studies, and relevant documents related to the target area, service providers, and referral pathways.

- Identify gaps in existing knowledge and gather preliminary information to guide the mapping exercises.

5.	Stakeholder Engagement:

- Identify and engage key stakeholders, including government authorities, NGOs, service providers, and community representatives, to ensure their participation and collaboration throughout the mapping exercises.

- Conduct meetings, interviews, and workshops to gather insights and ensure a comprehensive understanding of the local context.

6.	Data Collection:

- Develop appropriate data collection tools, such as surveys, questionnaires, and interview guides, to collect comprehensive and detailed information about service providers, referral pathways, and services for children.

- Conduct interviews, focus group discussions, and site visits to collect primary data from the identified stakeholders.

- Ensure ethical data collection practices are followed, with respect for privacy and confidentiality.

7.	Data Analysis:

- Analyze the collected data to identify patterns, gaps, and overlaps in the services provided.

- Assess the strengths and weaknesses of the existing referral pathways and services.

- Use appropriate analytical methods and tools to generate meaningful insights.

- 8.	Reporting:

- Prepare a comprehensive report documenting the findings of the service mapping exercises.

- Include detailed information about service providers, referral pathways, and services for children, highlighting areas of improvement and potential interventions.

- Present the findings in a clear and concise manner, using visual aids and data visualization techniques if necessary.

9.	Recommendations:

- Provide actionable recommendations to improve the service delivery and referral system for children outside family use.

- Consider the identified gaps, challenges, and opportunities for enhancing service provision and coordination.

- Suggest strategies for strengthening the referral process and increasing access to necessary services.

Deliverables

The consultancy is expected to produce the following deliverables:

- Desk review report summarizing the existing information about the target area, service providers, and referral pathways.

- Utilize data collection tools, including surveys, questionnaires, and interview guides used during the mapping exercises shared by the organization or developed with approval from IRC members.

- Comprehensive report presenting the findings, analysis, and recommendations from the service mapping exercises.

- Presentation slides summarizing the key findings and recommendations for dissemination and stakeholder engagement.

- Dissemination plan outlining strategies for sharing the final report with relevant stakeholders and wider audiences.

Expected duration of the assignment

The consultancy shall be executed within a maximum of 17 days commencing after signing the contract. The proposal should include a detailed schedule.

| Milestone | Deadline dates |
| --- | --- |
| Desk Review | 2 |
| Stakeholder Engagement | 3 |
| Data Collection | 7 |
| Data Analysis | 4 |
| Reporting | 1 |
| Total | 17 |

Budget

The budget prepared by the consultant should cover all the activities outlined above, including design, data collection, cleaning, analysis, and reporting. This budget is inclusive of all costs covering team member costs, travel, Enumerator training research costs and any other costs associated with the completion of the work including where required costs for reasonable adjustment. The selected consultant is required to organize and fund their own duty of care arrangements as required.

The consultant/s is required to provide a costed proposal in the form of a price schedule that as a minimum should include:

- Sub-total of fees for the delivery of any task or deliverable.

- Expenses and overheads broken down by deliverables.

- Reasonable adjustment costs

Proposals should include the following:

- Technical proposal –approach to the study; work plan with milestones; how meet qualifications.

- Financial proposal

- CVs of all involved persons

- Professional Skills and Qualifications

Qualifications: The selected consultant/s is required to clearly identify and provide CVs for all those proposed in the team, clearly stating their roles and responsibilities for the study. The Master’s Degree in an area relevant to the assignment, such as gender equality.

The proposed person or team should include the technical expertise and practical experience required to deliver the scope of work and outputs, in particular, concerning:

- Design: the team should include skills and expertise required to design, plan and conduct electronic data collection in fragile contexts, including developing qualitative and quantitative tools.

- Experience with studies and research on gender, social inclusion, and conflict in Somalia

- Relevant subject matter knowledge and experience: at least 5 years of experience required on conducting research with women and girls in conflict areas, gender and social inclusion, socio cultural practices and beliefs, to ensure that the design and methods are as relevant and meaningful as possible given the aims and objectives of the project and the context in which it is being delivered.

- Data collection management: manage a data collection process from end-to-end.

- Country experience: it is particularly important that the team has the appropriate country knowledge /experience and ability to interpret findings from a contextual perspective, as required to conduct the research.

- Data management and data cleaning.  Ability to supervise the collection, entry (if required), cleaning and management of large data sets.

- Safety and ethical considerations: Ensuring the whole process adheres to best practice for research with children including the implementation of child protection policy and procedures to ensure safety of participants.

Application Procedure

The interested candidates are requested to submit:

- Technical proposal showing how the consultant intends to carry out the consultancy.

- Financial proposal

- Qualifications

- Relevant experience related to the assignment including samples and references of most recent similar work done.

- VALUE & COST (Financial Requirements)

- The table below gives the specific requirement for the assignment which the proposed vendor must quote for below:

- For value and cost, please submit a realistic and detailed budget.

- Expected duration of the assignment

- The consultancy shall be executed within a maximum of 17 days commencing after signing the contract. The proposal should include a detailed schedule.

| Milestone |  | Deadline dates |
| --- | --- | --- |
| Desk Review |  | 2 |
| Stakeholder Engagement |  | 3 |
| Data Collection |  | 7 |
| Data Analysis |  | 4 |
| Reporting |  | 1 |
| Total |  | 17 |

Compliance with Requirements

|  | Yes, we will comply | No, we cannot comply | If marked as “No”, please provide counter proposal |
| --- | --- | --- | --- |
| Minimum Technical Specifications |  |  |  |
| Delivery Lead Time |  |  |  |
| Delivery Term (INCOTERMS) |  |  |  |
| Warranty Period (if applicable) |  |  |  |
| Validity of Quotation |  |  |  |
| Payment Terms (30 Days after service delivery) |  |  |  |
| Other Requirements (Please specify) |  |  |  |

# EVALUATION CRITERIA

CARE will evaluate all proposals based on the following criteria.  To ensure consideration for this Request for Proposal, your proposal should be complete and include all the following criteria:

Qualifications:

The selected consultant/s is required to clearly identify and provide CVs for all those proposed in the team, clearly stating their roles and responsibilities for the study. The Master’s Degree in an area relevant to the assignment, such as gender equality.

The proposed person or team should include the technical expertise and practical experience required to deliver the scope of work and outputs, in particular, concerning:

- Design: the team should include skills and expertise required to design, plan and conduct electronic data collection in fragile contexts, including developing qualitative and quantitative tools.

- Experience with studies and research on gender, social inclusion, and conflict in Somalia

- Relevant subject matter knowledge and experience: at least 5 years of experience required on conducting research with women and girls in conflict areas, gender and social inclusion, socio cultural practices and beliefs, to ensure that the design and methods are as relevant and meaningful as possible given the aims and objectives of the project and the context in which it is being delivered.

- Data collection management: manage a data collection process from end-to-end.

- Country experience: it is particularly important that the team has the appropriate country knowledge /experience and ability to interpret findings from a contextual perspective, as required to conduct the research.

- Data management and data cleaning.  Ability to supervise the collection, entry (if required), cleaning and management of large data sets.

- Safety and ethical considerations: Ensuring the whole process adheres to best practice for research with children including the implementation of child protection policy and procedures to ensure safety of participants.

- Relevant experience related to the assignment including samples and references of most recent similar work done.

Note for Country Offices (CO): The specific criteria must closely represent the objective and scope given the nature of the procurement required. Evaluation criteria reflected above can be added and or adjusted depending on the requirement and the type of purchase. The final evaluation criteria must be reflected above prior to releasing of this RFP.

CARE will review proposed budgets and pricing after the initial review of the criteria above.*