## Sheet1
Name of Region: Sool
Name of District: Las-Anod
Name of School: Abyan P-School
Type of work: (11.2Mx8.1M) Construction of School Mini Library in target schools.
No | Description of Item | Unit | Quantity | Rate USD | Amount USD
A) Site Clearance and construction of Foundation
1 | Site clearance from the debris, demolishing of existing four latrines. This including all necessary transport. | LS | 1
2 | B) Floor Construction
3 | Remove the exsisting Concrete Floor and Provide and laying of 40x40 cm of Emirates ceramic floor tiles non-slip. Use very quality and ALIGHT Engineer will aprove. This including skirting tiles(Baseboard) and verandah | M2 | 100
12 | C) Wall Construction
13 | Carrefully demolish and remove the exsisting partition wall measuring 6m length and 3.5m height including disposal of debris to an approved location. Then reconstruct 20cmx20cmx40cm concrete hollow block walls. Walls joined with cement /sand mortar of 1:4 mix. the partition wall will extend the library area by 1.8 m into the adjacent classroom, this include lintel shelves walls and ALIGHT Engineer will aprove. | M² | 30
14 | Repalce the exsisting GI pipe columns and reconstruction of four(4) 20x20cm of RCC Column with reinforced 4Y12mm dia and 6mm dia as column ties with space 20cm C/C at the Veranda. The height of the column does not exceed 3m. this including 50cm below the GL and exavation of column footings. Follow working drawings. Including column necks. and Alight engineer will approve. | M3 | 1.5
16 | Construction of 12 cm thick RCC continuous lintels above the reconstructed wall and avove the coloums of veranda. 1:2:4 (1-2” maximum aggregate size) mix. ratio with (4) 12mm rebars and 20 cm c/c staffs use 6mm dia bars. Concrete to be thoroughly tamped/ vibrated. And cured 4 days min. this also including top slab of shelves. and ALIGHT engineer will aprove. | M³ | 1.5
18 | Construction of concrete ramp of 2m wide at the lowest side of the building including handrail, the slope of the ram to be not more than 12 degrees, the ram must have local floor tiles on it as instructed by ALIGHT engineer. | Job | 1
19 | D) Roof Works
20 | Replace the damaged iron sheets and paint library's iron sheet with ALIGHT engineer's aprove). this includes 4 pcs of transparent iron sheet to prevent bat. | lms | 1
21 | Repair the damaged ceiling and Fixing 4mm wooden ceiling board in all library Hall including varendah. | lms | 1
22 | Fasten 20 cm fascia board around the entire building. Joints are to be attached by wooden joints or metal straps. this includes painting. color of paint to be identified by the ALIGHT Engineer. | ML | 40
24 | E) Plastering and Painting
25 | (2) Coats of cement/sand plastering on the reconstructed interior wall faces and all damaged wall faces. The mix ratio is 1:4 (sand-cement). | lms | 1
26 | (2) Coats of white-washing on all wall faces and ceiling with 1:275 lime/white glue ratio on all interior wall surfaces to be smoothed thoroughly before paint applied. | M² | 75
27 | (2) Coats of emulsional paint (oil paint) on all wall exterior walls and emulsion paint on the interior of wall surfaces. The color of the paint is to be identified by the Alight Engineer and all internal walls will be emulsion paint. | M² | 165
28 | ALIGHT -MOE and GPE writing on cement wall as instructed by ALIGHT engineer. | NO | 1
29 | Visibility for both Alight International logo and Donor logo and scripture ( Metal board) (1.5x1m) | NO | 1
30 | F) Doors, and Windows
31 | Replace the exsisting door and Provide and install main entrance doors for metal Eithopian doors 1.2m wide and 2.1m high complete with frame, hinges & security locks, and include two coats of gloss paint. Use box 4x5cm of main frame, 3x3cm of secondary metals, and 1.2mm of iron sheet. NB: approve sample for ALIGHT engineer. | No | 1
32 | Supply and install 2-leaf PVC frame for aluminum with glass slide window size 1.5 m wide and 1.5m high with PVC frame and security mesh with screen with x-beam. The color of the window is to be confirmed by the ALIGHT engineer. | No | 6
33 | G)Library furniture and electric installation.
34 | Provide and install of 20mm thickness of laminated plwood for wall shelves with dimension 60cm wide and 40cm height. | M2 | 60
35 | Provide Reading table of Library - with dimensions 1.60m length, 0.8m wide and 0.75m height, use metallic frame and length and use liminated supper wood with well finished at all joints as labelled on attached drawing and directed by the Engineer). | Pcs | 4
36 | Provide Library Reading Chairs- use imported chair follow attached drawings and verify technical engineers before you provide more details See drawings for detail. | NO | 40
37 | Provide of secretary chair for librarian person. See attached design. | NO | 2
38 | 1.6m long L-shaped executive imported table complete for librarian space. | NO | 1
39 | Supply and install Suadi Arabian electric wire with its appliances like 3 lamp holders with 3 lamps and, 8 electric sockets, a circuit controller, an electric breaker, an electric Watch, and three ceiling farms. follow instruction of engineer and drawings. | LS | 1
40 | Clearning site after construction complete following instruction of ALIGHT Engineer must remove all risk material on site. | LS | 1
Grand total Construction of Abyan P-School Mini Library | Estimated Total Cost for New Gabiley Primary ECE