# TERMS OF REFERENCE

Oxfam is a global movement of people who are fighting inequality to end poverty and injustice. Across regions, from the local to the global, we work with people to bring change that lasts.

| OVERVIEW |  |
| --- | --- |
| Title and brief description of the assignment | Call for expressions of interest: Consultancy for Establishing a Civil Society Network for Climate Action in Somalia and Somaliland. |
| Assignment location | Somaliland , Puntland And South Central |
| Contract start date | 01st March , 2026 (tentatively) |
| How to apply | Interested candidates are invited to submit with the following documents: - A technical proposal with a detailed response to the TOR, with a specific focus on the scope of work, methodology, and timelines. - Initial work plan and an indication of availability. - A financial proposal detailing the daily rate expected including accommodation, transportation, stationery, taxes arising from the consultancy service (6% tax for National consultant and 12 % tax for international consultants), and all other costs related to this assignment. (Operational and consultancy fees). - Curriculum Vitae(s) (CV) of the proposed consultant(s), proving relevant experience and/or qualifications. If multiple people are involved, an outline of roles/ responsibilities also needs to be included. - Evidence of conducting previous similar work by providing minimum two signed contracts / purchase orders (preferably from UN agencies and INGOs). - Two relevant references (minimum) for previous comparable assignments. - Proof of registration: The bidders also must include a copy of their registration at the relevant authority. See section ‘7. Application Process’ for further details |
| Application deadline | 21st Feb, 2026. |
| Specific considerations |  |

# PURPOSE OF THIS CONSULTANCY

# Oxfam is a global movement of people working together to end the injustice of poverty. Together we save, protect, and rebuild lives. We won’t stop until every person on the planet can defeat poverty or any type of inequality or discrimination. We are an international confederation of 19 organizations (affiliates) working together with partners and local communities in the areas of humanitarian aid, resilience building, development, and campaigning, in more than 90 countries. All our work is led by three core values: Empowerment, Accountability, Inclusiveness.

# Somalia/Somaliland is one of the world’s most climate vulnerable countries, facing recurrent droughts, floods, displacement and rapid environmental degradation. Civil society organizations (CSOs) play an essential role in bridging the gap between community needs, national climate policies, and global climate processes. However, climate focused CSO in Somalia remain fragmented with limited coordination, weak collective  advocacy, inconsistent engagement with government institutions and inadequate access to climate finance mechanisms..

# Oxfam Somali through Localization Investment Fund of Oxfam Ireland, is supporting the establishment of a nationwide Climate Action CSO Network with sub national chapters across Somalia/Somaliland. The network aims to bring together 250+ CSOs working on climate, environment, resilience, policy advocacy, and sustainable development by leveraging access to financial services to accelerate climate mitigation, and adaptation measures.To strengthen collection, policy influence, resource mobilization and ensure locally led climate response, its necessary to establish a national CSO network for climate action in Somalia/Somaliland with clear governance systems, legal standing and required capacity.

# SCOPE OF WORK

We are seeking an expression of interest from experienced individuals or consultant firms to design, facilitate and support the establishment of a nationally recognized CSO network for climate action in Somalia including its legal and regulatory framework, governance and institutional structures, operational modalities, policies and financial sustainability mechanisms.

## Overall objective

To establish a functional, legally compliant, inclusive and sustainable CSO network that strengthens civil society leadership and coordination on climate action in Somalia.

## Specific Objectives

# Map and engage existing climate related CSOs across Somalia in collaboration with relevant government/INGOs agencies

# organize and facilitate meetings to bring together existing CSO networks and support them formalization and institutionalization process

# Develop the neworks legal registration and compliance framework

# Establish inclusive governance and decision making strucures

# Develop operational systems, policies and modalities

# Develop a financial plan for the CSO 3-5 years of operation.

# Scope Of The work

# The consultant will take the following tasks:

# Task: institutional mapping and capacity assessment

# 1.	Stakeholder mapping and needs assessment (map national, regional and CBOs working on climate mitigation, adaptation, ecosystem restoration, sustainable livelihoods, NRM, assessment coordination gaps in consultation with relevant government agencies) .

# Task 2: Legal and regulatory framework

# The consultant shall finalize and propose the legal basis for the network in line with Somali laws and international best practice including applicable governing laws and policies (provisional constitution, - 2012, NGO/CSO registration laws, environmental and climate change policies, NDC, NTP). Draft constitution/bylaws, recommend legal structure, membership criteria and code of conduct, registration road map etc.

# Task 3: governance and institutional structures

# Design a governance system that is transparent, inclusive, gender responsive and accountable such as governance bodies (general assembly, BOD, ES,  Technical working groups, advisory council with clear mandates for each organ, decision making and voting procedures, conflict of interest and accountability mechanisms, gender, PWD, and marginalized group representation quotes.

# Task 4:  operational systems and policies (develop core operational frameworks: strategic plan 3-4 yrs, annual work plan and budgeting framework, financial mgt and procurement policies, safeguarding, PSEA and do no harm policies, human resource policies etc)

# Task 5: infrastructure, facilities and amenities

# Define minimum and scalable operational requirements (office space, equipment, meeting and training facilities, storage, websites etc)

# Task 6: advocacy, policy engagement and partnership Define mechanisms for structured engagement with federal and member state, UNFCCC processes, climate finance institutions (GCF, adaptation fund, FRLD), establish partnership and MoU frameworks.

# Tasks 7: Resource mobilization and financial sustainability

# Develop a diversified financing model (membership contributions, donor funding, service provision and grants management, climate finance readiness support)

## Planned timeline

The assignment will be conducted with an estimated duration of 40 days from the date of signing the contract.

# DELIVERABLES AND PAYMENT SCHEDULE

Remuneration is based on submission of final deliverables according to the schedule below.

| No. | Deliverables or Documents to be delivered | Estimated Dates | % Payment |
| --- | --- | --- | --- |
| 1 | DELIVERABLE 1 Inception report and Desk review – (Work plan, agreed. | 03rd March, 2026 | 40% |
| 2 | DELIVERABLE 2 Midpoint update presentation - (Stakeholder / Institutional Mapping and Needs Assessment Report- Comprehensive mapping of CSOs and key stakeholders in Somalia and Somaliland, including institutional capacity analysis and identification of priority needs. - Legal and Governance Framework- Draft legal and governance framework for the CSO climate action network, including constitutions, bylaws, and governance structures. - Institutional and Operational Systems Package- Development of institutional and operational systems, including operational guidelines, coordination mechanisms, and internal management systems. - Three-to-Five-Year Strategic Plan and Budgeted Action Plan | 18th March ,2026 |  |
| 3 | DELIVERABLE 3 Draft report submitted to Oxfam for comments. | 31st March 2026 |  |
| 4 | DELIVERABLE 4 Final report submitted and approved by Oxfam. | 10th April 2026 | 60% |
| TOTAL |  |  | 100% |

# PROFILE REQUIREMENTS

The company/ individual(s) should have the following competencies:

Essential

- Advanced degree in Climate Change, Environmental Science /Policy, International Development, Governance, or related field.

- Minimum 10 years’ experience in institutional development, civil society network development.

- Proven experience drafting governance documents (statutes, constitutions, charters).

- Experience facilitating multi stakeholder processes in fragile contexts.

- Strong understanding of Somal’s climate policy environment.

- Excellent communication skills in English; Somali language is an advantage.

# APPLICATION PROCESS

## Submission deadline

Quotations and applications must reach Oxfam no later than [21st Feb 2026].

## Submission instructions

- Responses must be submitted electronically to: SOM-Consultancies@oxfam.org

- The subject of the mail should be Call for expressions of interest: Consultancy for Establishing a Civil Society Network for Climate Action in Somalia and Somaliland

- All attached documents should be clearly labelled so it is clear to understand what each file relates to.

## Clarifications

Any questions, remarks or requests for clarification can be sent up to 6 days before the submission deadline in writing. The (anonymised) questions will be answered to all applicants.

## Administrative compliance (list of documents to be submitted)

Responses must be submitted and prepared in [English] and received by the deadline.

To be shortlisted for evaluation against award criteria, the following documents must be included in the application:

| Administrative Criteria |  | Importance |
| --- | --- | --- |
| 1 | Technical proposal / approach paper to conduct the assignment and achieve objectives including methodology, proposed work plan and timelines | Mandatory |
| 2 | Financial offer (price quotation) including budget and pricing A financial proposal detailing the daily rate expected including accommodation, transportation, stationery, taxes arising from the consultancy service (6% tax for National consultant and 12 % tax for international consultants), and all other costs related to this assignment. (Operational and consultancy fees) | Mandatory |
| 3 | Curriculum Vitae(s) (CV) of the proposed consultant(s), proving relevant experience and/or qualifications. If multiple people are involved, an outline of roles/ responsibilities also needs to be included. | Mandatory |
| 4 | Two relevant references (minimum) for previous comparable assignments | Mandatory |
| 5 | Proof of registration: The bidders also must include a copy of their registration at the relevant authority. | Mandatory |
| 6 | Evidence of conducting previous Similar work by providing minimum two Signed Contracts / Purchase Orders - (Preferably from UN agencies and INGOs). | Mandatory |

## Evaluation and award criteria

Incomplete applications will not be assessed, only quotations that meet the administrative criteria will be assessed.

Award decisions will be based on best value for money criteria covering both technical quality and price.

The award criteria are assessed according to the following distribution of points:

| Award Criteria |  | Max. points |
| --- | --- | --- |
| Technical offer/ approach paper evaluation |  |  |
| Experience/ competencies | Relevant experience with the NGO sector | 5% |
|  | Positive references/reputation | 5% |
|  | Relevance and quality of sample previous work, reporting etc. | 5% |
|  | Knowledge of country, context | 5% |
|  | Knowledge of team languages | 5% |
|  | Clearly indicated alignment with Oxfam values | 5% |
| Technical quality | Quality of application: complete, good presentation and format, etc. | 9% |
|  | Understanding of the assignment and the scope of the project | 9% |
|  | Quality of the methodology, workplan and feasibility of the timeline (concrete and realistic) | 9% |
|  | Quality and experience of staff resources assigned to the services + sufficient assigned resources (where relevant) | 9% |
|  | Ability to lead/manage a team (where relevant) | 9% |
| TOTAL: |  | 75% |
| Financial offer |  |  |
| Financial offer | Submission of realistic and acceptable financial proposal – reasonable budget breakdown and cost consideration detailing the daily rate expected including travel, accommodation, transportation, stationery, taxes arising from the consultancy service (6% tax for National consultant and 12 % tax for international consultants), and all other costs related to this assignment. (Operational and consultancy fees). The lowest evaluated financial proposal that meets the administrative criteria will be awarded the maximum point (25%). The points for all other Applications will be prorated. | 25% |
| GRAND TOTAL: |  | 100% |

Oxfam withholds the right to conduct interviews with one or more potential applicants before an award decision is made. The purpose of the interview is to seek further clarification on the submitted documents and learn more about the background and previous experiences of the potential suppliers and their teams.

# OTHER CONDITIONS

Issuance of this Terms of Reference does not constitute an award commitment on the part of Oxfam, nor does it commit Oxfam to pay for costs incurred in the preparation and submission of a bid.

The attached Annexes are an integral part of this Request for Proposals – see section 13.

Oxfam may contact bidders to confirm contacts, addresses, bid amount and to confirm that the bid was submitted for this solicitation.

OXFAM has the right to undertake due diligence to verify the references, and very details submitted before award.

## Quotation validity

- The quotation shall be valid for 90 days from the submitted. If this is not possible, the bidder may propose a different timeframe.

- If the bidder is awarded the contract, all information provided in the quotation and negotiation process is contractually binding.

## Right to Select/ Reject

Oxfam reserves the right to select and negotiate with those firms it determines, in its sole discretion, to be qualified for competitive proposals and to terminate negotiations without incurring any liability. Oxfam also reserves the right to reject any or all proposals received without explanation.

## Reserved rights

All applications and quotes become the property of Oxfam, and Oxfam reserves the right in its sole discretion to:

- Disqualify any offer based on applicant’s failure to follow solicitation instructions.

- Waive any deviations by the applicant from the requirements of this terms of reference that, in Oxfam’s opinion, are considered immaterial defects requiring rejection or disqualification; or where such a waiver will promote increased competition.

- Extend the time for submission of responses after notification to all applicants.

- Terminate or modify the process at any time and re-issue the request for quotation to whomever Oxfam deems appropriate.

- Issue an award based on the initial evaluation of offers without discussion.

- Award only part of the activities in the solicitation or issue multiple awards based on solicitation activities.

# CODE OF CONDUCT

Oxfam is committed to integrity in its operations and supply chains and ensuring high ethical standards. Complying with all laws and regulations and ensuring fair competition are fundamental to this commitment. We actively promote these principles and standards and expect all Oxfam suppliers to demonstrate commitment towards them.

All consultants/applicant are required to agree and adhere to the Oxfam Supplier Code of Conduct, whereas individuals (including consultants) must sign the Oxfam Non Staff Code of Conduct. These Codes of Conduct set out the specific standards and principles in the areas of human and labour rights, environmental impact and anti-corruption that suppliers must follow.

Oxfam has the following requirements of its service providers, to ensure integrity in its supply chain:

## Bribery and collusion

Oxfam does not tolerate fraud, including bribery or kickbacks, collusion among bidders, bribery or kickbacks. Any firm or individual violating these standards will be disqualified from this procurement and barred from future procurement opportunities.

Employees and representatives of Oxfam are strictly prohibited from asking for or accepting any money, fee, commission, credit, gift, gratuity, object of value or compensation from current or potential vendors or suppliers in exchange or as a reward for business.

## False statements

Bidders must provide full, accurate and complete information as required by this solicitation and Annexes. False statements in bids constitutes grounds for immediate termination of any agreement with the supplier. OXFAM takes misstatements, falsification, manipulation, alteration of facts and/or documents very seriously, has a zero-tolerance policy to such behaviours, and may choose to take legal action in a case of misrepresented disclosures by

## Conflict of interest

Bidders must provide disclosure of any past, present or future relationships with any parties associated with the issuance, review or management of this solicitation and anticipated award.  Failure to provide full and open disclosure may result in Oxfam having to re-evaluate the selection of a potential bidder.

## Diversion of funds

Oxfam is determined that all its funds and resources should only be used to further its mission and shall not be subject to illicit use by any third party nor used or abused for any illicit purpose. Suppliers (and their affiliates/group companies, employees, officers, owners, agents and sub-contractors) may be subject to formal screening against global lists of individuals subject to designation or proscription under financial sanctions or counter terrorism regulations.

# Monitoring

Due diligence: As a charitable organisation, Oxfam must take care to protect its assets and funds, as well as the communities that we work with. One of the steps that Oxfam takes to comply with this legal duty is to conduct adequate and proportionate due diligence on suppliers prior to entering a contract. This includes checking legal registration and financial solvency, but may also include other checks, such as misconduct/performance reference checks and if working with children or vulnerable adults, a criminal records check.

Important note: Oxfam performs a regular screening check of all suppliers against international sanctions lists.

Audit: Any audit requirements are detailed in the terms and conditions of business

Data protection: Oxfam is legally bound to ensure that all personal details held by the organisation relating to any individual or entity are kept secure and according to international data protection standards.

# MISCONDUCT REPORTING AND WHISTLEBLOWING

Oxfam’s reporting and whistleblowing mechanisms are available for Service Providers as well Oxfam employees, to ensure that Oxfam continues to operate under the highest ethical standards and principles.

You can use these reporting channels confidentially, anonymously, and in your own language to report any concerns involving fraud, corruption, waste, abuse or safeguarding concerns.

| Speak up |  |  |  |
| --- | --- | --- | --- |
|  | Oxfam GB | Oxfam Novib | Oxfam Intermón |
| Email: | SpeakUp@oxfam.org.uk | integrity@oxfamnovib.nl | buzon.etico@oxfam.org |
| Online: | Oxfam Misconduct Reporting Webform (including possibility for anonymous reporting) https://oxfam.clue-webforms.co.uk/webform/misconduct/ |  |  |
| Phone: | Global phone number: +44 1249 661808 Check https://speakup.oxfamnovib.nl for local numbers (you can request interpretation) |  |  |

# ANNEXES

- Oxfam Supplier Code of Conduct: https://oxfam.box.com/v/Oxfam-Supplier-CodeConduct

- Oxfam Non-Staff Code of Conduct: https://oxfam.box.com/v/Nonstaff-CodeConduct

- Conflict of interest declaration form: https://oxfam.box.com/v/Supplier-COI-declaration

- Safeguarding policy

- (If applicable) Oxfam child safeguarding policy

(Edit if applicable) Example privacy notice: https://oxfam.box.com/s/mo8artt9l8a2x0cnpqrqqrugt8k0r773

Non-Staff Code of Conduct applies for any self-employed individuals or contracted employees of suppliers who are working on Oxfam sites, or who have access to Oxfam materials, or who may represent Oxfam in any manner but are not part of Oxfam’s legal entity)