INVITATION TO BID FOR CONSULTANCY

Save the Children International (SCI) Somaliland program hereby invites interested consultants to bid for the consultancy assignment detailed below

| 1 | Title of Consultancy | Terms of Reference for consultancy to (a) conduct a Joint Mid- Term Review of the Somaliland Global Partnership for Education (GPE) Partnership Compact and (b) Conducting Joint Review of the Education Sector in Somaliland (JRES) (two consultancy work) |  |  |
| --- | --- | --- | --- | --- |
| 2 | SCI Contracting Office | Save the Children in Somaliland |  |  |
| 3 | Period of Consultancy | The two assignments will be 40 days each (inclusive of travel) |  |  |
| 4 | Consultant type required | Experienced and relevant Consultancy Firm |  |  |
| 5 | Responsibility for Logistics arrangements and Costs | Save the children will pay the consultant fee in a lump sum and will not reimburse any incurred costs during the assignment. The consultant will cover their own Logistical arrangements, costs; including food, accommodation, insurance, local transport and all cost associated with data collection work and whole activities. |  |  |
| 6 | Taxation Provisions | The consultancy firm shall be responsible for all applicable taxes related to the consultancy services, in accordance with local tax regulations at the SCI contracting office will apply and shall be withheld by SCI |  |  |
| 7 | Travel requirements | The consultancy firm will cover all travel costs (tickets) and arrange local travel to field sites. |  |  |
| 8 | Security requirements | The consultancy firm will comply with the standard of Save the Children Security procedures, including the completion of SCI online security training (applicable to international consultants) prior to travel to Somaliland. |  |  |
| 9 | Firm's Experience Requirement: | In addition to the individual expertise of the proposed consultants mentioned below, the consultancy firm must demonstrate institutional experience in conducting high-level education sector review and evaluations. This includes, but is not limited to, Joint Reviews of the Education Sector (JRES), mid-term or end-term evaluations of education sector plans, and reviews of global or national education partnership programs such as the GPE Partnership Compact. The firm should provide documented evidence of successfully completed assignments of a similar nature, including contracts, completion certificates, or official letters of award. Experience working with government ministries, international development partners, and multi-stakeholder education coordination platforms will be considered a strong asset. |  |  |
|  | KEY PROFESSIONAL STAFF/INDIVIDUAL REQUIREMENT |  |  |  |
|  | Description | Minimum Qualifications and professional experience |  |  |
|  | Assignment one: Joint Review of the Education Sector (JRES) |  | - An advanced degree (master’s or PhD) in education or a related social science field. - A minimum of ten years of relevant experience, with a strong preference for experience in supporting the education sector, particularly in planning, review, and evaluation. - Practical, hands-on experience in designing, implementing, and monitoring Sector-Wide Approaches in Education. - A strong background in data analysis, national-level planning and policy development, teacher development and management, girls' education, disability and inclusion, and learning assessments and producing quality reports. - A demonstrable understanding of gender equality and inclusion in education, including practical experience in applying gender-responsive approaches in planning, implementation, and evaluation. - Previous experience working in fragile or transitional countries is considered an asset. - Specific knowledge of the education sector in Somaliland/Somalia. - Excellent command of the English language, with proven analytical, report writing, presentation, and facilitation skills. - The ability to work effectively in challenging environments, demonstrating resilience and adaptability. - Computer literacy and proficiency with Microsoft Office. - Commitment: Availability to complete the assignment within strict deadlines. |  |
|  | Assignment two: Mid-term Review of the GPE Partnership Compact |  | - An advanced degree (master’s or PhD) in education or a related social science field. - A minimum of ten years of relevant experience, with a strong preference for experience in supporting the education sector, particularly in planning, review, and evaluation. - Practical, hands-on experience in designing, implementing, and monitoring Sector-Wide Approaches in Education. - A strong background in data analysis, national-level planning and policy development, teacher development and management, girls' education, disability and inclusion, and learning assessments. - A demonstrable understanding of gender equality and inclusion in education, including practical experience in applying gender-responsive approaches in planning, implementation, and evaluation. - Previous experience working in fragile or transitional countries is considered an asset. - Specific knowledge of the education sector in Somaliland/Somalia. - Excellent command of the English language, with proven analytical, report writing, presentation, and facilitation skills. - The ability to work effectively in challenging environments, demonstrating resilience and adaptability. - Computer literacy and proficiency with Microsoft Office. - Commitment: Availability to complete the assignment within strict deadlines. |  |
| 10 | EVALUATION CRITERIA The proposals submitted by consulting firms will be evaluated based on the following criteria: |  |  |  |
|  | Essential Criteria |  |  | Pass/Fail |
| 1 | The Bidder and its staff agree and sign to comply with SCI policies embedded below at this Invitation to Bid (ITB). The Bidder is to download below listed items, read, understand and sign off appropriate section in below. a) Terms & Conditions of Bidding b) Supplier Sustainability Policy and the included mandatory policies |  |  | Pass/Fail |
| 3 | A valid Certificate of Registration from relevant government authority |  |  | Pass/Fail |
| 4 | A valid Tax Compliance from relevant government authority |  |  | Pass/Fail |
|  | Capability Criteria (Technical Evaluation): |  |  |  |
| 5 | Bidders are required to submit a detailed Technical and financial proposal each separately for the two assignments outlining all necessary expenses. The proposals must be comprehensive and inclusive of all applicable taxes and statutory requirements. 🔹 Lead Consultant – Joint Review of the Education Sector (JRES) - Advanced degree in education or relevant field (Master/PhD) 3 marks - Minimum 10 years of relevant experience in education sector 4 marks - Proven track record leading or co-leading in JRES or education sector reviews 10 marks - Demonstrated experience working in the Somali/Somaliland education context 5 marks - Strong analytical, facilitation, and report writing skills 3 marks (Total of 25marks) 🔹 Lead Consultant – Mid-Term Review of the GPE Partnership Compact - Advanced degree in education or relevant field (Master/PhD) 3 marks - Minimum 10 years of relevant experience in education sector reform or M&E 4 marks - Experience conducting Mid-Term Reviews (MTR) or GPE Compact evaluations or similar education sector review 10 marks - Understanding of GPE’s strategic objectives, reform frameworks, and gender/inclusion principles 5 marks - Excellent analytical and communication skills, especially in report writing and facilitation 3 marks (Total of 25 marks) |  |  | 25 marks |
|  |  |  |  | 25 marks |
| 6 | - Submission of at least one JRES final report authored or co-authored by the consultant within the last 10 years, ideally in Somalia/Somaliland contexts. 10 Marks - Submission of at least one GPE Compact Review report or similar education sector review completed by the consultant. 10 Marks |  |  | 20 Marks |
|  | Sustainability Criteria |  |  |  |
|  | All bidders are required to submit a brief Sustainability policy outlining their commitment to ethical, inclusive, and socially responsible practices throughout the execution of this assignment. |  |  | 10 Marks |
|  | Commercial Criteria (Financial Proposal Requirements): |  |  |  |
| 7 | Bidders must submit two separate and detailed financial proposals—one for each assignment: Each financial proposal must be itemized and clearly outline all anticipated costs related to the respective assignment. This should include consultancy fees, accommodation, local transportation, communication, stationery, data collectors, research assistants, and any other associated expenses. All costs must be comprehensive, transparent, and inclusive of applicable taxes and statutory obligations. Note: No additional costs beyond what is included in the submitted financial proposals will be accepted. |  |  | 20 Marks |
|  | Total |  |  | 100 marks |
| Note: For the technical analysis, a company must score 60% and above on the capability to be considered in the next evaluation process and the ultimate decision will be based on detail document and interview performance. |  |  |  |  |
| 🔹 Final Interview Evaluation Bidders who score 60% or above in the technical (capability), financial (commercial), and sustainability criteria will proceed to a final interview stage. Note: The final selection will be based on the combined score from the proposal and interview performance. |  |  |  |  |
| 9 | Application Procedure | - Interested consultant (s) who meet the consultancy requirements are requested to submit their bid and each application package should include the above required minimum requirements. Applications can be submitted by either: Electronic Submission via ProSave - Submit your response in accordance with the guidance provided in the below document: - Bidders are encouraged to apply via Ariba system. Please request the Ariba link via email sending your company profile and Business registration certificate/CV. Please address your Ariba link request to the email. Electronic Submission via Protected Email box - Email should be addressed to somaliland.procurement@savethechildren.org - Note – this is a sealed tender box which will not be opened until the tender has closed. Therefore, do not send tender related questions to this email address as they will not be answered. The subject of the email should be TOR of consultancy to conduct a Joint Mid- Term Review of the GPE Partnership & Compact and Joint Review of the Education Sector in Somaliland (JRES) All attached documents should be clearly labelled so it is clear to understand what each file relates to. - Emails should not exceed 15mb – if the file sizes are large, please split the submission into two emails. - Do not copy other SCI email addresses into the email when you submit it as this will invalidate your bid. Applicants should also indicate the date they are available to start working on the consultancy. All applications MUST be submitted on or before the closing date below to be considered for the assignment. Only shortlisted Candidates will be contacted. |  |  |
|  |  | Bid Application Details: Interested firms or individual consultants are invited to submit a single tender application package for both assignments. While the consultancy involves two distinct assignments (1) the Joint Review of the Education Sector (JRES) and (2) the Mid-Term Review of the GPE Partnership Compact, they will be managed under one contract, one submission, and one interview process. However, each assignment will have its own timeline, deliverables, and final report. Applicants are required to submit the following documents: - Technical Proposal: Two separate and assignment-specific technical proposals must be submitted—one for the Joint Review of the Education Sector (JRES) and one for the Mid-Term Review of the GPE Partnership Compact. Each proposal should provide a detailed response to the ToR, clearly demonstrating understanding of the respective assignment’s scope of work, objectives, methodology, approach, timelines, and expected deliverable. - Financial Proposal: Two separate and detailed financial proposals are required—one for each assignment. Each financial proposal must provide a complete and itemized breakdown of all expected costs, including consultancy fees and associated operational expenses (e.g., accommodation, transportation, communication, stationery, data collection, and research assistance). All costs must be stated in USD and inclusive of applicable taxes. No additional costs will be considered beyond what is submitted in the financial bid. - Firm Profile: For consultancy firms, a company profile outlining relevant past experience, particularly in education sector reviews and mid-term evaluations. - Curriculum Vitae (CVs): Each firm must propose two separate lead consultants, one for each assignment (One lead consultant for the JRES assignment & One lead consultant for the Mid-Term Review of the GPE Compact) - Each CV must be complete, specific to the assignment, and include at least three traceable references. A single individual cannot be proposed for both assignments. - CVs should clearly demonstrate the candidate’s experience and qualifications in relation to the assignment they are being proposed for. Note: Bidders who do not submit two distinct lead consultant CVs (one for each assignment) will be considered non-compliant and disqualified from further evaluation. |  |  |
| 10 | Closing date for Applications | Interested consultants shall submit their BID applications through the above procedures by somaliland.procurement@savethechildren.org on 1st September 2025 at 12:00Am |  |  |

| We, the Bidder, hereby confirm we compliance with the following policies and requirements: |  |  |
| --- | --- | --- |
| Policy | Policy / Document | Signature |
| Terms & Conditions of Bidding |  |  |
| Supplier Sustainability Policy and the included mandatory policies | Click Here to Access |  |

| Note to Bidders: Each bidder is required to sign and complete the above section as confirmation of their acceptance and adherence to Save the Children’s policies. Save the Children will rely on these signed declarations as part of its evaluation and due diligence process. |  |
| --- | --- |
| Signature: | ………………………………………………….. |
| Name: | ………………………………………………….. |
| Title: | ………………………………………………….. |
| Company: | ………………………………………………….. |
| Date: | ………………………………………………….. |

Note: Clarification on Staffing Requirements for the Assignment

Given the distinct nature and technical focus of the two assignments under this ToR—the Mid-Term Review (MTR) of the GPE Partnership Compact and the Joint Review of the Education Sector (JRES) in Somaliland; it is mandatory that any applying consultancy firm proposes two separate lead consultants, each dedicated solely to one of the assignments. One lead consultant will be responsible for conducting the MTR of the GPE Compact, while the other will lead the JRES process. Both consultants will be expected to collaborate closely and operate concurrently, as the two processes are interlinked but two different reports will be produced. However, no single consultant may be proposed to cover both roles.

To ensure suitability, the applying firm must submit a separate and complete CV for each proposed lead consultant, clearly demonstrating their qualifications and experience aligned to the specific assignment they are being proposed for (Compact MTR or JRES). Save the Children will review and assess the qualifications of each consultant independently and reserves the right to reject applications that do not meet this dual-staffing requirement. Firms submitting only one lead consultant for both tasks will be considered non-compliant and will not proceed to the technical evaluation stage.

Terms of Reference for a Joint Mid- Term Review of the GPE Partnership   Compact and Joint Review of the Education Sector in Somaliland (JRES)

1.0: Introduction

Somaliland MOES will conduct a comprehensive review of GPE Partnership Compact combined with a light review of the performance of the Education Sector Strategic Plan for year 2024/25 in the format of Annual Joint Review of the Education Sector (JRES). The reviews will be used as a sector-wide performance monitoring system to measure and continuously follow up the progress made against the Partnership Compact and the yearly planned ESSP activities and result indicators to improve coordination and collaboration among education stakeholders.

Both reviews will involve different departments of the MOES at all levels, development partners, civil society and the private sector. It’s the first term that Midterm review of a GPE Partnership Compact is done in Somaliland context. However, the JRES initiative started in 2014 and so far, six review meetings were conducted between 2014 to 2022 and the Ministry is currently planning to conduct the seventh 2024/25 JRES along with the review of the GPE Partnership Compact. Therefore, MOES seeks two consultants who will jointly and technically lead the review process of the Compact and JRES in collaboration and coordination with a dedicated and government led task team who will work with the existing MOES Technical working groups of access, quality, system capacity, gender and education in emergencies. Gender equality and inclusion will be assessed and integrated throughout the review process of all the technical working groups.

The review process is expected to have both a backward look of what has been achieved during the lapsed implementation period of the Compact as well as 2024/25 academic year (JRES component) and the best way forward for the next academic year (2025/26).  Mid-term reviews are key moments for government and partners to assess the implementation of the partnership compact priority reform and determine opportunities to adjust, refine and strengthen its overall progress

2.0: Background and overview of the ESSP 2022-26 priority reforms

Somaliland has been recovering from historic conflict and fragility since 1991 and has established its own government system and functional institutions. It has managed to maintain peace and security in the last three decades and significant improvement has been made in many social and economic sectors including education services. However, the education sector still requires further support to improve access to good quality, equitable and efficient education services for all children. The third and current ongoing ESSP 2022 – 2026 for the MOES has started in 2022. The plan sets out the policy priority objectives of the education system that will be achieved during this period. These policies and objectives have been developed based on the national and international commitments of the Government of Somaliland through the Ministry of Education and Science to provide quality, affordable and inclusive education to its citizens throughout the country.  The ongoing sector plan is guided by the National Education Policy of 2015-2030, Somaliland Vision 2030 and NDP III.

The ESSP 2022-26 is an ambitious document that consists of six sub-sectors of education which include Early Childhood Education; Primary Education; Non-Formal Basic Education (NFE); Secondary Education; Technical and Vocational Education and Training (TVET), and Higher Education. The plan also covers MOES system capacity in areas such as sector governance, management and accountability, human resources; policy and planning; financial management, education decentralization; curriculum; teacher education, quality assurance systems, examinations, a national commission for higher education and education in emergencies.

The key targets of the ESSP 2022-26 are:

- Increase the pre-primary GER from 5% to 15% (50% girls) by 2026.

- Increase pre-primary NER from 3% to 10% by 2026 (50% girls) by 2026.

- Increase primary GER from 32% to 50% by 2026.

- Increase primary schools NER from 24% to 44% by 2026.

- Increase secondary education GER from 18% to 35% by 2026.

- Increase secondary education NER from 8% to 18% by 2026.

There are target dimensions for all the above subsectors of education in areas of equity and inclusion, quality, and governance. The same applies to the MOES System capacity component of the ESSP. The review will consider 2024/25 progress across the ESSP indicators but will specifically focus on headline targets and indicators of each subsector including system capacity.

2.1: The GPE Partnership Compact: background and overview of the priority reforms

The Government of Somaliland recognizes education as a pivotal tool for social and economic transformation and as a critical pillar in realizing its development Vision 2030. The philosophical and ideological basis for education is articulated in the Somaliland Education Act (XEER LR.77/2018) and Somaliland National Education Policy (SLNEP 2015-30). While education continues to receive a significant share of the country’s budget, the sector faces multiple challenges and has consistently relied on internal and external partners to complement government effort.

This Partnership Compact articulates a shared commitment between the government of Somaliland working together with partners to transform the education system to ensure equitable access to quality pre-primary and primary education in Somaliland. The development of the Compact was led by the local education group (LEG) in Somaliland - the Education Sector Committee (ESC). A GPE Task Team appointed by the Minister of Education and Science (MoES) on 2 September 2022 provided continuous technical support to the ESC. The Task Team was drawn from the relevant technical departments of MoES, the civil society organisations (CSOs), the private sector) and international partners supporting education interventions in Somaliland.

Based on the evidence and outcomes drawn from the analysis of key education documents, reports and researches the ESC adopted a shared priority reform to ensure “Improved Access to Quality Pre-primary and Primary Education for all in Somaliland”. MoES and stakeholders also settled on three interrelated policy outcomes: 1) Improved access to equitable and inclusive foundational education, 2) Improved learning outcomes and 3) Education system strengthened. The Compact reflects a comprehensive effort to address the constraints to access to quality basic education at pre-primary and primary education levels. Under the Compact, Somaliland is expected to expand opportunities for school enrolment, improve the quality of learning experience and ensure better learning outcomes at ECE and primary education.

3.0: Purpose of the consultancy work

JRES: The consultant will conduct, coordinate and facilitate the sector review process in collaboration with the MoES and development agencies through gathering relevant qualitative and quantitative data on the achievement of 2024/2025 and review and set priorities and plan within the ESSP result framework.

Compact: Mid-term review is a key moment for government and partners to assess the implementation of the priority reforms including the enabling factors for system transformation and progress towards gender equality and inclusion. The intended progress is reflected through the implementation of GPE System Transformation Grant (STG); Girls Education Accelerator (GEA) and System Capacity Grant (SCG). The review process is also expected to determine agreed-upon next steps for improvement and further sets out the agreed focus areas for future GPE grants and top-up triggers. Furthermore, the process provides an important chance to make course corrections, strengthen alignment among stakeholders, and pinpoint persistent challenges or bottlenecks that may be hindering reform efforts.

4:0: Objectives of the consultancies work (both Compact and JRES)

- Review the progress in implementing the ESSP 2022-2026, including against key indicators of access, quality and system capacity with emphasis on progress towards gender equality and inclusion across all components.

- Assess progress on gender equality and inclusion as part of the implementation of the priority reforms and enabling factors, in line with GPE’s MTR guidance

- To review the level of coordination of various actors in the education sector.

- To compile review reports for both the Compact and JRES and present it in the Conference.

- To compile and present a mid-term review Memo of the Compact and separately an Aide Memoire of the JRES review process and key action points agreed for both undertakings.

- Gauge the efficiency in which resources have been used toward achieving objectives and priorities of both ESSP and Compact.

- To examine and document key challenges, lessons learnt and best practices during implementation of the ESSP and Compact to help determine priority reforms for the period between 2027-2030 and possible extension of the current Compact.

- Provide recommendations for any adjustments to be made to the ESSP 2022-2026, and the Partnership Compact, as well as adjustment to their implementation.

- Assess progress against existing top-up GPE triggers where relevant and agree on intermediate actions needed to accelerate progress

5:0: Methodology and scope of the work

Desk Review: The consultants will undertake a technical and financial review of 2024/25 annual plans against the 2022–2026 ESSP through conducting extensive review of the relevant policy and strategy documents, available secondary data such as annual reports, monitoring and supervision reports, review and evaluation reports, ESA report, EMIS data and learning assessment reports that are available with the MoES and development partners.

Consultative Meetings:  participate and coordinate with MoES at different levels and development agencies in gathering the relevant information and data. The consultant is expected to conduct wider consultation with relevant education stakeholders in Somaliland. This includes the senior management and leadership and staff of MOES at all levels (Central, Regional, District, School) and education development partners to get wider insight and perspectives of the education sector including achievements and challenges. These consultations will be designed to ensure inclusive participation.

Field Visits: The consultant will carry out sample field visits to education institutions in rural and urban settings, including to regional and district education offices in a randomly selected regions to get a clearer picture of the situation on the ground through discussion with all education stakeholders.  The field visits shall capture gender and inclusion specific barriers. Based on these field visits, the consultant will prepare a field-visit report and key findings that will be part of the JRES meeting presentations, final Aid Memoire and Compact Mid-term review Memo.

Synthesis Report: The consultants will compile and produce two synthesis reports from the key findings of the desk review, consultation meetings and field visits against the achievement of the 2024/25 plan within the ESSP and review of the Partnership Compact. The synthesis reports will include data analysis, graphs and charts, as well as a narrative. The two separate synthesis reports will be circulated a few days prior to the JRES and provide the basis for discussions during the JRES Meeting and presentations.

Review of Education Action Plan for 2025/6: if deemed necessary, the consultant will assist the stakeholders, to review the Education Action Plans for 2026 ensuring that the activities proposed in the plan incorporate priorities and key strategies including the costing as well as the monitoring and evaluation framework for the Action Plan.

2 days facilitation of JRES and Partnership MTR workshops

Two separate Memos: Aide Memoire of the JRES review process and key action points and Partnership Compact review Memo agreed

The consultants will provide two separate final reports, first on the Joint Review of the ESSP, on issues discussed and raised, key findings and recommendations including the field visit and synthesis report. And secondly on Midterm Compact review using GPE provided template.

6:0: JRES: Key Deliverables

- Compile a synthesis report from the key findings of the desk review, consultation meetings and field visits against the achievement of the 2024/25 action plan and present it in the JRES meeting.

- Final report of the Joint Review of the Education Sector, on issues discussed and raised, key findings and recommendations including the field visit and synthesis report.

- compiled Aide Memoire of the JRES review process and key action points agreed

- if deemed necessary, revised education action plans for 2025 and 2026

6.1: Midterm review of the GPE Partnership Compact

- produce a detailed progress report using standard GPE template

- produce forward plan or updated priority reform (for planning period 2027-30)

- Country Snapshot Report; and MTR Progress Memo using standard GPE template

7.0: Management arrangements

The two consultants will be line managed by the SCI, GP program Director.  Both MOES and SCI will provide access to the office as required.

8.0: Work plan and Time Schedule

The tentative consultancy timetable is given below which could be reviewed during the inception period:

| SCHEDULE FOR JRES |  |  |
| --- | --- | --- |
| № | Deliverables | No. of Days |
| 1 | Desk Review | 6 |
| 3 | Consultation Meetings & Field Visits | 8 |
| 4 | Synthesis Reports | 6 |
| 5 | Joint Sector Review and Compact Review Workshop | 2 |
| 6 | JRES Aide Memoire and Compact Memo | 2 |
| 7 | Annual Education Action Plan 2024 | 6 |
| 8 | Final JRES and Compact Reports | 10 |
| Total No. of Days |  | 40 |
| SCHEDULE FOR COMPACT MID-TERM REVIEW |  |  |
| № | Deliverables | No. of Days |
|  | Desk Review | 6 |
|  | Consultative workshop with ESC | 2 |
|  | Produce a detailed progress report using standard GPE template | 8 |
|  | Produce forward plan or updated priority reform (for planning period 2027-30) | 8 |
|  | Produce a mid-term Memo report using a standard GPE template | 8 |
|  | Revised copy of Somaliland Compact Document | 8 |
| Total No. of Days |  | 40 |

Please note that the two engaged consultants will work jointly and collaboratively but each constant will focus on one specific task. Consult one will focus on JRES while the second consultant will focus on Mid-term review of the Compact. The total available days for each consultant will be 40 days.

9.0: Location: The Consultant will be based in Hargeisa, Somaliland for most of the Contract period but might be required to visit, sample regions, districts and schools.

10: Qualification and experience requirement

- Advanced degree (Master or PhD) in education or related social sciences.

- At least ten years of relevant experience, mostly in supporting the education sector and experience in the education sector planning, review and evaluation are highly preferred assets.

- Have hands-on experience with designing, implementing and monitoring Sector-Wide Approaches in Education.

- Strong background in data analysis, planning and policy development at the national level; teacher development and management; girls’ education; disability and inclusion; learning assessments.

- An understanding of gender equality and inclusion in education, with practical experience in applying gender-responsive approaches across planning, implementation, and evaluation processes.

- Excellent command of the English language with demonstrated analytical and report writing skills, presentation and facilitation skills.

- Ability to work in difficult environments; previous experience of working in fragile contexts or transition countries is an asset (resilience and adaptability to challenging country context).

- Specific knowledge of the education sector in Somalia/Somaliland.

- Availability and commitment to complete the assignment within strict deadlines.

- Computer literacy and familiarity with Microsoft Office.

The MOES will nominate a task lead team that will work with the existing technical thematic groups and the international consultants. It is expected that the external consultants and MOES technical leads will closely work with ESC Technical Working Groups (TWGs) to implement all the expected deliverables.

Start date: As soon as possible (ASP). The MOES and ESC have agreed that the final national conference will be held on the second week of November 2025.

Interested consultants shall submit their BID applications through the above procedures by somaliland.procurement@savethechildren.org on 1st September 2025 at 12:00Am