Terms Of Reference

Revision and Updating of Child Protection Case Management Documents including Standard Operating Procedures (SOPs) and Data Protection and Information Sharing Protocols (DPISP)

Supported by Gashan partners, UNICEF and SOS Children’s Village Project in collaboration with CP AoR secretariats and the Case Management Task Force (CMTF)

Duration: 10 weeks (23rd February 2025- 30th April 2025)

1.Background:

Child Protection case management is a critical component in ensuring the safety, well-being, and protection of vulnerable children across Somalia. The Child Protection Area of Responsibility (CP AoR) and the Case Management Task Force (CMTF) play a pivotal role in enhancing the quality of child protection services.

The current Standard Operating Procedures for Child Protection Case Management and the Data Protection and Information Sharing Protocols have been in used since 2021 to date. The SOP and DISP are essential tools that guide practitioners in the delivery of services and management of child protection cases. The current versions of these documents require adjustment to align with global best practices, national legislation, and the evolving operational and contextualization in Somalia. Furthermore, to enhance adoptability and implementation, these documents will be translated into Somali versions.

The CP AoR CMTF, with financial support from the (GAASHAN Consortium, UNICEF and SOS CV) will lead a comprehensive revision and update of these key documents to ensure they remain relevant and effective in strengthening child protection case management. The GAASHAN Programme, funded by the Foreign, Commonwealth & Development Office (FCDO), aims to provide sustainable humanitarian aid and prevent child protection risks in South Central Somalia.

This initiative is jointly supported by GAASHAN consortium partners, including Save the Children (Lead organization), International Rescue Committee (IRC), CARE International, Save Somali Women and Children (SSWC), Somali Women and Development Centre (SWDC), Somali Women’s Studies Centre (SWSC), and GREDO, in collaboration with SOS Children's Villages (SOS CV) and UNICEF.

In this initiative, SOS Children's Villages (SOS CV) is the lead organization at the national level for coordinating and overseeing the implementation of this activity across Somalia with support from CP AoR Secretariats.

Together, GAASHAN partners, CP AoR, UNICEF, and SOS CV are committed to enhancing child protection case management service delivery in Somalia. Their collective efforts aim to standardize, strengthen, and ensure a coordinated response to child protection concerns, aligning with Somalia’s humanitarian and development goals.

2. Objective

The main objective of this is to review, update, and align the CP case management documents with the current global standards and the evolving protection needs in Somalia. This process will ensure that both SOPs and DPISP reflect:

- Best practices in child protection case management.

- Compliance with data protection standards.

- Efficient coordination and information sharing among child protection actors.

- Contextualization the documents in to translation into Somali.

3.Scope of Work:

- Document Review: Review the existing Child Protection Case Management SOPs and DPISP to identify gaps, inconsistencies, and outdated practices.

- Conduct Data Protection Initial Assessment: Conduct an initial assessment to evaluate the data protection standards currently in place

- Stakeholder Consultations: Conduct consultations with key child protection stakeholders, including government agencies, CP AoR, CMTF members, and other relevant actors, to gather input on the revision process.

- Updating Documents: Revise the SOPs and DPISP based on consultations, ensuring they meet current child protection standards, particularly in data protection, confidentiality, and case management best practices.

- Translation into Somali language: Translate the updated documents into Somali to ensure widespread accessibility and usability.

- Validation Workshop: Organize validation workshops with CP AoR and CMTF members to review and finalize the updated documents.

- Printing and Distribution: Prepare the final versions (in English and Somali) for printing and dissemination to all stakeholders involved in child protection case management in Somalia.

4.Methodology:
The CP AoRs proposed to hire the consultant to support the following activities.

- Desk review of current Standard Operating Procedures and Data Protection and Information Sharing Protocols (SOPs and DPSP).

- Stakeholder engagement through workshops and meetings.

- Collaborative drafting and revision process with input from key stakeholders, including CP AoR and CMTF members.

- Inception report with a detailed work plan and methodology.

- Validation of the final documents through stakeholder feedback and report.

5.Deliverables

The following key deliverables are expected from the consultancy:

- Revised Child Protection Case Management SOPs.

- Updated Data Protection and Information Sharing Protocols (DPISP).

- Translated documents (English and Somali versions).

- Printed copies of both English and Somali versions for dissemination.

- Timeline:
The expected timeline for the project is as follows

| Week | Activity |
| --- | --- |
| Week 1-2 | Conducting data protection initial Assessment (DPIA) |
| Week 3-4 | Review of existing documents and initial stakeholder consultations (CP AoR Secretariat, CMTF members). |
| Week 5 | Revision and updating of the SOPs and DPISP based on stakeholder feedback. |
| Week 6 | Translation of documents into Somali. |
| Week 7 | Organizing and conducting a validation workshop with CP AoR and CMTF members. |
| Week 8 | Finalization of documents based on feedback from the validation workshop. |
| Week 9-10 | Printing and distribution of both English and Somali versions. |

7. Roles and Responsibilities:

- CP AoR secretariat and CMTF taskforce oversee the project, coordinate stakeholder consultations, and provide technical support.

- SOS children’s Village is the lead organization for this activity at national level.

- Consultants: Conduct reviews, facilitate consultations, and draft revised documents.

- Stakeholders: Provide input and feedback throughout the revision process.

8. Approval and Review Process:

- The revised Standard Operating Procedures and Data Protection and Information Sharing Protocols will be circulated among stakeholders, including CP AoR secretariats and CMTF members, for review and approval before finalization. The process will ensure that all relevant parties will be given opportunity to contribute to the final documents.

- The consultant/firm will also directly report to the National CP AoR Secretariats. Regular updates and coordination meetings will be held with the assessment taskforce and key stakeholders.

9. Consultant Selection

A consultant or consultancy firm with expertise in child protection case management and CPIMS+ will be engaged. The selection process will follow standard procurement procedures, ensuring transparency and competitiveness.

10. Child Safeguarding and Ethical Considerations

Throughout the process, strict adherence to child safeguarding principles and protocols will be maintained to ensure the protection, dignity, and well-being of all children and vulnerable individuals involved. This includes:

- Prioritizing Child Safety and Well-being: All activities will be designed and implemented with a child-centered approach, ensuring the protection and best interests of children at all times.

- Ethical Data Collection and Engagement: Interviews, surveys, and discussions will be conducted in a sensitive, respectful, and ethical manner, following established guidelines for working with children and vulnerable groups.

- Capacity Strengthening on Safeguarding: All team members, including assessment and technical staff, will receive training on child safeguarding policies, procedures, and reporting mechanisms to ensure compliance and accountability.

- Prevention and Response to Safeguarding Concerns: Proactive measures will be in place to identify, mitigate, and respond to any safeguarding risks that may arise during the process, with clear referral pathways for reporting and addressing concerns.

- Confidentiality and Data Protection: Stringent data protection measures will be implemented to safeguard children's personal information, ensuring informed consent and adherence to national and international child protection data-sharing protocols.

11. Submission of Proposals

Interested consultants/firms are invited to submit their proposals, including:

- Technical proposal detailing methodology and work plan.

- Financial proposal with a detailed budget.

- Company profile or CV including a minimum of 3 references

12. How to Apply

To submit applications for this consultancy, please send the documentation to SOS Children’s Village International Somalia at: procurement@sossomalia.org

Please send your completed applications not later than 10th March 2025