Terms of Reference (ToR) for End-line evaluation

Project: Cultivating the Future: Strengthening Food Security and Resilience of Vulnerable Communities in Maroodijeh

Project Period: 1 March 2025 – 31 August 2026

- INTRODUCTION:

This Terms of Reference outlines the scope, objectives, methodology, deliverables, responsibilities, and timeline for the end-line evaluation of the project “Cultivating the Future: Strengthening Food Security and Resilience of Vulnerable Communities in Maroodijeh.”

The end-line evaluation will assess the extent to which the project achieved its expected results, outcomes, and approved indicators. It will also document key achievements, lessons learned, implementation challenges, sustainability prospects, and recommendations for future programming.

The evaluation will cover the six target communities of Abaarso, Beeyo Liban, Biyo Macaan, Xidhinta, Gogoysa, and Ilma Dado in Gabiley and Hargeisa Districts.

- PROJECT BACKGROUND:

The project “Cultivating the Future: Strengthening Food Security and Resilience of Vulnerable Communities in Maroodijeh” started on 1 March 2025 and is being implemented over an 18-month period, ending on 31 August 2026. The project is funded by the Italian Presidency of the Council of Ministers – 8x1000, with ActionAid International Italia E.T.S. as the lead partner and ActionAid International Somaliland as the implementing partner in Somaliland.

The project is being implemented in six pastoral and agro-pastoral communities in Hargeisa and Gabiley Districts: Abaarso, Beeyo Liban, Biyo Macaan, Xidhinta, Gogoysa, and Ilma Dado. Since the start of implementation in March 2025, the project has focused on improving access to food and water for drought-affected households, strengthening community resilience, and promoting inclusive and women-led approaches in the target communities.

The project was originally designed in response to the severe drought, food insecurity, water scarcity, and market-related shocks affecting Somaliland and wider Somalia during the proposal development period. Although the project was approved and started implementation in March 2025, the underlying context remained highly relevant at the time of implementation. Drought conditions, reduced household income, livestock losses, limited agricultural production, high food and fuel prices, and wider geopolitical shocks continued to affect vulnerable pastoral and agro-pastoral communities. These pressures increased household vulnerability and reinforced the need for timely support to improve access to food, water, livelihoods, and resilience.

Women, girls, children, elderly persons, internally displaced persons, and persons with disabilities remained among the most affected groups. Women and girls, in particular, continued to face increased unpaid care responsibilities, longer distances to access water and basic services, and heightened protection risks. Therefore, the project’s design and implementation approach remained relevant both to the crisis context identified during proposal development and to the continuing humanitarian and livelihood challenges present when implementation began in March 2025.

As the project approaches its final implementation period, this end-line evaluation will assess the extent to which the project has achieved its intended objectives, results, and approved indicators since implementation began in March 2025. The evaluation will also document key achievements, challenges, lessons learned, sustainability prospects, and recommendations for future food security, resilience, agroecology, cash, and WASH-related programming.

- PROJECT OBJECTIVE

Overall Objective: To contribute to the strengthening of food security and climate change resilience of vulnerable agro-pastoral and pastoral communities in Maroodijeh.

Specific Objective / Outcome: Increase access to food and water for drought-affected households through an inclusive, women-led approach in the Maroodijeh region of Somaliland.

Expected Results:

Result 1: Drought-affected households have increased access to food and water through unconditional cash and cash for work

Result 2: Target communities (especially women) have increased capacity and knowledge on agroecological practices to cope with recurrent drought and food insecurity.

Result 3: Target communities have increased access to water and community management of water infrastructure has improved.

- PROJECT ACTIVITIES COVERED BY THE EVALUATION

Result 1 Activities

- Cash-for-Work: construction of embankments targeting 200 households.

- Cash-for-Work: cleaning of dams targeting 90 households.

- Unconditional cash transfers to vulnerable families targeting 200 households.

- Post-distribution monitoring related to cash assistance and Cash-for-Work.

Result 2 Activities

- Training for farmers, herders, and women’s groups on food reserve establishment and money saving targeting 50 participants.

- Training for small farmers on integrated use of organic pesticides and supply of organic pesticide materials targeting 50 participants.

- Training for small farmers on crop diversification, drought-resistant alternative crops, and seed distribution targeting 50 participants.

Result 3 Activities

- Rehabilitation of berkads in pastoral communities for human and animal use targeting three water infrastructures and approximately 150 households.

- Excavation of ponds and distribution of low-density polyethylene sheets for rainwater harvesting targeting 200 households.

- Training of water management committees and transfer of basic water management skills targeting three water management committees with 7 members each.

- OBJECTIVES OF THE ENDLINE ASSESSMENT

The primary objective of the end-line assessment is to evaluate and provide reliable, final data on the project's performance against established benchmarks. The assessment will identify the best practices and key lessons in both technical implementation and program management. These insights will facilitate ongoing learning and improvements in resilience-building and climate-smart adaptation for women farmers and the general agricultural community. The findings will be shared with the ActionAid Federation, Cultivating the Future project, implementing ActionAid countries, and donors, serving as a resource for future fundraising efforts.

- EVALUATION QUESTIONS

- To what extent did the project achieve each approved outcome and result indicator?

- To what extent did Cash-for-Work and unconditional cash transfers improve household access to food, water, and essential needs?

- To what extent did the project improve knowledge and adoption of agroecological practices, including organic pesticides, crop diversification, drought-resistant crops, food reserves, and saving practices?

- To what extent did the project improve access to water through berkad rehabilitation and household rainwater harvesting support?

- How effectively did the project promote women’s participation, leadership, and inclusion in trainings, committees, and community decision-making?

- How did the project benefit women, girls, youth, persons with disabilities, internally displaced persons, and other vulnerable groups?

- Were protection, safeguarding, dignity, informed consent, and do-no-harm principles adequately considered during implementation?

- What key lessons, good practices, challenges, and recommendations emerged from implementation?

- Was the project cost-effective, considering value for money principles of equity, effectiveness, economy, and efficiency?

- How can lessons learned from this intervention inform future programme design, implementation, coordination, and adaptive management?

- EVALUATION CRITERIA

The evaluation will align with OECD's recommended criteria, covering relevance, effectiveness, efficiency, sustainability, and impact. This assessment aims to enhance accountability to donors, stakeholders, and beneficiaries while informing future programming.

Relevance

- Did the project align with Somaliland’s agricultural and climate change policies?

- How effectively did the project address the needs and priorities of target communities, especially marginalized groups?

Effectiveness

- To what extent has the project improved farmers’ knowledge, experience, and access to agricultural tools? Were the results satisfactory?

- What key drivers and challenges affected project delivery?

- How effectively has the project applied lessons learned to enhance implementation?

Efficiency

- Were resources used efficiently, and could the same results have been achieved at a lower cost?

- Were project activities completed within the planned timeframe and budget?

- What technical, managerial, and policy constraints affected implementation?

Sustainability

- Has the project established sustainable, community-supported structures for climate adaptation?

- Can the community sustain project benefits without external support? If not, what are the key challenges?

Impact

- How has the project improved the quality of life in affected communities?

- Were there unintended positive or negative impacts on the household or community level?

- Has the project influenced climate change policy at the national level?

Equity

- Did the project promote equitable participation and benefits across different demographic groups?

- What efforts were made over the past two years to advance equity, and what were the challenges?

- APPROACH AND METHODOLOGY

This endline study adopts a non-experimental design to conduct a pre-post comparison of results using mixed methods.

Data collection will involve:

- A quantitative household survey

- Document review

- Key informant interviews

- Focus group discussions

- Stakeholder consultations

- Direct observation of selected project outputs, including rehabilitated berkads, rainwater harvesting ponds, embankments, and dam cleaning sites.

The consultant will propose a detailed methodology, including sampling strategy, data analysis approach, ethical considerations, and quality assurance measures.

- SCOPE OF THE EVALUATION

The assessment will cover Abaarso, Biyo Macaan, Beeyo Liban, Xidhinta, Gogoysa, and Ilma Dado in Gabiley and Hargeisa Districts.

Evaluation participants will include direct beneficiary households, women beneficiaries, Cash-for-Work participants, unconditional cash transfer beneficiaries, agroecology training participants, water infrastructure users, water management committees, Village Development Committees, project committees, community leaders, relevant government authorities, ActionAid International Somaliland staff, and ActionAid International Italia representatives where applicable.

- RESPONSIBILITIES OF ACTIONAID

- Mobilizing communities, government authorities, and other stakeholders

- Providing funding for consultancy fees, logistics, and materials

- Introducing the consultant to relevant stakeholders

- Reviewing and approving data collection tools

- Facilitating field access and supporting quality assurance, while maintaining the consultant’s independence in data collection, analysis, findings, conclusions, and recommendations.

- Reviewing and approving the final report

- RESPONSIBILITIES OF THE CONSULTANT

- Managing logistics and recruiting enumerators

- Developing and obtaining approval for the methodology and data collection tools

- Creating a detailed work plan

- Conducting document reviews and leading field data collection

- Training enumerators

- Conducting interviews and focus group discussions

- Presenting preliminary findings to ActionAid

- Submitting the final evaluation report

- KEY DELIVERABLES

- Inception Report detailing methodology, sample size, ethical considerations, and work plan

- Draft Evaluation Report addressing key evaluation questions, followed by a review process with ActionAid

- Final Evaluation Report using the following suggested format:

  - Executive Summary (one page written succinctly to summarize the methodology, key findings, and lessons learned)

  - Recommendations list of key recommendations and learning from the evaluation, with brief explanations

  - Introduction:

  - Project Introduction, purpose and objectives

  - Methodology, Scope, and Sampling

  - Limitations

  - Key Findings analyzed on evaluation criteria and in reference to the evaluation question, while also providing gender and geographically disaggregated data.

  - Conclusions

  - Recommendations for future programming.

  - List of interviewees including name, organization and role (if applicable)

- Submission of Dataset(s) including raw and cleaned data, codebooks, and transcriptions

- DURATION OF THE ASSIGNMENT

The assignment will last 18 working days, covering travel, fieldwork, and reporting. The evaluation is expected to take place from 13th July to 30th July 2026.

  - Endline evaluation timeline:

| Phase | Activity | Duration |
| --- | --- | --- |
| Phase 1 | Desk Review of Project Documents | 2 Days |
| Phase 2 | Inception Phase and Development of Evaluation Tools | 2 Days |
| Phase 3 | Field Data Collection | 4 Days |
| Phase 4 | Data Analysis and Interpretation | 5 Days |
| Phase 5 | Report Writing and Finalization | 5 Days |
| Total |  | 18 Days |

- KEY GUIDELINES FOR CONTENT GATHERING

- Ensure informed consent is obtained by all those photographed, interviewed or videoed using this form. This goes for those fully recognizable in the background of shots, unaware they are being captured. All consent must be provided when delivering content. Consent can be gathered in a voice note or on a video. Please talk the individual through the form and explain where their image or story may be seen and what information might be used. Please record them saying their name, location and to repeat the first line of the consent form to have a record of their consent: 
  
‘My name is XXX. My location is XXX. I agree that the words spoken by me and photographs and/or video footage taken of myself, and my family may be used by ActionAid to communicate about their work, raise money for their work, or be used in international media to publicize their work for a period of five years.’

- Please deliver the consent along with the content. We will not be able to use content without a record of informed consent.

- Anonymity: individuals may not wish to be identified, for legal, safety or other reasons. If that is the case, we can protect their identities by changing names, locations and identifying details, photographing them in a way that conceals identity or doing audio-only interviews.

- ActionAid’s Visual Content Guidelines, including our Child Protection Policy (in English here and Arabic here) must be read and understood BEFORE a trip commences.

- DOCUMENTS TO SUBMIT:

- Technical Proposal

  - Cover letter briefly introducing the consultant/company/team and expressing interest in the assignment.

  - Consultant/company profile, including experience, expertise, and previous assignments related to end-line evaluations, food security, resilience, cash transfer programming, WASH, agriculture, livelihoods, gender, inclusion, and community-based programming.

  - Work plan and timeline for desk review, data collection, analysis, and reporting.

  - Methodology and approach for the evaluation.

  - Team composition, including key personnel and their roles.

- Financial Proposal

  - Detailed budget, cost estimates, and financial justification for the end-line evaluation.

- Supporting Documents

  - References or testimonials from previous clients or partners.

  - Samples of previous end-line evaluation reports or similar assignments.

  - Relevant registration and tax compliance documents, where applicable.

- Advertising period:

  - 22nd June 2026 – 29th June 2026.