TOR for Independent Evaluation services for ‘Home-Grown School Feeding Program in Somaliland’ (HGSFP) Endline Study

- Summary

CARE Somalia is seeking to procure the services of an evaluation company / consultants (consultants) to conduct the endline study of Home-Grown School Feeding Project in Somaliland (HGSFP) funded by Finland Ministry of Foreign Affairs (MOFA). HGSF has high demands in terms of the quantity and quality of data to be collected, in order to generate robust evidence to be used by multiple stakeholders.

The evaluation company / consultants will be responsible for the overall design of the endline study including the development of the methodology and tools as required, manage data collection services, carry out qualitative and quantitative data analysis, and prepare a comprehensive endline report for HGSFP. The external consultants will provide an independent and rigorous evaluation to enable the project to assess progress against outcomes at baseline, and to what extent the intervention was effective in contributing to gender transformative processes that contributed strengthened linkages between local agricultural production and school feeding systems to enhance nutrition, education outcomes, and community resilience in Somaliland.

CARE is a humanitarian non-governmental organization committed to working with poor women, men, boys, girls, communities, and institutions to have a significant impact on the underlying causes of poverty. CARE seeks to contribute to economic and social transformation, unleashing the power of the most vulnerable women and girls.  CARE has been providing emergency relief and lifesaving assistance to the Somali people since 1981. CARE is implementing three mutually supportive programs and are designed along the humanitarian-development nexus: Education and Gender Equality: Builds the capacity of government institutions to provide gender responsive education services while building adolescents and young people’s life skills. It strengthens the capacity of feminist organizations and Savings Groups Networks and supports their collective advocacy. Climate Justice, Food, Water, and Nutrition: Contributes to increased food security and an improved nutritional status of vulnerable populations through promoting gender-responsive, climate-smart and sustainable crop and livestock production, diversifying livelihoods, linking pastoralists and smallholder farmers with financial services and markets, promoting WASH and nutrition, and strengthening early warning systems and family and community contingency planning. Humanitarian Assistance: Provide a wide range of humanitarian services covering food security and economic recovery as well as education, health, nutrition, WASH, and protection in emergencies, ensuring investments into recovery. We will continue to contribute to humanitarian coordination and promote gender-responsive emergency assistance with the help of Rapid Gender Assessments and the promotion of women’s leadership in response.

- Project Overview

The Home-Grown School Feeding (HGSF) Project, implemented by CARE International in collaboration with the Ministry of Education and Science (MoES) and the Ministry of Agriculture (MoA) with funding from the Ministry of Foreign Affairs of Japan (MOFA), was designed to strengthen the nexus between agriculture, nutrition, and education in Somaliland. The project aims to ensure that school children, particularly in drought-prone and food-insecure regions, have access to regular, nutritious meals sourced locally from smallholder farmers. By linking school feeding programs with local food systems, HGSF contributes not only to improved student health, attendance, and learning outcomes but also to enhanced livelihood opportunities and market access for local producers. The project aligns with the Somaliland Education Sector Strategic Plan (ESSP 2022–2026) and the government’s Home-Grown School Feeding Policy, emphasizing community ownership, sustainability, and inclusion.

The HGSF project operates on the premise that improving nutrition and education outcomes requires an integrated, systems-based approach. At its core, the project recognizes that hunger and poor nutrition are among the leading causes of school absenteeism, low concentration, and early dropouts particularly among children from low-income households. Through targeted interventions such as the provision of school meals, capacity building for school management committees (CECs), and the creation of structured market linkages between schools and local farmers, the project stimulates demand for locally produced food. This, in turn, incentivizes smallholder farmers especially women to increase productivity, diversify crops, and adopt climate-smart agricultural practices, creating a sustainable supply chain that strengthens both the education and food systems.

The Theory of Change (ToC) guiding the project posits that if schools are able to consistently provide nutritious, locally sourced meals, then children’s attendance, concentration, and learning outcomes will improve; concurrently, if local farmers and traders are integrated into the supply chain through training, aggregation, and contract farming, their income, resilience, and participation in local markets will increase. These dual outcomes reinforce each other, as improved farmer livelihoods sustain the school feeding system while enhanced education outcomes contribute to long-term human capital development. Furthermore, by embedding accountability, gender inclusion, and policy advocacy mechanisms, the HGSF model contributes to a nationally owned, economically viable, and socially inclusive school feeding system, thereby strengthening community resilience and government capacity to sustain the program beyond donor support.

- Purpose and Objectives of the Endline Study

The primary objective of the HGSF Endline Evaluation is to assess the extent to which the project has achieved its planned outcomes compared to the baseline benchmarks and project logical framework. The endline will measure performance against outcome and output indicators while analyzing the factors that have influenced results. The evaluation will draw lessons on sustainability, policy relevance, and scalability of the home-grown school feeding model within the Somali context.

Specifically, the endline study is:

- To validate and compare progress against baseline values and assess whether the observed changes in nutrition, attendance, and farmer income are attributable to the project interventions

- To identify enabling and constraining factors influencing expected outcomes, testing the assumptions in the project’s Theory of Change (ToC) across the education–nutrition–livelihood nexus

- To demonstrate accountability to the Government of Finland, the Government of Somaliland, and other stakeholders by providing credible evidence of results and value for money

- To inform learning and policy, generating actionable insights for MoE, MoA, and local authorities to strengthen national systems for sustainable, locally sourced school feeding

- To share evidence and lessons with donors, research institutions, and regional school feeding networks to inform the broader discourse on sustainable and climate-smart school feeding in fragile contexts

- Endline Evaluation Questions

The endline evaluation will explore the following domains and guiding questions:

- Project design and implementation

- Was the HGSF project designed and implemented in a way that effectively linked school feeding, local agriculture, and nutrition outcomes?

- How well were partnerships between MoE, MoA, and local actors coordinated, and what lessons can be drawn for future multi-sectoral collaboration?

- Were monitoring, accountability, and feedback mechanisms effective in ensuring transparency and adaptive management?

- Effectiveness and impact: education and nutrition outcomes

- What measurable improvements have been achieved in school attendance, retention, and dietary diversity since the baseline?

- To what extent have school meals improved concentration, classroom participation, and academic performance among boys and girls?

- Were there differences in the impact of school meals across gender, location, or socio-economic groups?

- What worked (and did not work) in enhancing student nutrition and learning outcomes through locally sourced school meals?

- Effectiveness and impact: livelihoods and local economy

- How has the project influenced farmer productivity, income, and participation in school feeding markets?

- What role did community procurement and aggregation models play in strengthening local food systems?

- To what extent did women farmers and traders benefit economically and socially from their involvement in the HGSF supply chain?

- Were there spillover benefits (e.g., job creation, local trade expansion) beyond the direct target group?

- Gender equality, inclusion, and social norms

- How effectively were women, youth, and marginalized groups integrated into HGSF governance and economic activities?

- What shifts in gender roles or decision-making power have occurred among participating households and communities?

- How has the project addressed social and cultural barriers affecting women’s and girls’ participation in both education and livelihood activities?

- Sustainability and systems strengthening

- To what extent are local institutions (MoE, MoA, schools, CECs) capable of sustaining the HGSF model beyond project funding?

- What progress has been made toward embedding HGSF into national education and agricultural policies and budgets?

- Did the project leverage additional resources or partnerships that enhance sustainability and ownership?

- Accountability and governance

- How effective were the project’s feedback, grievance, and information-sharing mechanisms in promoting transparency and responsiveness?

- To what extent did communities, CECs, and school committees participate in decision-making and oversight of feeding activities?

- Were accountability systems inclusive, accessible, and gender-sensitive?

- Learning

- What unintended (positive or negative) effects did the project have on local food systems, school management, or community dynamics?

- How can lessons from the HGSF model inform the design of future climate-smart, locally owned school feeding programs in Somalia and similar fragile settings?

- Evaluation Approach and Methodology

The endline evaluation will adopt a mixed-methods approach integrating both quantitative and qualitative methods to ensure comprehensive analysis of the project’s performance, effectiveness, and sustainability. This approach will enable triangulation of findings and provide both the measurable evidence of change and the contextual understanding of the processes that led to it. The evaluation will be guided by OECD-DAC evaluation criteria relevance, effectiveness, efficiency, coherence, impact, sustainability, and gender equality and will align with CARE’s GESI and accountability framework.

The evaluation will utilize a comparative, cross-sectional design, drawing on data from the baseline study (2023) and the endline survey. This design allows the evaluation to measure change in key outcome indicators across education, nutrition, and livelihoods components, while also testing the assumptions embedded in the project’s Theory of Change.

Quantitative component

The quantitative component will focus on measuring change in key performance indicators related to school feeding coverage, attendance and retention, dietary diversity, community awareness, and farmer engagement in school feeding markets. Data will be collected using structured tools from representative samples of:

- Students (for attendance, dietary diversity, and perceived benefits);

- School headteachers and CEC members (for school management and adherence to standards);

- Farmers and traders (for production, sales, and income outcomes).
Descriptive and inferential statistics will be used to determine changes from the baseline, including difference-in-means tests, cross-tabulations, and where feasible, regression analysis to identify significant predictors of outcomes. Disaggregation by gender, region, school, community and vulnerability group will be conducted to assess inclusivity and equity.

Qualitative component

The qualitative component will be designed to explore the “how” and “why” behind the quantitative results, providing insight into perceptions, institutional dynamics, and sustainability prospects. Data will be collected through Focus Group Discussions (FGDs) and Key Informant Interviews (KIIs) with teachers, CECs, parents, farmers, and government stakeholders at regional and national levels. Thematic analysis will be used to interpret qualitative data, focusing on community participation, gender inclusion, local procurement processes, and accountability mechanisms. The qualitative findings will also test the project’s Theory of Change and assess whether the intended pathways of change have materialized in practice.

Sampling and data quality

Sampling should cover across the three project regions (Marodijeex, Togdheer, and Sanaag) to ensure representativeness and comparability with the baseline. The endline will maintain consistency in sampling parameters to allow statistical comparison over time. Data quality will be ensured through enumerator training, pilot testing of tools, real-time data validation using digital data collection platforms, and daily field supervision. Triangulation between data sources and verification of anomalies will ensure robustness and reliability of results.

Ethical Approaches

The approach to the endline must consider the safety of participants and especially children at all stages of the evaluation. All consultants staff and data collectors who will participate in the study will receive training on CARE’s policies on Child Protection and on Prevention of Sexual Harassment and Abuse (PSHEA); all consultants staff and data collectors will be required to sign their compliance with both policies before deployment. The bidder will need to demonstrate how they have considered the protection of children through the different data collection stages, including recruitment and training of research staff, data collection and data analysis and report writing.

- Scope of work

- Review the project’s MEL framework, project proposal, project baseline report and project annual reports.

- Submit an inception report (draft and final), that outlines the research methodology, including data collection tools, detailed analysis framework, ethical approach, quality control plan, limitations, enumerator training plan, and detailed work plan outlining all tasks to be completed by each of the members of the endline team.

- Finalization of tools, including back-translation supervision.

- Enumerator training toolkits, and training on data collection tools and their application to enumerators.

- Implement and supervise enumerators’ work in the field during data collection (qualitative and quantitative) ensuring quality of data, including overnight checks of electronic datasets.

- Validate all datasets and collate data as necessary for analysis.

- Analyse the collected data in accordance with the agreed analysis framework.

- Prepare a comprehensive draft and final endline report, according to the format discussed with CARE.

- Deliverables

In reference to the scope of work above, the consultant team is expected to accomplish and submit the following:

- An inception report including:

  - Research methodology including the sampling methodology and the analysis framework,

  - Draft data collection tools,

  - Detailed work plan outlining all tasks to be completed by each of the members of the consultant team for the duration of the endline.

  - Ethical approach, quality control plan, limitations, enumerator training plan,

- In depth quantitative and qualitative analysis of data.

- Complete clean datasets in STATA, inclusive of complete codebooks, and where applicable, consolidated datasets

- Complete transcriptions and translations of qualitative data, as well as sound (audio) files;

- A draft report (in MS Word), following the format required by CARE.

- Presentations of preliminary findings and recommendations validation and feedback with CARE and other stakeholders.

- Final report with corresponding finalized annexes in English.

- 3 success or human-interest stories

- Updated PMF with all the endline value for the indicators

- Professional Skills and Qualifications

Bidders are required to clearly identify and provide detailed CVs for all members of the proposed Evaluation Team. The proposed team composition should collectively demonstrate the technical expertise, contextual understanding, and practical experience necessary to deliver the scope of work and output as outlined in this ToR.

- Advanced degree in education, nutrition, or related field with a minimum of 7 years of evaluation experience.

- Strong understanding of the education, nutrition, and food systems sectors, preferably in the context of home-grown school feeding programs, smallholder agriculture, and community-based food procurement.

- Demonstrated expertise in designing and implementing mixed-methods evaluations, with a focus on education, school feeding, nutrition, and livelihoods.

- Proven capacity in the design, management, and analysis of both quantitative and qualitative data, including triangulation of findings from multiple data sources. Ability to apply robust statistical analysis (using software such as STATA, SPSS, or R) and qualitative analysis techniques (thematic or content analysis).

- Practical experience in conducting gender-sensitive and participatory field research with children, teachers, community members, and farmers in fragile or conflict-affected settings.

- Proven familiarity with the context, including understanding of local governance systems, education and agriculture policies, and socio-cultural dynamics affecting gender and inclusion. Ability to interpret findings contextually and ensure sensitivity to local norms, languages, and cultural considerations.

- Demonstrated capacity to integrate gender, inclusion, and accountability dimensions into research and evaluation processes.

- Strong ability to synthesize complex data into clear, evidence-based analytical reports, policy briefs, and presentations. Excellent command of written and spoken English is required. Knowledge of Somali language and familiarity with local institutional frameworks is desirable.

- Timelines

Bidders are required to include in their detailed work plans the milestones set out below.

| Milestone | Number of days |
| --- | --- |
| Draft Inception Report submitted for review and comments | 4 |
| Final Inception Report + Revised tools submitted | 2 |
| Translation of tools from English to Somali and back translation, electronic versions of tools | 1 |
| Training and Pilot testing | 4 |
| Field data collection | 8 |
| First draft of endline report, stories/cases submitted for review | 5 |
| Review by Project Management and stakeholders completed / comments provided to Supplier | 3 |
| Supplier addresses comments and revises third evaluation round Report | 2 |
| Final evaluation round report and success stories | 1 |
| Total Days | 30 |

- Budget

The budget prepared by the bidder should cover all the activities outlined above, including endline evaluation design, data cleaning, analysis and reporting. This budget is inclusive of all costs covering team member costs, travel except vehicle transport within the country, research costs (enumerators) and any other costs associated the completion of the work including where required costs for reasonable adjustment. Bidders are required to organise and fund their own duty of care arrangements as required.

Bidders are required to provide a fully costed proposal in the form of a price schedule that as a minimum should include:

•	Sub-total of fees for the delivery of any task or deliverable.

•	Sub-total for number of days per partner organisation (as applicable);

•	Expenses and overheads broken down by the project cost categories.

•	Reasonable adjustment costs; and

•	Total costs before and after any taxes that are applicable.

Submission Information / How to Apply

Bidders must download the request for proposal (RFP) attached along with the ToR and complete all required information including attachments where necessary

Please send your complete RFP, technical and financial proposals to this email address som.consultant@care.org clearly marking the subject line “Endline Evaluation of HGSF.” no later than 31th October 2025 11:59 PM.