INVITATION TO BID FOR INDIVIDUAL LOCAL CONSULTANCY

Save the Children International (SCI) Somaliland program hereby invites interested individual local consultants to bid for the consultancy assignment detailed below

| 1 | Title of Consultancy | Terms of Reference for consultancy of Strengthening Climate Change Coordination in Somaliland’s Education Sector. |
| --- | --- | --- |
| 2 | SCI Contracting Office | Save the Children in Somaliland |
| 3 | Period of Consultancy | Total duration will be 40 working days (each local consultant) |
| 4 | Consultant type required | Experienced and relevant Local Individual Consultants (Consultancy Company is not applicable). Two individual local consultants are required in this assignment (one being expert in the coordination mechanism for the education sector and the other being expert in the coordination mechanism for climate change). Please note that two paired individuals or single consultants are allowed in this consultancy. |
| 5 | Responsibility for Logistics arrangements and Costs | Save the children will pay the fee for the local individual consultants in a lump sum and will not reimburse any other costs incurred during the assignment. The consultants will cover their own Logistical arrangements costs; including food, accommodation, local transport, insurance and all cost associated with data collection work. |
| 6 | Taxation Provisions | The consultants shall be responsible for all applicable taxes related to the consultancy services, in accordance with local tax regulations at the SCI contracting office will apply and shall be withheld by SCI. |
| 7 | Travel requirements | Save the Children will cover travel cost outside Hargeisa for the purpose of this consultancy. |
| 8 | Security requirements | The consultants will comply with the standard of Save the Children Security procedures. |
| 9 | Consultant’s Experience Requirement: | This consultancy assignment will focus exclusively on Strengthening Climate Change Coordination in Somaliland’s Education Sector. Applications are invited from qualified individual local consultants with proven expertise in the coordination mechanisms for education and climate change and have contextual understanding of Somaliland’s institutional landscape. |
| 10 | KEY PROFESSIONAL REQUIREMENT |  |
|  | Minimum Qualifications and professional experience |  |
|  | - Advanced degree (Master or PHD) in Education, Curriculum Development, or related field. - At least 10 years’ experience in policy analysis, institutional coordination, or education systems strengthening. - Proven expertise in climate change adaptation and resilience, particularly in fragile or developing country contexts. - Strong understanding of Somaliland or Horn of Africa governance structures. - Experience facilitating multi-stakeholder consultations and workshops. - Demonstrated ability to integrate gender and social inclusion into coordination processes. - Excellent analytical, writing, and communication skills in English. Somali language skills desirable. |  |
| 11 | EVALUATION CRITERIA The proposals submitted by consultants will be evaluated based on the following criteria: |  |
|  | The following award criteria will be used during the evaluation of the technical proposals. Description; Possible Score. Compliance with consultancy requirements: - Responsiveness of the technical proposal to ToR. - Methodology and techniques to be applied well stipulated - Clear description and explanation of tasks in their Scope of Work; 20. Consultant Qualification and Experience: - Qualifications and general experience of the consultant demonstrating specific experience in conducting similar assignments, particularly in Somaliland/Somalia within the past ten years, with reputable organizations. Note – Save the Children has the right to undertake due diligence to verify the references before award; 20. Financial offer: - Reasonability of the costs presented in the financial proposal.; 20. Interview scores; 40. Total Score; 100. |
| 12. | Application Procedure |  |
|  | Candidates interested in the consultancy are expected to provide the following documentation: - A technical proposal with a detailed response to the TOR, with specific focus on the scope of work, methodology and timelines. - Initial work plan and indication of availability - A financial proposal detailing the daily rate - At least copy of one report/contract indicting the successful completion of similar assignments by the individual consultant. - A detailed curriculum vitae (CV) of the consultant with contact details (the CV should include at least three traceable references). |  |
| 13 | Closing date for Applications |  |
|  | Interested consultants are requested to submit their BID applications by following the outlined procedures and send their complete proposals to somaliland.procurement@savethechildren.org no later than 26th November 2025 at 11:59 PM. |  |

### Terms of Reference (ToR)

Strengthening Climate Change Coordination in Somaliland’s Education Sector

- Context and Background

The Climate Smart Education System Initiative (CSESI) was launched in early 2023 by the Global Partnership for Education (GPE) in partnership with Save the Children, UNESCO Education for Sustainable Development Section and UNESCO-IIEP and is implemented in around 35 countries. The initiative seeks to enhance countries’ capacities to mainstream climate change adaptation and environmental sustainability into education sector plans, budgets and strategies as well as to enhance education ministry capacity for cross sectoral coordination on climate and environment-related policy and programming. This involves developing scalable models for this integration and fostering collaboration across all levels to create an environment conducive to building resilience among children and within the education sector.

In Somaliland, education is increasingly vulnerable to climate-related risks such as droughts, flooding, and extreme weather events. While policies such as the 2015 National Environmental Policy and the 2023 National Climate Change Policy recognize the importance of environmental and climate education, coordination between ministries remains limited.

To address this, a Task Team on Climate Change and Education Coordination has been established, comprising senior representatives (Directors General and technical staff) from the Ministry of Education and Science (MoES), the Ministry of Environment and Climate Change (MoECC), the Ministry of Public Works, Land and Housing (MoPWL&H), the National Disaster Preparedness and Food Reserve Authority (NADFOR), and the Project Coordinator/Secretariat from Save the Children International. This Task Team already has an agreed ToR and functions as a high-level platform for inter-ministerial collaboration.
The consultant will work through and strengthen this existing Task Team, supporting its operationalization and ensuring it becomes an effective mechanism for integrating climate change into education sector policies, planning, and implementation.

To ensure its work yields a direct and enduring policy impact, the Task Team's success should be explicitly tied to a pivotal government process, for instance, the formulation of the subsequent Education Sector Strategic Plan (ESSP).

B. Objectives
Overall Objective
To enhance internal and cross-sector coordination for climate change in Somaliland’s education sector, ensuring MoES is well-positioned to lead climate change-smart education planning and policy implementation.

Specific Objectives
Activity 2.1: Assess and map existing climate change coordination mechanisms within MoES and across ministries, using the Task Team as the entry point.
Activity 2.2: Undertake a feasibility study on strengthening MoES’s internal and external coordination on climate change
Activity 2.3: Support the Task Team in identifying and advancing opportunities for cross-ministerial technical engagement and collaboration

Incorporate a specific objective centered on delivering a tangible output—such as the co-development and high-level endorsement of a formalized Inter-Ministerial Coordination Framework—to provide the consultancy with a clear and measurable goal.

C. Scope of Work / Key Tasks
The consultant will carry out the following tasks:

- Activity 2.1: Assessment and Mapping

  - Conduct a specific assessment of climate and education-related budget lines and funding flows across relevant ministries to pinpoint gaps and opportunities in financial coordination.

  - Review existing coordination frameworks, committees, communication protocols, and processes within MoES and across ministries.

  - Identify gaps, redundancies, overlaps, and opportunities for improvement.

  - Prepare a detailed assessment report with actionable recommendations to improve inter-ministerial coordination and ensure alignment with climate resilience objectives, including a focus on gender inclusion

  - Organize a stakeholder workshops and validation meetings through the Task Team

- Activity 2.2: Feasibility Study

  - Examine how MoES can strengthen internal and external coordination on climate change and incorporate a rigorous analysis of the institutional mandates, operational incentives, and potential points of resistance within each ministry.

  - Review comparable models and international best practices.

  - Propose feasible coordination structures (including gender-responsive approaches).

  - Facilitate workshops through the Task Team to validate recommended models.

  - Produce a feasibility study report outlining short-, medium-, and long-term options.

  - Activity 2.3: Cross-Ministerial Technical Engagement

  - Work through the existing Task Team to convene and strengthen inter-ministerial consultations.

  - Identify relevant technical focal points through the task team to include all the technical departments across ministries

  - Organize and deliver capacity-building sessions (training workshops, joint technical working groups or task forces).

  - Support the operationalization of the Task Team by facilitating regular meetings, strengthening communication protocols, supporting joint work planning, and ensuring gender-balanced participation.

  - To solidify stakeholder buy-in and generate early momentum, the Task Team’s work plan will include at least one achievable, high-impact initiative (such as a joint policy brief or a common risk assessment tool) designed to demonstrate early success and strengthen collaboration.

  - Produce a report summarizing opportunities, mechanisms, and agreed next steps.

D. Methodology
The consultant is expected to use a participatory and evidence-based approach, including:

- Desk review of relevant policies, strategies, and international best practices.

- Conduct initial Power/Stakeholder Analysis to diagnose the influence, interests, and relationships of key actors.

- Key informant interviews with Ministry of Education and Science (MoES), Ministry of Public Works, Land and Housing (MoPWL&H), National Disaster Preparedness and Food Reserve Authority (NADFOR), Meteorological department, Ministry of Environment and Climate Change (MoECC), Ministry of Labour Social Affairs and Family, Ministry of Finance & Economic Development, Education Sector Committee members, education partners, including civil society, and organisations focused on gender and social inclusion.

- Task Team workshops for validation and consensus-building.

- Facilitation of technical meetings and trainings to operationalize recommendations.

- E. Deliverables
The consultant will provide the following outputs:

- Inception Report with detailed workplan and methodology (within 2 weeks).

- Assessment Report on existing coordination mechanisms (Activity 2.1).

- Feasibility Study Report with recommended coordination models (Activity 2.2).

- Task Team Action Plan, meeting reports agreed next steps, and coordination outcomes (Activity 2.3).

- Cross-Ministerial Engagement Report summarizing technical collaboration opportunities and capacity-building activities.

- Final Consolidated Report integrating all findings and validated action points. It must include an accompanying executive Policy Brief. This brief should have a designed with visual appeal, and will synthesize key findings and recommendations for the exclusive use of high-level ministry officials

F. Timeline & Duration
The consultancy will be implemented over 12 months, aligned with the workplan:

- Activity 2.1: 3 months

- Activity 2.2: 9 months (overlapping with Activity 2.1 completion)

- Activity 2.3: 12 months (running throughout the consultancy)

To ensure sustainability, the final two months of the consultancy must be designated as a phased handover period, during which the consultant transitions from a leading role to mentoring the Task Team secretariat.

G. Required Qualifications

- Advanced degree in Education Policy, Climate Change, Environmental Governance, or related fields.

- At least 10 years’ experience in policy analysis, institutional coordination, or education systems strengthening.

- Proven expertise in climate change adaptation and resilience, particularly in fragile or developing country contexts.

- Strong understanding of Somaliland or Horn of Africa governance structures.

- Experience facilitating multi-stakeholder consultations and workshops.

- Demonstrated ability to integrate gender and social inclusion into coordination processes.

- Excellent analytical, writing, and communication skills in English. Somali language skills desirable.

H. Management & Reporting
The consultant will report directly to Save the Children Somaliland Country Office, with technical backstopping from the global CSESI team. Day-to-day oversight and validation of deliverables will be carried out through the Task Team.

I. Logistics & Resources

- Save the Children Somaliland will provide:

- Access to relevant documents and data.

- Logistical support for workshops and stakeholder meetings.

- Coordination with the task team, ministries and partners.