Terms of Reference

Consultancy to Conduct Labor Market Assessment in Jowhar with a Particular Focus on IDPs, and Vulnerable Host Communities

Location:		Somalia

Duration: 		30 working days (21st April – 2nd June 2024)

Critical interface: 	Head of Programme, LFS Specialist, Area Managers, LFS Manager, Area

Program Manager

Consultancy type	Open

Travel:			Travel required for this consultancy

Background and context

Jowhar has a rich agricultural landscape, supporting fisheries, rain-fed and irrigated agriculture, as well as animal farming. However, access to the city was severely restricted for aid organizations for some time due to control by Al-Shabaab. The Somali National Army, with assistance from AMISOM, recaptured Jowhar from Al-Shabaab in February 2013, facilitating improved access for humanitarian efforts and development initiatives.

The BREACH Project funded by European Union, spearheaded by the Norwegian Refugee Council (NRC), unfolds as a three-year initiative spanning from 2023 to 2025, with the focal point set in Jowhar, Somalia. As the administrative capital of Hirshabelle state and the Middle Shabelle region, Jowhar holds strategic importance in facilitating durable solutions for displacement-affected communities (DACs). The project's overarching objectives centre on enhancing conditions for durable solutions, promoting livelihood opportunities, facilitating (re)integration, and building capacity among stakeholders. Through targeted interventions, including strengthening housing, land, and property (HLP) rights, improving access to water, sanitation, and hygiene (WASH) facilities, supporting income-generating activities (IGAs), and providing vocational training, the project aims to empower DACs and foster self-reliance for 40,000 beneficiaries in Kongo and Baraki settlements.

Furthermore, by fostering social cohesion and dialogue between DACs and host communities, the project endeavours to facilitate the smooth (re)integration of DACs into the local community fabric. Overall, the BREACH Project endeavours to benefit a substantial number of beneficiaries residing in Jowhar, including DACs, host communities, and other vulnerable populations, thus contributing to sustainable development and resilience in the region.

Objectives of the Study:

- Mapping out the current state of the labor market in Jowhar, including local vocational skills training, farming practices and skills needed, best practices of farming using technologies.

- Providing an overview of current labor market trends, conducting on farm and off farm production-based technologies, and assessing the potential for agricultural courses that are marketable in the context of Hirshabelle.

- Identifying economically feasible sectors and sub-sectors with higher potential for agriculture courses that enable youth to connect to the market.

- Analyzing potential for farm based TVET skills, entrepreneur, and business development, including challenges facing youth entrepreneurs and new entries to agro business in Jowhar.

- Evaluating the capacity of existing Technical and Vocational Education and Training (TVET) and Youth Employment Programs (YEP) service providers for conducting vocational skills training.

- Identifying types of jobs available in the market that can be filled by YEP graduates, with a special focus on highly demanded innovative skills.

- Role of the private sector.

- Analyse the supply and demand of labour:

  - The profile of labour supplies in Jowhar, examining education and skills of labourers.

  - The labour market characteristics and conditions of youth, women and those affected by displacement, and examining their current skill and activity level in the market.

  - The current structure of employment across sectors, examining wages and quality of work.

  - The type of workers and the skills needed in high potential and growth sectors, and determining the wages, to promote the livelihood diversification and economic opportunities for the target population (i.e., those affected by displacement, women and youth).

Methodology:

The consultant/consulting firm is expected to employ the following methodology:

- Thorough desk review of secondary data, including project documents, reports, assessments, and previous labor market surveys.

- Conducting interviews and focus group discussions with key market actors, youth and business associations, displacement-affected communities, learning centers, and government line ministries and institutions.

- Map out the vocational Skills service providers and conduct KII with the skills centers.

- Utilization of a well-designed questionnaire for primary data collection, ensuring a solid evidence base for NRC's livelihood interventions.

- Extensive mapping and analysis of labor market needs, including primary data collection and analysis.

- Collaboration with relevant stakeholders, including vocational training institutes and government departments, to ensure comprehensive participation and inputs.

- Pre-testing of study tools in the field and necessary adjustments based on feedback.

- Data analysis and preparation of draft and final reports, including recommendations for NRC's livelihood interventions.

- Extensive mapping of labour market needs through primary data collection.

- The consultant / firm will review and finalize study tools (Questionnaires FGDs, formal & informal interviews with government officials and community representatives.

- Analysis/tabulation plan development simultaneous with survey questionnaire development

- Conduct data analysis, first level of analysis based on already submitted tabulation plan, giving measurements for all indictors; run frequencies; cross-tabulations, graphs.

- Prepare and submit final report.

- Community and stakeholder in particular Vocational Skills and Training (VST) institutes, agricultural institutes, local universities participation is a crucial element, hence in carrying out the assessment, every effort should be made to include all the relevant stakeholders’ views and ideas towards the private sector and labour market assessment.

Deliverables

- Inception report

- Sampling plan and Filed plan for data collection, checklists for field monitoring.

- Complete tabulation plan (submit just after finalization of the questionnaire)

- Report on enumerators training and study tool pretesting.

- Filed monitoring reports for data collection phase.

- Cleaned dataset

- Submit draft survey report

- Final comprehensive report,

- High resolution pictures (field activity snapshots)

Level of Effort (LOE) – Suggested (consultancy firm may do the breakdown of 30 days as per plan given below and Share-It is subject to modifications as needed)

| S.No. | Activity* | Number of days |
| --- | --- | --- |
| 1 | Review of methodology, questionnaire | 2 |
| 2 | Study tool translation & preparation of study tool | 1 |
| 3 | Training of the surveyors and supervisors with tool pretesting | 2 |
| 4 | Data collection/supervision and monitoring in the field | 15 |
| 5 | Monitoring for data entry and clean dataset | 4 |
| 6 | Data analysis | 2 |
| 7 | Report writing (first draft) | 3 |
| 8 | Final Report | 1 |
| Total consultant LOE |  | 30 days |

* Household survey only

Payment schedule

- Completion of training of surveyors- 25%

- Data collection- 25%

- Submission of final report- 50%

Role of Norwegıan Refugee Councıl

NRC will provide support in the following areas:

- Technical assistance as needed.

- Facilitation of tool/method finalization process.

- Coordination with local line departments for survey approval and facilitation.

- Assistance in hiring enumerators if requested.

- Monitoring ongoing activities in the field, especially enumerator training and data collection.

- Providing feedback for improvement in the draft report.

- Making payments in accordance with the payment schedule.

COMPETENCIES

A research consulting firm/individual with the following qualifications and skills is required:

Key skills

- Degree in economics, agriculture, or related field, with specialization in private sector, labor market analysis, and related areas.

- Strong writing and intercultural communication skills

- Knowledge of the socio-economic environment in Somalia is an added advantage

- Sensitivity to cultural and understanding of political and ethical issues in Somalia

- Demonstrates integrity and fairness, by modelling the NRC values and ethical standards.

- Promotes the vision, mission, and strategic goals of NRC.

- Knowledge of Somali context, region – Southcentral context

Experience:

- Minimum of five (5) years of experience in labor market policy development, planning, and analysis.

- Experience with vocational training and job placement programs

- Similar work experience – in the region – Southcentral is essential.

Education:

- Degree in economics, agriculture, or related field, with specialization in private sector, labor market analysis, and related areas.

Language:

- Proficiency in written and spoken English.

- Good working knowledge of another official language, in particular Arabic is an asset.

Applıcation procedures and requırements

The consultant/consulting firm interested are expected to provide following documentation:

- A technical proposal with detailed response to the TORs, with specific focus on the scope of work, methodology to be used and key selection criteria for respondents.

- Initial work plan based on methodology outlined, and indication of availability

- A financial proposal detailing the daily rate expected and other mode of payment

- Company profile or CVs/ profiles of consultant who shall take lead/ part in this process including a minimum of 3 references

- Detailed budget breakdown based on expected daily rates.

Evaluation of Bid

The Norwegian Refugee Council shall examine the legal documentation and other information submitted by Bidders to verify eligibility and then will review and score bids according to the following criteria.

| Descriptions | Score criteria | Comments |
| --- | --- | --- |
| Completion and inclusion of requested information and supporting documents (Administrative compliance) to be submitted with the application |  |  |
| Copy of company registration – Proof of registration from the country of origin as a limited liability company sole trader/self-employed | 5% | Pass marks to proceed to technical evaluation is 5 points |
| Copy of tax registration | 5% |  |
| Total score criteria (Administrative compliance) | 10% |  |
| Technical supporting documents |  |  |
| A technical proposal of not more than 10 pages outlining how to execute the task with a clear framework, methodology, and timelines. The proposed methodology should demonstrate a clear understanding of the ToR. (Technical evaluation). | 30% |  |
| Previous experiences in similar works/services – Evidence of having agricultural research and assessment (including Greenhouse, Drip irrigation and Hydroponic system). Conducted, led, or participated in the design and successful completion of previous similar TVET and agriculture assessments is added value attracting further consideration in the context of Somalia (Samples of similar work) is required (Technical evaluation). | 30% |  |
| Resume of each team member (Schedules (Key Personnel and Activity schedule) | 10% |  |
| Total score criteria (Technical evaluation) | 80% |  |
| Financial supporting documents |  |  |
| Price in comparison to NRC estimated rate – Proposed budget indicating consultancy fee, logistics cost and all other auxiliary costs in USD (Financial evaluation) | 20% |  |
| Total score criteria (Financial evaluation) | 20% |  |
| Grand total score (Administrative compliance, Technical and Financial evaluation) | 100% | Consultancy |

The whole exercise including report writing should be completed within 30 days of award of the contract.

Submission

All applications should be addressed to so.logistics@nrc.no on or before 11th April 2024 @16:30pm. Referencing “TOR- to conduct labour market assessment in Jowhar” in the subject of the email.