Shabelle Community Development Organization (SHACDO)

Terms Of Reference (ToR)

Engagement of a Technical Consulting Firm for the Design, Development, Deployment, Training and Maintenance Support of an Integrated Enterprise Resource Planning (ERP) System

# 1. BACKGROUND AND CONTEXT

Shabelle Community Development Organization (SHACDO), established on October 21, 2007, is a humanitarian, non-profit, non-governmental organization dedicated to responding to humanitarian emergencies, promoting peace and stability, and implementing long- and short-term development programmes targeting the most vulnerable communities. In delivering these programmes, SHACDO manages financial, procurement, operations, HR, and programme functions that require accurate, timely, and well-controlled information systems. These functions are currently supported by fragmented, largely manual or disconnected systems and spreadsheets, which limit real-time visibility, increase the risk of errors, and constrain the Organization's ability to demonstrate strong internal controls and accountability to its Board, donors, partners and regulators.

To address these gaps, SHACDO intends to design, develop and deploy a comprehensive, integrated Enterprise Resource Planning (ERP) system tailored to the operational and compliance requirements of non-governmental organizations (NGOs). The system is expected to strengthen internal controls, improve transparency and accountability, enhance operational efficiency, and reduce financial, procurement and programmatic risks across the Organization.

SHACDO now wishes to engage a qualified and experienced technical consulting firm ("the Consultant") to deliver this assignment on a turnkey basis, encompassing system development/configuration, data migration/export support, staff training, and post-launch maintenance support.

# 2. OBJECTIVES OF THE ASSIGNMENT

The overall objective is to design, develop, implement and support an integrated, user-friendly and secure ERP system that automates and links SHACDO's Finance, Procurement, Operations, HR and Programmes functions. Specifically, the assignment aims to:

- Design and develop (or configure, if an appropriate existing platform is proposed) an ERP system tailored to NGO operations and donor compliance requirements;

- Strengthen internal controls through automated workflows, approval hierarchies, segregation of duties and complete audit trails;

- Improve transparency and accountability through real-time, accurate and accessible financial and operational reporting;

- Support the secure export, migration and cleansing of existing organizational data from current systems/spreadsheets into the new ERP;

- Build the capacity of SHACDO staff to effectively use, administer and troubleshoot the system through structured training; and

- Provide reliable post-launch maintenance and technical support to ensure system stability, security and continuous improvement.

# 3. SCOPE OF WORK

The assignment is organized into four inter-related components as outlined below.

## 3.1 Component 1: ERP System Design and Development

The Consultant shall:

- Conduct an inception meeting, detailed requirements-gathering exercise and business process review/mapping across Finance, Procurement, Operations, HR and Programmes departments;

- Propose a suitable ERP architecture (cloud-based, on-premise or hybrid) and technology platform, with clear justification of cost, scalability, security and suitability for NGO operations in SHACDO's operating context, including areas with limited connectivity;

- Design and develop/configure the integrated modules summarized in the table below, ensuring seamless interlinkage between modules;

- Design role-based user access controls, approval workflows and segregation-of-duties matrices aligned with SHACDO's financial and operations manuals;

- Ensure the system supports multi-donor, multi-currency and multi-project/grant reporting, and can generate donor-compliant financial and narrative reports;

- Build in audit trail, data backup, disaster recovery and cybersecurity features consistent with good practice and applicable data protection requirements;

- Conduct system testing, including User Acceptance Testing (UAT), and address all defects identified prior to go-live.

| Module | Key Functionality |
| --- | --- |
| Finance & Accounting | General ledger, budgeting, multi-donor/multi-currency accounting, accounts payable/receivable, bank reconciliation, fixed assets, financial reporting compliant with donor and statutory requirements |
| Procurement & Supply Chain | Purchase requisitions, vendor management, competitive bidding/RFQ workflow, purchase orders, goods receipt, inventory/warehouse management, asset tracking |
| Human Resources & Payroll | Staff records, recruitment, leave & attendance, performance management, payroll processing, statutory deductions, contract management |
| Programmes / Grants Management | Project & grant budgeting, donor compliance tracking, results/indicator (M&E) tracking, sub-grantee management, budget vs. actual analysis |
| Internal Controls & Audit | Approval workflows/segregation of duties, audit trails, document management, role-based access controls |
| Reporting & Business Intelligence | Configurable dashboards, donor and management reports, data export in standard formats (Excel, PDF, CSV) |

## 3.2 Component 2: Data Export and Migration Support

The Consultant shall:

- Undertake a data audit/inventory of existing financial, procurement, HR and programme data currently held in legacy systems, spreadsheets and other records;

- Design and execute a data cleansing, validation and migration plan to transfer relevant historical and active data into the new ERP with minimal disruption to operations;

- Support SHACDO to export data and generate reports from the new system in commonly used formats (e.g., Excel, CSV, PDF) for donor reporting, audit and Board purposes;

- Verify and reconcile migrated data against source records, and provide a data migration completion/sign-off report.

## 3.3 Component 3: Capacity Building and Training

The Consultant shall:

- Develop a structured, role-specific training plan and user manuals/standard operating procedures (SOPs) covering system administration, finance, procurement, HR and programmes modules;

- Conduct a Training of Trainers (ToT) for designated super-users/system administrators, as well as end-user training for relevant staff across departments and, where applicable, field offices;

- Provide hands-on, practical training using SHACDO's actual (migrated/test) data, with accompanying job aids, quick-reference guides and recorded training sessions;

- Conduct a post-training competency assessment and provide a training completion report with recommendations for any refresher needs.

## 3.4 Component 4: Post-Launch Maintenance and Support

The Consultant shall:

- Provide a defined period of "hypercare" (intensive on-call) support immediately following go-live to resolve emerging issues promptly;

- Provide ongoing technical maintenance and support (minimum 12 months, renewable) including bug fixes, security patches, system updates and performance monitoring, under a documented Service Level Agreement (SLA) with clearly defined response and resolution times;

- Provide a help-desk/support channel (e.g., phone, email, ticketing system) for SHACDO staff to log and track issues;

- Propose options for ongoing licensing, hosting and support costs beyond the initial contract period, including any exit/handover arrangements and source code/data ownership terms.

# 4. KEY DELIVERABLES

- Inception report, including detailed work plan, methodology and requirements-gathering findings;

- System design document, including architecture, module specifications, workflows and internal control matrix;

- Fully developed/configured and tested ERP system (Finance, Procurement, Operations, HR and Programmes modules);

- Data migration report confirming successful export, cleansing and reconciliation of legacy data;

- Training materials, user manuals/SOPs, and a training completion report;

- User Acceptance Testing (UAT) sign-off report and system go-live confirmation;

- Maintenance and Support Plan/SLA, including hypercare and post-launch support arrangements;

- Final project completion report, including system administrator credentials, source code/configuration documentation (as applicable), and recommendations for future enhancement.

# 5. DURATION AND INDICATIVE TIMELINE

The assignment is expected to be completed within approximately fourteen (14) weeks from contract signing to go-live, followed by a minimum twelve (12)-month post-launch maintenance and support period, renewable by mutual agreement. The Consultant shall submit a detailed work plan with the technical proposal, which may refine the indicative timeline below.

| Phase | Activity | Indicative Duration |
| --- | --- | --- |
| 1 | Inception, requirements gathering & business process mapping | 1 weeks |
| 2 | System design, configuration/development & data architecture | 4 weeks |
| 3 | Data migration/export, integration & user acceptance testing (UAT) | 3 weeks |
| 4 | Staff training (ToT and end-user) | 1 weeks |
| 5 | Go-live, hypercare support & handover | 2 weeks |
| 6 | Post-launch maintenance & support | 12 months (renewable) |

# 6. REQUIRED QUALIFICATIONS AND EXPERIENCE

The Consultant (firm) should demonstrate the following minimum qualifications:

- Registered legal entity with a minimum of five (5) years' experience designing, developing and/or implementing ERP or integrated management information systems;

- Demonstrated prior experience implementing ERP or similar systems for NGOs, UN agencies, or other non-profit/development organizations, including donor compliance and multi-currency/multi-grant reporting requirements;

- A multidisciplinary team with relevant qualifications, e.g., systems/business analysts, software developers, database administrators, data migration specialists, trainers and project management professionals;

- Demonstrated understanding of financial management, procurement and internal control principles applicable to the NGO sector;

- Proven capacity to provide remote and/or on-site post-implementation technical support, including in contexts with limited connectivity;

# 7. EVALUATION CRITERIA

Proposals will be evaluated using a combined technical and financial scoring methodology, with technical proposals weighted at 80% and financial proposals at 20% of the overall technical criteria as detailed below. Only firms attaining a minimum technical score of 70% will have their financial proposals opened and evaluated.

| Criteria | Weight |
| --- | --- |
| Technical capacity, qualifications & relevant experience of the firm/team | 20% |
| Understanding of the assignment & proposed methodology/work plan | 20% |
| Relevant experience developing/implementing ERP systems for NGOs or similar organisations | 20% |
| Training approach and post-implementation maintenance/support plan | 10% |
| Financial proposal (cost-effectiveness and value for money) | 30% |
| Total | 100% |

# 8. PROPOSAL SUBMISSION REQUIREMENTS

Interested firms should submit a technical and financial proposal comprising:

- Company profile, registration/incorporation documents and tax compliance certificate;

- Technical proposal detailing understanding of the assignment, proposed ERP solution/platform, methodology and work plan;

- CVs of key personnel to be assigned to the engagement;

- Detailed, itemized financial proposal covering development, training, licensing (if applicable), and maintenance/support costs; and

- Proposed contract and payment terms, in line with the payment modality set out in Section 9.

Submit proposals, together with all supporting documents, to SHACDO by email at procurement@shacdo.org, with the subject line clearly marked "Technical and Financial Proposal for ERP System," no later than Wednesday, 07 October 2026.

# 9. PAYMENT MODALITY10

Payment to the Consultant shall be made in two (2) instalments, tied to contract signing and satisfactory completion of the assignment, as follows:

30% of the total contract value shall be paid upon signing of the contract and submission and satisfactory acceptance by SHACDO of the Inception Report and Concept Note, including the proposed methodology, detailed work plan, implementation approach, requirements-gathering approach, and proposed system development/configuration plan.

70% of the total contract value shall be paid upon successful completion of the assignment and formal written acceptance by SHACDO of all required deliverables, including system development/configuration, data migration, User Acceptance Testing (UAT), staff training, system go-live, handover, and submission of the final project completion report and related documentation.

All payments shall be subject to satisfactory performance, SHACDO's formal written acceptance of the relevant deliverables, submission of a valid invoice and supporting documentation, and compliance with SHACDO's standard financial procedures.

# 10. REPORTING ARRANGEMENTS AND CONTRACT MANAGEMENT

The Consultant shall report to a designated SHACDO Project Focal Point/ERP Steering Committee comprising representatives from Finance, Procurement, Operations, HR, Programmes and MEAL. The Consultant shall submit periodic progress report/update (at least bi-weekly during implementation) and attend regular review meetings. All deliverables shall require formal written sign-off by SHACDO before the corresponding payment (per Section 9) is processed.

# 11. CONFIDENTIALITY, DATA PROTECTION AND OWNERSHIP

The Consultant shall treat all SHACDO data, records and information accessed during the assignment as strictly confidential and shall not disclose such information to third parties without prior written consent. The Consultant shall implement appropriate data protection and cybersecurity safeguards throughout system design, migration and hosting. Upon contract completion or termination, all source code, system configurations, documentation and data shall remain the sole property of SHACDO, and the Consultant shall provide full handover of administrator access and technical documentation.