## Lot2
Lot 2: consists of the BOQs for the 16 healthcare facilities, as shown below
1 | Dacar-budhuq health center
2 | Awbarkhadle PHU
3 | Sahardiid Health center
4 | Xeedho Health center
5 | Iftin health center
6 | Abdi Idan health center
7 | Sh.Omer health center
8 | Daarasalaam health center
9 | Ilinta Galbeed PHU
10 | baliga- cas PHU
11 | Guryo-Samo heath center
12 | Sh.Nour health center
13 | New Hargiesa health center
14 | Hodan Hills health center
15 | Daami B health center
16 | Ina-Aamin health center
Bill of Quantities (BOQ) for DE Montfort Mark 8a Waste Incinerator
No. | Description | Unit | Quantity | Unit Cost | Total Cost
1 | Foundation and Base
1.1 | Excavation for foundation (0.5m depth, 2m x 2m) | CUM | 2
1.2 | Concrete for foundation (2m x 2m x 0.15m) | CUM | 0.6
2 | Brickwork and Insulation
2.1 | Firebricks for incinerator (230mm x 110mm x 60mm, two layers) | PCS | 400
2.4 | Fire cement and sand for mortar (1:4 mix) | CUM | 0.5
3 | Metal Components
3.1 | Rolled angle (MS) 30x30x3mm thick | Meter | 12
3.2 | Flat sheet (MS) for loading door (600mm x 750mm x 3mm) | Sheet | 1
3.3 | Flat sheet (MS) for ash door (600mm x 750mm x 3mm) | Sheet | 1
3.4 | Flat sheet (MS) for ash door (250mm x 250mm x 3mm) | Sheet | 1
3.5 | Rolled channel (MS) 100x40x5mm thick | Meter | 10
3.6 | Flat sheet (MS) for chimney spigot support (250mm x 250mm x 3mm) | Sheet | 1
3.7 | MS pipe 150 dia x 3mm thick | M | 4
3.8 | Hinges for ash door | Set | 2
3.9 | Pipe (CGI) for loading door hinge (1 inch) | Meter | 1
3.1 | Rod for loading door hinge (3/4 inch) | Meter | 1
3.11 | Masonry plugs, screws No10 | Pack | 1
3.12 | Welding rods | Pack | 1
3.13 | Steel cable 5mm, 7 strand | Meter | 10
3.14 | Ant-corrosion paint to all MS surfaces | Lump Sum | 1
3.15 | The fence wall for the incinerator will be constructed using mesh wire supported by steel angle bars anchored to fixed foundations. It will also include door gates and all necessary accessories. | Lump Sum | 1
5 | Miscellaneous
5.2 | Labor costs include masonry, metalwork, and installation | Lump Sum | 1
5.3 | Transportation of materials | Lump Sum | 1
| Total Cost |  |  |  | 0
| number of health centers required incinerators (Guryosamo, Dacar-budhuq, and Awbarkhadle) | No. | 3 | 0 | 0
Bill of Quantities (BOQ) for Placenta pit
Item No. | Description | Unit | Qty | Unit Cost | Total Cost
1 | Excavation
1.1 | Excavation of pit (2m deep x 1.8m x 1.8m) | CUM | 6.48
2 | Masonry Work
2.1 | 200mm hollow blocks for lining (7.2m perimeter, 2m height) | SQM | 14.4
2.2 | Cement mortar for blockwork (1:4 mix) | CUM | 0.864
3 | Reinforced Concrete Slab Cover
3.1 | Concrete slab (1.8m x 1.8m x 0.15m) | CUM | 0.486
4 | Steel Cover and Vent Chimney Pipe
4.1 | Steel cover (450mm x 450mm) | Number | 1
4.2 | Vent chimney pipe (PVC, 100mm dia, 2m height) | Meter | 2
5 | Drainage Around the Pit
5.1 | Small drainage trench (1m wide, 0.1m deep, 7.2m perimeter) | CUM | 0.72
5.2 | Gravel for drainage | CUM | 0.72
6 | Miscellaneous
6.1 | Formwork for concrete slab | SQM | 3.24
6.2 | Paint for steel cover and vent pipe | Lump Sum | 1
6.3 | Labor costs | Lump Sum | 1
| Total Cost |  |  |  | 0
| number of health facilities required placenta pits (Sh.Nour, Dacar-budhuq, Awbarkadle) | No. | 3 | 0 | 0
Bill of Quantities (BOQ) for water storage tank for delivery room.
No | Description | Quantity | Unit | Unit Price ($) | Total Price ($)
1 | Cylindrical horizontal Rotoplast water tank (2000 liters) | 1 | Pcs
2 | Steel frame structure to hold and mount the tank (3m height). The main holding bars should be galnazied 2 inch | 1 | lsm
3 | Concrete foundation materials (cement, sand, gravel) | 1 | lsm
4 | Bolts, nuts, and fasteners for assembling the frame | 1 | Set
5 | water pipes, tape/faucets, and connectors | 1 | set
6 | Anti-corrosion paint and primer for steel frame | 8 | Liters
7 | Labor for welding and assembling the steel frame | 1 | Job
8 | Transportation of tank and materials to the site | 1 | Job
9 | Contingency for any additional small items. | 1 | Lsm
Total Cost one water storage tank |  |  |  |  | 0
A number of health facilities required water storage tanks (Dacar-budhuq, Awbarkhadle, Iftin, Sh.Omer, Abdi-Idan, Daami B, Ina-Amin, New-Haregisa, Hodan hills, Ilinta-galbeed, Galiga-cas) |  | No. | 12 | 0 | 0
Rehabilitation works for Dacar-budhuq Health center
Bill of Quantities (BOQ) for rehabilitation works
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1. Rehabilitation of the 4 rooms through the painting/doors/windows/tiles
1.1 | Apply a two-coat paint system on the interior and exterior walls of the four rooms. Before painting, ensure the walls are cleaned, inspected for any damage, and primed where necessary. Use high-quality paint for a durable and professional finish. | Sq.m | 240
1.2 | Replace 8 windows with aluminum sliding frames includes the service costs | Pcs | 8
1.3 | Replace 4 doors to the four rooms | Pcs | 4
1.4 | Placement of tiles for the EPI room | Sqm | 25
| Sub-total costs for the rehabilitations of 4 rooms painting, titles for one room, and windows/doors |  |  |  | 0
2 | Installation of Handwashing Basin
2.1 | installation of handwashing basin including the water pipes connecting the water storage tank and its waste pipes, as well as labor cost | Job | 1
| Sub-total for the handwashing basin |  |  | 2 | 0
3 | Ceilings
3.1 | Replace cracked/damaged ceilings with new ceilings for some rooms | Lump Sum | 1
3.2 | Tie previous ceilings and fix where possible | Lump Sum | 1
| Total costs for the rehabilitation ceiling |  |  |  | 0
| Total costs of the rehabilitations in the Dacabudhuq HC |  |  |  | 0
Rehabilitation works for Awbarkhadle PHU
Bill of Quantities (BOQ) for rehabilitation works
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
2 | Installation of Handwashing Basin
2.1 | Purchase of the handwashing basin | Pcs | 1
2.2 | 30m small pipe connection from elevated water storage tank | m | 30
2.3 | Water tap, valve, nipples, and sockets | Set | 1
2.4 | Labor for installation and service costs | Lump Sum | 1
| Sub-total for the handwashing basin |  |  | 2 | 0
3 | Construction of Pateint/Disabled Access Ramps
3.1 | The access ramp is needed for patients and individuals using wheelchairs at the main gate. | Lsm | 1
| Total cost for the ramps for Pateint/disabled people |  |  |  | 0
| Total costs of the rehabilitations in the Awbarkadle PHU |  |  |  | 0
WASH/REHABILITATIONS OF THE Sahardiid health center
Bill of Quantities (BOQ) for rehabilitation works for Sahardiid HC.
| Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1 | BOQ for for Shading Space Construction
1.1 | 2-inch Holding galvanized Steel Bars (8m length; approx. 6 pieces needed) | Pieces | 6
1.2 | 28-Gauge Iron Sheets (3.5m width x 10m length) | S.q,s | 35
1.3 | Labor Costs for Installation | Lsm | 1
1.4 | Fasteners and Accessories (nuts, bolts, etc.) | Lot | 1
1.5 | Miscellaneous (transportation, tools, etc.) | Lsm | 1
| Sub total cost for the shading area |  |  |  | 0
2 | Rehabilitation of external protective network frame structure
2.1 | The external protective frame network structure for two windows includes installation costs. | Pcs | 2
| Total cost for windows rehabilitations |  |  |  | 0
| Grand total costs of the covering the gaps in the Sahardiid HC |  |  |  | 0
Rehabilitation works for Xeedho Health center
Bill of Quantities (BOQ) for rehabilitation works for Xeedho HC.
| Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1 | BOQ for for Shading Space Construction
1.1 | 2-inch Holding galvanized Steel Bars (8m length; approx. 8 pieces needed) | Pieces | 8
1.2 | 28-Gauge Iron Sheets (8.5m width x 12m length) | S.q,s | 102
1.3 | Labor Costs for Installation | Lsm | 1
1.4 | Fasteners and Accessories (nuts, bolts, etc.) | Lot | 1
1.5 | Miscellaneous (transportation, tools, etc.) | Lsm | 1
| Sub-total for shading area |  |  |  | 0
2 | Lay somaliland tiles in the area (12m x 8.5m)
2.1 | Qualified sand filling and compacting | Lsm | 1
2.2 | Lay Somaliland tiles | m² | 102
| Sub-total for somaliland tiles |  |  |  | 0
3 | Rehabilitation of windows/doors
3.1 | 5 windows needs rehabilitation to prevent the raining water | Pcs | 5
3.2 | Rehabilitation of two doors by changing the locksets | pcs | 2
| Sub-total cost for the doors/windows |  |  |  | 0
| Total rehabilitation costs of the Heedho HC |  |  |  | 0
Rehabilitation works for Iftin Health center
Bill of Quantities (BOQ) for rehabilitation works for IFTIN HC
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1. Rehabilitation of the 4 rooms through the painting/doors/windows.
1.1 | Apply a two-coat paint system on the interior and exterior walls of the four rooms. Before painting, ensure the walls are cleaned, inspected for any damage, and primed where necessary. Use high-quality paint for a durable and professional finish. | Sq.m | 240
1.2 | Replace 6 windows with aluminum sliding frames includes the service costs | Pcs | 6
1.3 | Replace 5 doors to the four rooms | Pcs | 5
| Sub-total costs for the rehabilitations of 4 rooms painting, titles for one room, and windows/doors |  |  |  | 0
2 | Rehabilitation of Handwashing Basin in the delivery room, and laborotry
2.1 | 40m pipe connection from elevated water storage tank | m | 40
2.2 | Water tap, valve, nipples, and sockets | Set | 1
2.3 | Labor for installation and service costs | Lump Sum | 1
| Sub-total for the handwash rehabilitation |  |  | 2 | 0
| Total rehabilitation works for the IFTIN HC |  |  |  | 0
| Total costs of the rehabilitations in the IFTIN HC |  |  |  | 0
Bill of Quantities (BOQ) for rehabilitation works for Abdi Idan.
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1. Rehabilitation of the 3 rooms through the painting/doors/windows
1.1 | Apply a two-coat paint system on the interior and exterior walls of the three rooms. Before painting, ensure the walls are cleaned, inspected for any damage, and primed where necessary. Use high-quality paint for a durable and professional finish. | Sq.m | 180
1.2 | Replace 6 windows with aluminum sliding frames includes the service costs | Pcs | 6
1.3 | reolacement of 4 doors new doors to the four rooms | Pcs | 4
| Sub-total costs for the rehabilitations, windows/doors |  |  |  | 0
2 | Rehabilitation of Handwashing Basin
2.1 | 50m small pipe connection from elevated water storage tank | m | 50
2.2 | Water tap, valve, nipples, and sockets | Set | 1
2.3 | Labor for installation and service costs | Lump Sum | 1
| Sub-total for the 4 handwash basin rehabilitation |  |  | 4 | 0
3 | Construction of Disabled Access Ramps
3.1 | The ramp access for patient and disabled people | Lsm | 1
| Total cost for the ramps for Pateint/disabled people |  |  |  | 0
6 | Latrines
6.1 | rehabilitation of toilet seats in the delivery toilet | Pcs | 1
6.2 | Rehabilitation of the 4 doors for toilets includes the delivery latrine through the whitewashing and painting of toilets. | Lsm | 1
| Total costs for latrine rehabilitations |  |  |  | 0
Total rehabilitation costs for the Abdi idan HC |  |  |  |  | 0
Rehabilitation works for Sh.Omer Health center
Bill of Quantities (BOQ) for rehabilitation works for Sh.Omer HC
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1. Rehabilitation of the 3 rooms through the painting/doors/windows
1.1 | Rehabilitation of the doors includes replacing the locksets and repairing the main gate. | Pcs | 4
1.2 | Replace 2 windows with aluminum sliding frames includes the service costs | Pcs | 2
| Sub-total costs for the rehabilitations and windows/doors |  |  |  | 0
2 | Rehabilitation of Handwashing Basin
2.1 | 50m small pipe connection from elevated water storage tank | m | 50
2.2 | Water tap, valve, nipples, and sockets | Set | 1
2.3 | Labor for installation and service costs | Lump Sum | 1
| Sub-total for the 3 handwash basin rehabilitation |  |  | 3 | 0
3 | Construction of Pateint/Disabled Access Ramps
3.1 | The access ramp is needed for patients and individuals using wheelchairs. This sho | Lsm | 1
| Total cost for the ramps for Pateint/disabled people |  |  |  | 0
4 | Latrines
4.1 | Rehabilitation of public toilet seats and inspection of the waste pipe in the one public toilet | Pcs | 1
| Total costs for latrine rehabilitations |  |  |  | 0
Total rehabilitation costs for the Sh.Omer HC |  |  |  |  | 0
Rehabilitation works for Daarasalam Health center
Bill of Quantities (BOQ) for rehabilitation works for Dara Salaam MCH
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1 | Rehabilitation of Handwashing Basin and WC
1.1 | 25m small pipe connection from elevated water storage tank | m | 25
1.2 | Rehabilitating flushing of WC and Sanitariy hand washing | Lsm | 1
1.3 | Water tap, valve, nipples, and sockets | Set | 1
1.4 | Labor for installation and service costs | Lump Sum | 1
1.5 | Fixing the handle doors | Lsm | 1
| Sub-total for the handwash and WC rehabilitation |  |  |  | 0
2 | Rehabilitation of Waiting Area
2.1 | Wall washing/and painting | m² | 30
2.2 | Tie and fix the previous ceilings | Lump Sum | 1
2.3 | A permanent brick platform, up to 0.8 meters in height, will be constructed in the waiting area under the guidance of the ALIGHT engineer. | Lum Sum | 1
2.4 | To create a childfrendly environment the artist should be drawn friendly animals or cartoons by using bright different colors | Lum Sum | 1
| Total costs for the rehabilitation of the waiting area |  |  |  | 0
3 | Construction of Disabled Access Ramps
3.1 | The main door ramp (including labor and materials) ensures a standard slope of no more than 1:12, with non-slip surfaces. | Lump Sum | 1
3.2 | Care rooms ramp (including labor and materials) ensures a standard slope of no more than 1:12, with non-slip surfaces. | Lump Sum | 1
| Sub-total cost for the ramps for disabled people |  |  |  | 0
4 | Rehabilitation of the painting wall
4.1 | Apply a two-coat paint system on the interior and exterior walls of the delivery room, ward, and nutrition room. Before painting, ensure the walls are cleaned, inspected for any damage, and primed where necessary. Use high-quality paint for a durable and professional finish. | Sq.m | 630
| Total Estimated for the rehabilitated Costs: |  |  |  | 0
1 | Installation of Handwashing Basin
1.1 | installation of handwashing basin including the water pipes connecting the water storage tank and its waste pipes, as well as labor cost | Job | 1
| Sub-total for the handwashing basin |  |  | 2 | 0
Total rehabilitation costs for the Daarasalaam Health center |  |  |  |  | 0
Rehabilitation works Ilinta galbeed PHU
Bill of Quantities (BOQ) for rehabilitation works
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1 | Rehabilitation of Handwashing Basin and WC
1.1 | 25m small pipe connection from elevated water storage tank to handwashing toilet and handwashing facility. | m | 6
1.2 | Rehabilitating flushing of WC and its handwashing facility | Lsm | 1
1.3 | Water tap, valve, nipples, and sockets | Set | 1
1.4 | Labor for installation and service costs | Lump Sum | 1
1 | Installation of Handwashing Basin
2.1 | installation of handwashing basin including the water pipes connecting the water storage tank and its waste pipes, as well as labor cost | Job | 1
| Total costs for rehabilitation workd for Ilinta Galbeed PHU |  |  |  | 0
Rehabilitation works of Baliga-cas PHU
Bill of Quantities (BOQ) for rehabilitation works for Balayga Cas PHU
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1. Delivery Room & Ward
1.1 | Apply a two-coat paint system on the interior and exterior walls of the delivery room, ward, and nutrition room. Before painting, ensure the walls are cleaned, inspected for any damage, and primed where necessary. Use high-quality paint for a durable and professional finish. | Sq.m | 288
1.2 | Replace 4 windows with aluminum sliding frames includes the service costs | Pcs | 4
1.3 | Rehabilitate 3 doors (replace door frames, paint) | Lsm | 3
| Sub-total costs for the rehabilitations of deliver room, ward& nutritional room & other windows/doors |  |  |  | 0
2 | Rehabilitation of Handwashing Basin and WC
2.1 | 25m small pipe connection from elevated water storage tank | m | 25
2.2 | Rehabilitating flushing of WC and Sanitariy hand washing | Lsm | 1
2.3 | Water tap, valve, nipples, and sockets | Set | 1
2.4 | Labor for installation and service costs | Lump Sum | 1
| Sub-total for the handwash and WC rehabilitation |  |  | 1 | 0
3 | Ceilings
3.1 | Plastering the bottom of the slab with ratio 1:4 | sqm | 4
| Total costs for the rehabilitation ceiling |  |  |  | 0
4 | Rehabilitation of Waiting Area
4.1 | Wall washing/and painting | m² | 30
4.2 | Tie and fix the previous ceilings | Lump Sum | 1
4.3 | A permanent brick platform, up to 0.8 meters in height, will be constructed in the waiting area under the guidance of the ALIGHT engineer. | Lum Sum | 1
4.4 | To create a childfrendly environment the artist should be drawn friendly animals or cartoons by using bright different colors | Lum Sum | 1
| Total costs for the rehabilitation of the waiting area |  |  |  | 0
5 | Construction of Disabled Access Ramps
5.1 | The main door ramp (including labor and materials) ensures a standard slope of no more than 1:12, with non-slip surfaces. | Lump Sum | 1
5.2 | Care rooms ramp (including labor and materials) ensures a standard slope of no more than 1:12, with non-slip surfaces. | Lump Sum | 1
| Total cost for the ramps for disabled people |  |  |  | 0
6 | Latrines
6.1 | rehabilitation of toilet seats in 2 toilets | No. | 2
6.2 | Rehabilitation of the 2 doors for toilets, whitewashing and painting of toilets. | Lum sum | 2
| Total costs for latrine rehabilitations |  |  |  | 0
| Total costs of the rehabilitation works of Baliga-cas PHU |  |  |  | 0
Rehabilitation for Guryo Samo health center
Bill of Quantities (BOQ) for Rehabilitation for Guryo Samo MCH
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1 | Repairing and fixing water pipes, tabs, and sanitary pipes
1.1 | Repairing and fixing water pipes, tabs, and sanitary pipes | Lsm | 1
| Sub-total cost for the ramps for disabled people |  |  |  | 0
2 | Apply a two-coat paint system on the interior and exterior walls of the delivery room, ward, and nutrition room. Before painting, ensure the walls are cleaned, inspected for any damage, and primed where necessary. Use high-quality paint for a durable and professional finish. | Sq.m | 420
3 | Replace 5 doors with aluminum frames including the service costs | Pcs | 6
| Total rehabilitation costs for the Guryasamo health center |  |  |  | 0
Rehabilitation for Sh.Nour health center
Bill of Quantities (BOQ) for rehabilitation works for Sheikh Nour
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1 | Rehabilitation of plumbing and side drainage
1.1 | Construction side drainage 0.5x0.2x12 | m3 | 1
1.2 | Repairing water pipes system at the latrines and handwashing and including lintel security repairing | Lum Sum | 1
1.3 | Two coats and desmtepring of white-washing on all wall faces and ceiling with lime/white glue ratio on all interior wall surfaces to be smoothed thoroughly before paint applied. | sq.m | 600
1.4 | Security fence wiring of wall protection | Lsm | 1
| Total costs for the rehabilitation of the waiting area |  |  |  | 0
2 | Installation of Handwashing Basin
2.1 | installation of handwashing basin including the water pipes connecting the water storage tank and its waste pipes, as well as labor cost | Job | 1
| Sub-total for the handwashing basins at two stations |  |  | 2 | 0
| Total rehabilitated costs for Sh.Nour health center |  |  |  | 0
Rehabilitation for New Hargeisa health center
Bill of Quantities (BOQ) for Rehabilitation for New Hargeisa MCH
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1 | Repairing and fixing water pipes, tabs, and sanitary pipes
1.1 | Repairing and fixing water pipes, tabs, and sanitary pipes | Lsm | 1
| Sub-total costs for repairing pipes |  |  |  | 0
2 | Apply a two-coat paint system on the interior and exterior walls of the delivery room, ward, and nutrition room. Before painting, ensure the walls are cleaned, inspected for any damage, and primed where necessary. Use high-quality paint for a durable and professional finish. | Sq.m | 400
3 | Rehabilitation walls draining and providing proper drainage | Lsm | 1
4 | Demolishing the old flooring of two public latrines | Sq.m | 6.48
5 | Contruction of flooring tiles 40x40 | Sq.m | 7.5
6 | Intalling trukish Seats for two toilets | PCs | 2
| Sub-total costs for the rehabilitations |  |  |  | 0
Total costs for the New Hargeisa MCH need to be the center of excellence. |  |  |  |  | 0
Rehabilitation for Hodan Hills health Center
Bill of Quantities (BOQ) for rehabilitation works
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1 | Construction of Disabled Access Ramps
1.1 | The main door ramp (including labor and materials) ensures a standard slope of no more than 1:12, with non-slip surfaces. | Lump Sum | 1
1.2 | Care rooms ramp (including labor and materials) ensures a standard slope of no more than 1:12, with non-slip surfaces. | Lump Sum | 1
| Sub-total cost for the ramps for disabled people |  |  |  | 0
2 | Installation of Handwashing Basin
2.1 | installation of handwashing basin including the water pipes connecting the water storage tank and its waste pipes, as well as labor cost | Job | 1
| Sub-total for the handwashing basin |  |  | 1 | 0
Total costs for the rehabilitations of Hodan Hillis Health Center |  |  |  |  | 0
Rehabilitation for Daami B health Center
Bill of Quantities (BOQ) for rehabilitation works
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1 | Rehabilitation of Flooring and plumbing
1.1 | Demolishing flooring plain mortared | m² | 3.24
1.2 | Construction flooring tiles 40x40 | m² | 3.4
1.3 | Installation water pipes system at the latrines and handwashing stations and connect to the new water tank | Lum Sum | 1
1.4 | Installation WC with its fittings | Lum Sum | 1
| Total costs for the rehabilitation of the flooring and plumbing |  |  |  | 0
2 | Construction of Disabled Access Ramps
2.1 | The main door ramp (including labor and materials) ensures a standard slope of no more than 1:12, with non-slip surfaces. | Lump Sum | 1
2.2 | Care rooms ramp (including labor and materials) ensures a standard slope of no more than 1:12, with non-slip surfaces. | Lump Sum | 1
| Sub-total cost for the ramps for disabled people |  |  |  | 0
3 | Replacements of the Windows/Doors and surrounding walls
3.1 | Replace 12 windows with aluminum sliding frames includes the service costs | Pcs | 12
3.2 | Replace 8 doors with aluminum frames including the service costs | Pcs | 8
3.3 | Painting of walls with combination of white washing, stucco, and destempering | Sq.m | 3.12
| Sub- total |  |  |  | 0
| Total costs for rehabilitation it the Daami B health center |  |  |  | 0
Rehabilitation for Ina Amin health Center
Bill of Quantities (BOQ) for the rehabilitaiton works
Item No. | Description of Work | Unit | Quantity | Unit Cost (USD) | Total Cost (USD)
1 | Construction of Disabled Access Ramps
1.1 | The main door ramp (including labor and materials) ensures a standard slope of no more than 1:12, with non-slip surfaces. | Lump Sum | 1
1.2 | Care rooms ramp (including labor and materials) ensures a standard slope of no more than 1:12, with non-slip surfaces. | Lump Sum | 1
| Sub-total cost for the ramps for disabled people |  |  |  | 0
2 | Installation of Handwashing Basin
2.1 | installation of handwashing basin including the water pipes connecting the water storage tank and its waste pipes, as well as labor cost | Job | 1
| Sub-total for the handwashing basin |  |  | 1 | 0
Total costs for rehabilitations for the Ina Amin health center. |  |  |  |  | 0
Total costs for the WASH, WMF, and REHABILITATION WORKS IN LOT2
No. | Descriptions | Unit | QTY | RATES | TOTALS
1 | Incinerators | No. | 3
2 | Placenta pits | No. | 3
3 | Water storage tanks | No. | 12
4 | Dacar-budhuq health center | No. | 1
5 | Awbarkhadle PHU | No. | 1
6 | Sahardiid Health center | No. | 1
7 | Xeedho Health center | No. | 1
8 | Iftin health center | No. | 1
9 | Abdi Idan health center | No. | 1
10 | Sh.Omer health center | No. | 1
11 | Daarasalaam health center | No. | 1
12 | Ilinta Galbeed PHU | No. | 1
13 | baliga- cas PHU | No. | 1
14 | Guryo-Samo heath center | No. | 1
15 | Sh.Nour health center | No. | 1
16 | New Hargiesa health center | No. | 1
17 | Hodan Hills health center | No. | 1
18 | Daami B health center | No. | 1
19 | Ina-Aamin health center | No. | 1
| Total costs of the lot 2 |  |  |  | 0

## Budget summary
No. | Lots | Budget summary
1 | Total cost of lot2: 16 health facilities
2
3
4
Total Budget