## WP
Construction of 21 emergency standard latrines and 3 Disability friendly latrines for IDPs in Baidoa, including visibility writing
Note: The instructions for completing the Work Plan are provided in the next sheet of this template. Tenderers are required to carefully read and understand the instructions before filling in the activity durations and implementation schedule. The final work plan should be signed and stamped by the tenderer.
No | Task | Month (…) | [30 empty] | Month (….) | [30 empty] | Month (….)
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1
2
3
4
5
6
7
8
9
10
11
12

## Instruction
Instructions Sheet
You are requested to submit a comprehensive Work Plan detailing the approach, sequence, and timeframe for completing the project in accordance with the technical specifications and schedule. The Work Plan will form part of the evaluation criteria and should clearly demonstrate your ability to manage and execute the works effectively. Your Work Plan should include, but not be limited to, the following key activities: Preparation and acquisition of required permits and approvals, Mobilization of resource both human and equipment, Site clearing, setting out, and layout verification, latrine construction, and final handover In addition, the plan should specify: Expected duration for each activity (Standard latrine construction and disability latrine construction), Key milestones and dependencies between tasks, Responsible personnel and resources, Quality assurance and safety measures and Any proposed methods to enhance efficiency or quality Tenderers are advised to amend the provided template as necessary to reflect their proposed methodology and timeline. Please also attach any supporting documents (such as schedules, charts, equipment lists, or technical notes) and additional information deemed relevant to strengthen your submission.